## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Supply and installation of Printed Wooden Frame Flex Banner Size: 8' x 4' for Creating Public Awareness on Water & Sanitation and General Health & Hygiene for 10 days (from 08.01.2023 to 17.01.2023) at Lot-8 - 200 nos. as per direction & satisfaction of the EIC in connection with G.S. Mela 2023 under Diamond Harbour Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001528/2022-2023 | 429/DHSD | 19/12/2022 | 29/12/2022 | SUMAN INDUSTRIES PVT. LTD. | 2.83 | 2.83 | 100 | 90
2 | BANKURA |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Supply and installation of Printed Wooden Frame Flex Banner Size: 8' x 4' for Creating Public Awareness on Water & Sanitation and General Health & Hygiene for 10 days (from 08.01.2023 to 17.01.2023) at Lot-8 - 200 nos. as per direction & satisfaction of the EIC in connection with G.S. Mela 2023 under Diamond Harbour Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001528/2022-2023 | 429/DHSD | 19/12/2022 | 29/12/2022 | SUMAN INDUSTRIES PVT. LTD. | 2.83 | 2.83 | 100 | 90
3 | BIRBHUM |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Supply and installation of Printed Wooden Frame Flex Banner Size: 8' x 4' for Creating Public Awareness on Water & Sanitation and General Health & Hygiene for 10 days (from 08.01.2023 to 17.01.2023) at Lot-8 - 200 nos. as per direction & satisfaction of the EIC in connection with G.S. Mela 2023 under Diamond Harbour Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001528/2022-2023 | 429/DHSD | 19/12/2022 | 29/12/2022 | SUMAN INDUSTRIES PVT. LTD. | 2.83 | 2.83 | 100 | 90
4 | COOCHBEHAR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Supply and installation of Printed Wooden Frame Flex Banner Size: 8' x 4' for Creating Public Awareness on Water & Sanitation and General Health & Hygiene for 10 days (from 08.01.2023 to 17.01.2023) at Lot-8 - 200 nos. as per direction & satisfaction of the EIC in connection with G.S. Mela 2023 under Diamond Harbour Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001528/2022-2023 | 429/DHSD | 19/12/2022 | 29/12/2022 | SUMAN INDUSTRIES PVT. LTD. | 2.83 | 2.83 | 100 | 90
5 | DAKSHIN DINAJPUR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Supply and installation of Printed Wooden Frame Flex Banner Size: 8' x 4' for Creating Public Awareness on Water & Sanitation and General Health & Hygiene for 10 days (from 08.01.2023 to 17.01.2023) at Lot-8 - 200 nos. as per direction & satisfaction of the EIC in connection with G.S. Mela 2023 under Diamond Harbour Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001528/2022-2023 | 429/DHSD | 19/12/2022 | 29/12/2022 | SUMAN INDUSTRIES PVT. LTD. | 2.83 | 2.83 | 100 | 90
6 | DARJEELING |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Supply and installation of Printed Wooden Frame Flex Banner Size: 8' x 4' for Creating Public Awareness on Water & Sanitation and General Health & Hygiene for 10 days (from 08.01.2023 to 17.01.2023) at Lot-8 - 200 nos. as per direction & satisfaction of the EIC in connection with G.S. Mela 2023 under Diamond Harbour Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001528/2022-2023 | 429/DHSD | 19/12/2022 | 29/12/2022 | SUMAN INDUSTRIES PVT. LTD. | 2.83 | 2.83 | 100 | 90
7 | HOOGHLY |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Supply and installation of Printed Wooden Frame Flex Banner Size: 8' x 4' for Creating Public Awareness on Water & Sanitation and General Health & Hygiene for 10 days (from 08.01.2023 to 17.01.2023) at Lot-8 - 200 nos. as per direction & satisfaction of the EIC in connection with G.S. Mela 2023 under Diamond Harbour Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001528/2022-2023 | 429/DHSD | 19/12/2022 | 29/12/2022 | SUMAN INDUSTRIES PVT. LTD. | 2.83 | 2.83 | 100 | 90
8 | HOWRAH |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Supply and installation of Printed Wooden Frame Flex Banner Size: 8' x 4' for Creating Public Awareness on Water & Sanitation and General Health & Hygiene for 10 days (from 08.01.2023 to 17.01.2023) at Lot-8 - 200 nos. as per direction & satisfaction of the EIC in connection with G.S. Mela 2023 under Diamond Harbour Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001528/2022-2023 | 429/DHSD | 19/12/2022 | 29/12/2022 | SUMAN INDUSTRIES PVT. LTD. | 2.83 | 2.83 | 100 | 90
9 | JALPAIGURI |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Supply and installation of Printed Wooden Frame Flex Banner Size: 8' x 4' for Creating Public Awareness on Water & Sanitation and General Health & Hygiene for 10 days (from 08.01.2023 to 17.01.2023) at Lot-8 - 200 nos. as per direction & satisfaction of the EIC in connection with G.S. Mela 2023 under Diamond Harbour Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001528/2022-2023 | 429/DHSD | 19/12/2022 | 29/12/2022 | SUMAN INDUSTRIES PVT. LTD. | 2.83 | 2.83 | 100 | 90
10 | JHARGRAM |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Supply and installation of Printed Wooden Frame Flex Banner Size: 8' x 4' for Creating Public Awareness on Water & Sanitation and General Health & Hygiene for 10 days (from 08.01.2023 to 17.01.2023) at Lot-8 - 200 nos. as per direction & satisfaction of the EIC in connection with G.S. Mela 2023 under Diamond Harbour Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001528/2022-2023 | 429/DHSD | 19/12/2022 | 29/12/2022 | SUMAN INDUSTRIES PVT. LTD. | 2.83 | 2.83 | 100 | 90
11 | KALIMPONG |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Supply and installation of Printed Wooden Frame Flex Banner Size: 8' x 4' for Creating Public Awareness on Water & Sanitation and General Health & Hygiene for 10 days (from 08.01.2023 to 17.01.2023) at Lot-8 - 200 nos. as per direction & satisfaction of the EIC in connection with G.S. Mela 2023 under Diamond Harbour Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001528/2022-2023 | 429/DHSD | 19/12/2022 | 29/12/2022 | SUMAN INDUSTRIES PVT. LTD. | 2.83 | 2.83 | 100 | 90
12 | MALDAH |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Supply and installation of Printed Wooden Frame Flex Banner Size: 8' x 4' for Creating Public Awareness on Water & Sanitation and General Health & Hygiene for 10 days (from 08.01.2023 to 17.01.2023) at Lot-8 - 200 nos. as per direction & satisfaction of the EIC in connection with G.S. Mela 2023 under Diamond Harbour Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001528/2022-2023 | 429/DHSD | 19/12/2022 | 29/12/2022 | SUMAN INDUSTRIES PVT. LTD. | 2.83 | 2.83 | 100 | 90
13 | MURSHIDABAD |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Supply and installation of Printed Wooden Frame Flex Banner Size: 8' x 4' for Creating Public Awareness on Water & Sanitation and General Health & Hygiene for 10 days (from 08.01.2023 to 17.01.2023) at Lot-8 - 200 nos. as per direction & satisfaction of the EIC in connection with G.S. Mela 2023 under Diamond Harbour Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001528/2022-2023 | 429/DHSD | 19/12/2022 | 29/12/2022 | SUMAN INDUSTRIES PVT. LTD. | 2.83 | 2.83 | 100 | 90
14 | NADIA |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Supply and installation of Printed Wooden Frame Flex Banner Size: 8' x 4' for Creating Public Awareness on Water & Sanitation and General Health & Hygiene for 10 days (from 08.01.2023 to 17.01.2023) at Lot-8 - 200 nos. as per direction & satisfaction of the EIC in connection with G.S. Mela 2023 under Diamond Harbour Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001528/2022-2023 | 429/DHSD | 19/12/2022 | 29/12/2022 | SUMAN INDUSTRIES PVT. LTD. | 2.83 | 2.83 | 100 | 90
15 | NORTH 24 PARGANAS |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Supply and installation of Printed Wooden Frame Flex Banner Size: 8' x 4' for Creating Public Awareness on Water & Sanitation and General Health & Hygiene for 10 days (from 08.01.2023 to 17.01.2023) at Lot-8 - 200 nos. as per direction & satisfaction of the EIC in connection with G.S. Mela 2023 under Diamond Harbour Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001528/2022-2023 | 429/DHSD | 19/12/2022 | 29/12/2022 | SUMAN INDUSTRIES PVT. LTD. | 2.83 | 2.83 | 100 | 90
16 | PASCHIM BARDHAMAN |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Supply and installation of Printed Wooden Frame Flex Banner Size: 8' x 4' for Creating Public Awareness on Water & Sanitation and General Health & Hygiene for 10 days (from 08.01.2023 to 17.01.2023) at Lot-8 - 200 nos. as per direction & satisfaction of the EIC in connection with G.S. Mela 2023 under Diamond Harbour Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001528/2022-2023 | 429/DHSD | 19/12/2022 | 29/12/2022 | SUMAN INDUSTRIES PVT. LTD. | 2.83 | 2.83 | 100 | 90
17 | PASCHIM MEDINIPUR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Supply and installation of Printed Wooden Frame Flex Banner Size: 8' x 4' for Creating Public Awareness on Water & Sanitation and General Health & Hygiene for 10 days (from 08.01.2023 to 17.01.2023) at Lot-8 - 200 nos. as per direction & satisfaction of the EIC in connection with G.S. Mela 2023 under Diamond Harbour Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001528/2022-2023 | 429/DHSD | 19/12/2022 | 29/12/2022 | SUMAN INDUSTRIES PVT. LTD. | 2.83 | 2.83 | 100 | 90
18 | PURBA BARDHAMAN |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Supply and installation of Printed Wooden Frame Flex Banner Size: 8' x 4' for Creating Public Awareness on Water & Sanitation and General Health & Hygiene for 10 days (from 08.01.2023 to 17.01.2023) at Lot-8 - 200 nos. as per direction & satisfaction of the EIC in connection with G.S. Mela 2023 under Diamond Harbour Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001528/2022-2023 | 429/DHSD | 19/12/2022 | 29/12/2022 | SUMAN INDUSTRIES PVT. LTD. | 2.83 | 2.83 | 100 | 90
19 | PURBA MEDINIPUR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Supply and installation of Printed Wooden Frame Flex Banner Size: 8' x 4' for Creating Public Awareness on Water & Sanitation and General Health & Hygiene for 10 days (from 08.01.2023 to 17.01.2023) at Lot-8 - 200 nos. as per direction & satisfaction of the EIC in connection with G.S. Mela 2023 under Diamond Harbour Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001528/2022-2023 | 429/DHSD | 19/12/2022 | 29/12/2022 | SUMAN INDUSTRIES PVT. LTD. | 2.83 | 2.83 | 100 | 90
20 | PURULIA |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Supply and installation of Printed Wooden Frame Flex Banner Size: 8' x 4' for Creating Public Awareness on Water & Sanitation and General Health & Hygiene for 10 days (from 08.01.2023 to 17.01.2023) at Lot-8 - 200 nos. as per direction & satisfaction of the EIC in connection with G.S. Mela 2023 under Diamond Harbour Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001528/2022-2023 | 429/DHSD | 19/12/2022 | 29/12/2022 | SUMAN INDUSTRIES PVT. LTD. | 2.83 | 2.83 | 100 | 90
21 | SOUTH 24 PARGANAS |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Supply and installation of Printed Wooden Frame Flex Banner Size: 8' x 4' for Creating Public Awareness on Water & Sanitation and General Health & Hygiene for 10 days (from 08.01.2023 to 17.01.2023) at Lot-8 - 200 nos. as per direction & satisfaction of the EIC in connection with G.S. Mela 2023 under Diamond Harbour Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001528/2022-2023 | 429/DHSD | 19/12/2022 | 29/12/2022 | SUMAN INDUSTRIES PVT. LTD. | 2.83 | 2.83 | 100 | 90
22 | UTTAR DINAJPUR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Supply and installation of Printed Wooden Frame Flex Banner Size: 8' x 4' for Creating Public Awareness on Water & Sanitation and General Health & Hygiene for 10 days (from 08.01.2023 to 17.01.2023) at Lot-8 - 200 nos. as per direction & satisfaction of the EIC in connection with G.S. Mela 2023 under Diamond Harbour Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001528/2022-2023 | 429/DHSD | 19/12/2022 | 29/12/2022 | SUMAN INDUSTRIES PVT. LTD. | 2.83 | 2.83 | 100 | 90
23 | ALIPURDUAR |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Installation of Har Ghar Jal (HGJ) Display Board (50 nos.) at different villages under various PWSS under Birbhum Division P.H.E Dte. | AE | Estimator | ORD/000439/2023-2024 | 4644/BHM | 20/12/2023 | 19/01/2024 | IMAGIN | 8.6 | 8.49 | 98.69 | 100
24 | BANKURA |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Installation of Har Ghar Jal (HGJ) Display Board (50 nos.) at different villages under various PWSS under Birbhum Division P.H.E Dte. | AE | Estimator | ORD/000439/2023-2024 | 4644/BHM | 20/12/2023 | 19/01/2024 | IMAGIN | 8.6 | 8.49 | 98.69 | 100
25 | BIRBHUM |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Installation of Har Ghar Jal (HGJ) Display Board (50 nos.) at different villages under various PWSS under Birbhum Division P.H.E Dte. | AE | Estimator | ORD/000439/2023-2024 | 4644/BHM | 20/12/2023 | 19/01/2024 | IMAGIN | 8.6 | 8.49 | 98.69 | 100
26 | COOCHBEHAR |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Installation of Har Ghar Jal (HGJ) Display Board (50 nos.) at different villages under various PWSS under Birbhum Division P.H.E Dte. | AE | Estimator | ORD/000439/2023-2024 | 4644/BHM | 20/12/2023 | 19/01/2024 | IMAGIN | 8.6 | 8.49 | 98.69 | 100
27 | DAKSHIN DINAJPUR |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Installation of Har Ghar Jal (HGJ) Display Board (50 nos.) at different villages under various PWSS under Birbhum Division P.H.E Dte. | AE | Estimator | ORD/000439/2023-2024 | 4644/BHM | 20/12/2023 | 19/01/2024 | IMAGIN | 8.6 | 8.49 | 98.69 | 100
28 | DARJEELING |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Installation of Har Ghar Jal (HGJ) Display Board (50 nos.) at different villages under various PWSS under Birbhum Division P.H.E Dte. | AE | Estimator | ORD/000439/2023-2024 | 4644/BHM | 20/12/2023 | 19/01/2024 | IMAGIN | 8.6 | 8.49 | 98.69 | 100
29 | HOOGHLY |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Installation of Har Ghar Jal (HGJ) Display Board (50 nos.) at different villages under various PWSS under Birbhum Division P.H.E Dte. | AE | Estimator | ORD/000439/2023-2024 | 4644/BHM | 20/12/2023 | 19/01/2024 | IMAGIN | 8.6 | 8.49 | 98.69 | 100
30 | HOWRAH |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Installation of Har Ghar Jal (HGJ) Display Board (50 nos.) at different villages under various PWSS under Birbhum Division P.H.E Dte. | AE | Estimator | ORD/000439/2023-2024 | 4644/BHM | 20/12/2023 | 19/01/2024 | IMAGIN | 8.6 | 8.49 | 98.69 | 100
31 | JALPAIGURI |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Installation of Har Ghar Jal (HGJ) Display Board (50 nos.) at different villages under various PWSS under Birbhum Division P.H.E Dte. | AE | Estimator | ORD/000439/2023-2024 | 4644/BHM | 20/12/2023 | 19/01/2024 | IMAGIN | 8.6 | 8.49 | 98.69 | 100
32 | JHARGRAM |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Installation of Har Ghar Jal (HGJ) Display Board (50 nos.) at different villages under various PWSS under Birbhum Division P.H.E Dte. | AE | Estimator | ORD/000439/2023-2024 | 4644/BHM | 20/12/2023 | 19/01/2024 | IMAGIN | 8.6 | 8.49 | 98.69 | 100
33 | KALIMPONG |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Installation of Har Ghar Jal (HGJ) Display Board (50 nos.) at different villages under various PWSS under Birbhum Division P.H.E Dte. | AE | Estimator | ORD/000439/2023-2024 | 4644/BHM | 20/12/2023 | 19/01/2024 | IMAGIN | 8.6 | 8.49 | 98.69 | 100
34 | MALDAH |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Installation of Har Ghar Jal (HGJ) Display Board (50 nos.) at different villages under various PWSS under Birbhum Division P.H.E Dte. | AE | Estimator | ORD/000439/2023-2024 | 4644/BHM | 20/12/2023 | 19/01/2024 | IMAGIN | 8.6 | 8.49 | 98.69 | 100
35 | MURSHIDABAD |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Installation of Har Ghar Jal (HGJ) Display Board (50 nos.) at different villages under various PWSS under Birbhum Division P.H.E Dte. | AE | Estimator | ORD/000439/2023-2024 | 4644/BHM | 20/12/2023 | 19/01/2024 | IMAGIN | 8.6 | 8.49 | 98.69 | 100
36 | NADIA |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Installation of Har Ghar Jal (HGJ) Display Board (50 nos.) at different villages under various PWSS under Birbhum Division P.H.E Dte. | AE | Estimator | ORD/000439/2023-2024 | 4644/BHM | 20/12/2023 | 19/01/2024 | IMAGIN | 8.6 | 8.49 | 98.69 | 100
37 | NORTH 24 PARGANAS |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Installation of Har Ghar Jal (HGJ) Display Board (50 nos.) at different villages under various PWSS under Birbhum Division P.H.E Dte. | AE | Estimator | ORD/000439/2023-2024 | 4644/BHM | 20/12/2023 | 19/01/2024 | IMAGIN | 8.6 | 8.49 | 98.69 | 100
38 | PASCHIM BARDHAMAN |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Installation of Har Ghar Jal (HGJ) Display Board (50 nos.) at different villages under various PWSS under Birbhum Division P.H.E Dte. | AE | Estimator | ORD/000439/2023-2024 | 4644/BHM | 20/12/2023 | 19/01/2024 | IMAGIN | 8.6 | 8.49 | 98.69 | 100
39 | PASCHIM MEDINIPUR |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Installation of Har Ghar Jal (HGJ) Display Board (50 nos.) at different villages under various PWSS under Birbhum Division P.H.E Dte. | AE | Estimator | ORD/000439/2023-2024 | 4644/BHM | 20/12/2023 | 19/01/2024 | IMAGIN | 8.6 | 8.49 | 98.69 | 100
40 | PURBA BARDHAMAN |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Installation of Har Ghar Jal (HGJ) Display Board (50 nos.) at different villages under various PWSS under Birbhum Division P.H.E Dte. | AE | Estimator | ORD/000439/2023-2024 | 4644/BHM | 20/12/2023 | 19/01/2024 | IMAGIN | 8.6 | 8.49 | 98.69 | 100
41 | PURBA MEDINIPUR |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Installation of Har Ghar Jal (HGJ) Display Board (50 nos.) at different villages under various PWSS under Birbhum Division P.H.E Dte. | AE | Estimator | ORD/000439/2023-2024 | 4644/BHM | 20/12/2023 | 19/01/2024 | IMAGIN | 8.6 | 8.49 | 98.69 | 100
42 | PURULIA |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Installation of Har Ghar Jal (HGJ) Display Board (50 nos.) at different villages under various PWSS under Birbhum Division P.H.E Dte. | AE | Estimator | ORD/000439/2023-2024 | 4644/BHM | 20/12/2023 | 19/01/2024 | IMAGIN | 8.6 | 8.49 | 98.69 | 100
43 | SOUTH 24 PARGANAS |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Installation of Har Ghar Jal (HGJ) Display Board (50 nos.) at different villages under various PWSS under Birbhum Division P.H.E Dte. | AE | Estimator | ORD/000439/2023-2024 | 4644/BHM | 20/12/2023 | 19/01/2024 | IMAGIN | 8.6 | 8.49 | 98.69 | 100
44 | UTTAR DINAJPUR |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Installation of Har Ghar Jal (HGJ) Display Board (50 nos.) at different villages under various PWSS under Birbhum Division P.H.E Dte. | AE | Estimator | ORD/000439/2023-2024 | 4644/BHM | 20/12/2023 | 19/01/2024 | IMAGIN | 8.6 | 8.49 | 98.69 | 100
45 | ALIPURDUAR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-II Block) | AE/Ulu | JE/USD | ORD/000350/2023-2024 | 678/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
46 | BANKURA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-II Block) | AE/Ulu | JE/USD | ORD/000350/2023-2024 | 678/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
47 | BIRBHUM |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-II Block) | AE/Ulu | JE/USD | ORD/000350/2023-2024 | 678/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
48 | COOCHBEHAR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-II Block) | AE/Ulu | JE/USD | ORD/000350/2023-2024 | 678/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
49 | DAKSHIN DINAJPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-II Block) | AE/Ulu | JE/USD | ORD/000350/2023-2024 | 678/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
50 | DARJEELING |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-II Block) | AE/Ulu | JE/USD | ORD/000350/2023-2024 | 678/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
51 | HOOGHLY |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-II Block) | AE/Ulu | JE/USD | ORD/000350/2023-2024 | 678/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
52 | HOWRAH |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-II Block) | AE/Ulu | JE/USD | ORD/000350/2023-2024 | 678/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
53 | JALPAIGURI |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-II Block) | AE/Ulu | JE/USD | ORD/000350/2023-2024 | 678/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
54 | JHARGRAM |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-II Block) | AE/Ulu | JE/USD | ORD/000350/2023-2024 | 678/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
55 | KALIMPONG |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-II Block) | AE/Ulu | JE/USD | ORD/000350/2023-2024 | 678/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
56 | MALDAH |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-II Block) | AE/Ulu | JE/USD | ORD/000350/2023-2024 | 678/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
57 | MURSHIDABAD |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-II Block) | AE/Ulu | JE/USD | ORD/000350/2023-2024 | 678/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
58 | NADIA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-II Block) | AE/Ulu | JE/USD | ORD/000350/2023-2024 | 678/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
59 | NORTH 24 PARGANAS |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-II Block) | AE/Ulu | JE/USD | ORD/000350/2023-2024 | 678/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
60 | PASCHIM BARDHAMAN |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-II Block) | AE/Ulu | JE/USD | ORD/000350/2023-2024 | 678/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
61 | PASCHIM MEDINIPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-II Block) | AE/Ulu | JE/USD | ORD/000350/2023-2024 | 678/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
62 | PURBA BARDHAMAN |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-II Block) | AE/Ulu | JE/USD | ORD/000350/2023-2024 | 678/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
63 | PURBA MEDINIPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-II Block) | AE/Ulu | JE/USD | ORD/000350/2023-2024 | 678/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
64 | PURULIA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-II Block) | AE/Ulu | JE/USD | ORD/000350/2023-2024 | 678/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
65 | SOUTH 24 PARGANAS |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-II Block) | AE/Ulu | JE/USD | ORD/000350/2023-2024 | 678/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
66 | UTTAR DINAJPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-II Block) | AE/Ulu | JE/USD | ORD/000350/2023-2024 | 678/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
67 | ALIPURDUAR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-I Block) | AE/Ulu | JE/USD | ORD/000346/2023-2024 | 675/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
68 | BANKURA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-I Block) | AE/Ulu | JE/USD | ORD/000346/2023-2024 | 675/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
69 | BIRBHUM |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-I Block) | AE/Ulu | JE/USD | ORD/000346/2023-2024 | 675/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
70 | COOCHBEHAR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-I Block) | AE/Ulu | JE/USD | ORD/000346/2023-2024 | 675/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
71 | DAKSHIN DINAJPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-I Block) | AE/Ulu | JE/USD | ORD/000346/2023-2024 | 675/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
72 | DARJEELING |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-I Block) | AE/Ulu | JE/USD | ORD/000346/2023-2024 | 675/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
73 | HOOGHLY |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-I Block) | AE/Ulu | JE/USD | ORD/000346/2023-2024 | 675/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
74 | HOWRAH |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-I Block) | AE/Ulu | JE/USD | ORD/000346/2023-2024 | 675/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
75 | JALPAIGURI |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-I Block) | AE/Ulu | JE/USD | ORD/000346/2023-2024 | 675/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
76 | JHARGRAM |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-I Block) | AE/Ulu | JE/USD | ORD/000346/2023-2024 | 675/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
77 | KALIMPONG |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-I Block) | AE/Ulu | JE/USD | ORD/000346/2023-2024 | 675/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
78 | MALDAH |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-I Block) | AE/Ulu | JE/USD | ORD/000346/2023-2024 | 675/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
79 | MURSHIDABAD |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-I Block) | AE/Ulu | JE/USD | ORD/000346/2023-2024 | 675/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
80 | NADIA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-I Block) | AE/Ulu | JE/USD | ORD/000346/2023-2024 | 675/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
81 | NORTH 24 PARGANAS |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-I Block) | AE/Ulu | JE/USD | ORD/000346/2023-2024 | 675/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
82 | PASCHIM BARDHAMAN |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-I Block) | AE/Ulu | JE/USD | ORD/000346/2023-2024 | 675/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
83 | PASCHIM MEDINIPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-I Block) | AE/Ulu | JE/USD | ORD/000346/2023-2024 | 675/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
84 | PURBA BARDHAMAN |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-I Block) | AE/Ulu | JE/USD | ORD/000346/2023-2024 | 675/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
85 | PURBA MEDINIPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-I Block) | AE/Ulu | JE/USD | ORD/000346/2023-2024 | 675/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
86 | PURULIA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-I Block) | AE/Ulu | JE/USD | ORD/000346/2023-2024 | 675/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
87 | SOUTH 24 PARGANAS |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-I Block) | AE/Ulu | JE/USD | ORD/000346/2023-2024 | 675/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
88 | UTTAR DINAJPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-I Block) | AE/Ulu | JE/USD | ORD/000346/2023-2024 | 675/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.77 | 4.77 | 100 | 100
89 | ALIPURDUAR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-I Block) | AE/Ulu | JE/USD | ORD/000349/2023-2024 | 677/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.82 | 4.82 | 100 | 100
90 | BANKURA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-I Block) | AE/Ulu | JE/USD | ORD/000349/2023-2024 | 677/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.82 | 4.82 | 100 | 100
91 | BIRBHUM |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-I Block) | AE/Ulu | JE/USD | ORD/000349/2023-2024 | 677/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.82 | 4.82 | 100 | 100
92 | COOCHBEHAR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-I Block) | AE/Ulu | JE/USD | ORD/000349/2023-2024 | 677/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.82 | 4.82 | 100 | 100
93 | DAKSHIN DINAJPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-I Block) | AE/Ulu | JE/USD | ORD/000349/2023-2024 | 677/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.82 | 4.82 | 100 | 100
94 | DARJEELING |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-I Block) | AE/Ulu | JE/USD | ORD/000349/2023-2024 | 677/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.82 | 4.82 | 100 | 100
95 | HOOGHLY |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-I Block) | AE/Ulu | JE/USD | ORD/000349/2023-2024 | 677/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.82 | 4.82 | 100 | 100
96 | HOWRAH |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-I Block) | AE/Ulu | JE/USD | ORD/000349/2023-2024 | 677/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.82 | 4.82 | 100 | 100
97 | JALPAIGURI |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-I Block) | AE/Ulu | JE/USD | ORD/000349/2023-2024 | 677/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.82 | 4.82 | 100 | 100
98 | JHARGRAM |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-I Block) | AE/Ulu | JE/USD | ORD/000349/2023-2024 | 677/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.82 | 4.82 | 100 | 100
99 | KALIMPONG |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-I Block) | AE/Ulu | JE/USD | ORD/000349/2023-2024 | 677/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.82 | 4.82 | 100 | 100
100 | MALDAH |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-I Block) | AE/Ulu | JE/USD | ORD/000349/2023-2024 | 677/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.82 | 4.82 | 100 | 100
101 | MURSHIDABAD |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-I Block) | AE/Ulu | JE/USD | ORD/000349/2023-2024 | 677/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.82 | 4.82 | 100 | 100
102 | NADIA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-I Block) | AE/Ulu | JE/USD | ORD/000349/2023-2024 | 677/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.82 | 4.82 | 100 | 100
103 | NORTH 24 PARGANAS |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-I Block) | AE/Ulu | JE/USD | ORD/000349/2023-2024 | 677/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.82 | 4.82 | 100 | 100
104 | PASCHIM BARDHAMAN |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-I Block) | AE/Ulu | JE/USD | ORD/000349/2023-2024 | 677/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.82 | 4.82 | 100 | 100
105 | PASCHIM MEDINIPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-I Block) | AE/Ulu | JE/USD | ORD/000349/2023-2024 | 677/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.82 | 4.82 | 100 | 100
106 | PURBA BARDHAMAN |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-I Block) | AE/Ulu | JE/USD | ORD/000349/2023-2024 | 677/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.82 | 4.82 | 100 | 100
107 | PURBA MEDINIPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-I Block) | AE/Ulu | JE/USD | ORD/000349/2023-2024 | 677/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.82 | 4.82 | 100 | 100
108 | PURULIA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-I Block) | AE/Ulu | JE/USD | ORD/000349/2023-2024 | 677/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.82 | 4.82 | 100 | 100
109 | SOUTH 24 PARGANAS |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-I Block) | AE/Ulu | JE/USD | ORD/000349/2023-2024 | 677/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.82 | 4.82 | 100 | 100
110 | UTTAR DINAJPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Amta-I Block) | AE/Ulu | JE/USD | ORD/000349/2023-2024 | 677/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.82 | 4.82 | 100 | 100
111 | ALIPURDUAR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-II Block) | AE/Ulu | JE/USD | ORD/000351/2023-2024 | 679/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.76 | 4.76 | 100 | 100
112 | BANKURA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-II Block) | AE/Ulu | JE/USD | ORD/000351/2023-2024 | 679/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.76 | 4.76 | 100 | 100
113 | BIRBHUM |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-II Block) | AE/Ulu | JE/USD | ORD/000351/2023-2024 | 679/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.76 | 4.76 | 100 | 100
114 | COOCHBEHAR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-II Block) | AE/Ulu | JE/USD | ORD/000351/2023-2024 | 679/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.76 | 4.76 | 100 | 100
115 | DAKSHIN DINAJPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-II Block) | AE/Ulu | JE/USD | ORD/000351/2023-2024 | 679/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.76 | 4.76 | 100 | 100
116 | DARJEELING |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-II Block) | AE/Ulu | JE/USD | ORD/000351/2023-2024 | 679/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.76 | 4.76 | 100 | 100
117 | HOOGHLY |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-II Block) | AE/Ulu | JE/USD | ORD/000351/2023-2024 | 679/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.76 | 4.76 | 100 | 100
118 | HOWRAH |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-II Block) | AE/Ulu | JE/USD | ORD/000351/2023-2024 | 679/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.76 | 4.76 | 100 | 100
119 | JALPAIGURI |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-II Block) | AE/Ulu | JE/USD | ORD/000351/2023-2024 | 679/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.76 | 4.76 | 100 | 100
120 | JHARGRAM |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-II Block) | AE/Ulu | JE/USD | ORD/000351/2023-2024 | 679/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.76 | 4.76 | 100 | 100
121 | KALIMPONG |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-II Block) | AE/Ulu | JE/USD | ORD/000351/2023-2024 | 679/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.76 | 4.76 | 100 | 100
122 | MALDAH |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-II Block) | AE/Ulu | JE/USD | ORD/000351/2023-2024 | 679/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.76 | 4.76 | 100 | 100
123 | MURSHIDABAD |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-II Block) | AE/Ulu | JE/USD | ORD/000351/2023-2024 | 679/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.76 | 4.76 | 100 | 100
124 | NADIA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-II Block) | AE/Ulu | JE/USD | ORD/000351/2023-2024 | 679/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.76 | 4.76 | 100 | 100
125 | NORTH 24 PARGANAS |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-II Block) | AE/Ulu | JE/USD | ORD/000351/2023-2024 | 679/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.76 | 4.76 | 100 | 100
126 | PASCHIM BARDHAMAN |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-II Block) | AE/Ulu | JE/USD | ORD/000351/2023-2024 | 679/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.76 | 4.76 | 100 | 100
127 | PASCHIM MEDINIPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-II Block) | AE/Ulu | JE/USD | ORD/000351/2023-2024 | 679/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.76 | 4.76 | 100 | 100
128 | PURBA BARDHAMAN |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-II Block) | AE/Ulu | JE/USD | ORD/000351/2023-2024 | 679/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.76 | 4.76 | 100 | 100
129 | PURBA MEDINIPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-II Block) | AE/Ulu | JE/USD | ORD/000351/2023-2024 | 679/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.76 | 4.76 | 100 | 100
130 | PURULIA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-II Block) | AE/Ulu | JE/USD | ORD/000351/2023-2024 | 679/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.76 | 4.76 | 100 | 100
131 | SOUTH 24 PARGANAS |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-II Block) | AE/Ulu | JE/USD | ORD/000351/2023-2024 | 679/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.76 | 4.76 | 100 | 100
132 | UTTAR DINAJPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-II Block) | AE/Ulu | JE/USD | ORD/000351/2023-2024 | 679/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.76 | 4.76 | 100 | 100
133 | ALIPURDUAR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-I Block) | AE/Ulu | JE/USD | ORD/000344/2023-2024 | 673/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.85 | 4.85 | 100 | 100
134 | BANKURA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-I Block) | AE/Ulu | JE/USD | ORD/000344/2023-2024 | 673/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.85 | 4.85 | 100 | 100
135 | BIRBHUM |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-I Block) | AE/Ulu | JE/USD | ORD/000344/2023-2024 | 673/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.85 | 4.85 | 100 | 100
136 | COOCHBEHAR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-I Block) | AE/Ulu | JE/USD | ORD/000344/2023-2024 | 673/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.85 | 4.85 | 100 | 100
137 | DAKSHIN DINAJPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-I Block) | AE/Ulu | JE/USD | ORD/000344/2023-2024 | 673/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.85 | 4.85 | 100 | 100
138 | DARJEELING |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-I Block) | AE/Ulu | JE/USD | ORD/000344/2023-2024 | 673/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.85 | 4.85 | 100 | 100
139 | HOOGHLY |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-I Block) | AE/Ulu | JE/USD | ORD/000344/2023-2024 | 673/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.85 | 4.85 | 100 | 100
140 | HOWRAH |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-I Block) | AE/Ulu | JE/USD | ORD/000344/2023-2024 | 673/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.85 | 4.85 | 100 | 100
141 | JALPAIGURI |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-I Block) | AE/Ulu | JE/USD | ORD/000344/2023-2024 | 673/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.85 | 4.85 | 100 | 100
142 | JHARGRAM |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-I Block) | AE/Ulu | JE/USD | ORD/000344/2023-2024 | 673/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.85 | 4.85 | 100 | 100
143 | KALIMPONG |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-I Block) | AE/Ulu | JE/USD | ORD/000344/2023-2024 | 673/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.85 | 4.85 | 100 | 100
144 | MALDAH |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-I Block) | AE/Ulu | JE/USD | ORD/000344/2023-2024 | 673/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.85 | 4.85 | 100 | 100
145 | MURSHIDABAD |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-I Block) | AE/Ulu | JE/USD | ORD/000344/2023-2024 | 673/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.85 | 4.85 | 100 | 100
146 | NADIA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-I Block) | AE/Ulu | JE/USD | ORD/000344/2023-2024 | 673/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.85 | 4.85 | 100 | 100
147 | NORTH 24 PARGANAS |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-I Block) | AE/Ulu | JE/USD | ORD/000344/2023-2024 | 673/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.85 | 4.85 | 100 | 100
148 | PASCHIM BARDHAMAN |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-I Block) | AE/Ulu | JE/USD | ORD/000344/2023-2024 | 673/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.85 | 4.85 | 100 | 100
149 | PASCHIM MEDINIPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-I Block) | AE/Ulu | JE/USD | ORD/000344/2023-2024 | 673/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.85 | 4.85 | 100 | 100
150 | PURBA BARDHAMAN |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-I Block) | AE/Ulu | JE/USD | ORD/000344/2023-2024 | 673/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.85 | 4.85 | 100 | 100
151 | PURBA MEDINIPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-I Block) | AE/Ulu | JE/USD | ORD/000344/2023-2024 | 673/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.85 | 4.85 | 100 | 100
152 | PURULIA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-I Block) | AE/Ulu | JE/USD | ORD/000344/2023-2024 | 673/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.85 | 4.85 | 100 | 100
153 | SOUTH 24 PARGANAS |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-I Block) | AE/Ulu | JE/USD | ORD/000344/2023-2024 | 673/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.85 | 4.85 | 100 | 100
154 | UTTAR DINAJPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-I Block) | AE/Ulu | JE/USD | ORD/000344/2023-2024 | 673/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.85 | 4.85 | 100 | 100
155 | ALIPURDUAR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-II Block) | AE/Ulu | JE/USD | ORD/000345/2023-2024 | 674/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.68 | 4.68 | 100 | 100
156 | BANKURA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-II Block) | AE/Ulu | JE/USD | ORD/000345/2023-2024 | 674/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.68 | 4.68 | 100 | 100
157 | BIRBHUM |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-II Block) | AE/Ulu | JE/USD | ORD/000345/2023-2024 | 674/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.68 | 4.68 | 100 | 100
158 | COOCHBEHAR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-II Block) | AE/Ulu | JE/USD | ORD/000345/2023-2024 | 674/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.68 | 4.68 | 100 | 100
159 | DAKSHIN DINAJPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-II Block) | AE/Ulu | JE/USD | ORD/000345/2023-2024 | 674/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.68 | 4.68 | 100 | 100
160 | DARJEELING |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-II Block) | AE/Ulu | JE/USD | ORD/000345/2023-2024 | 674/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.68 | 4.68 | 100 | 100
161 | HOOGHLY |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-II Block) | AE/Ulu | JE/USD | ORD/000345/2023-2024 | 674/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.68 | 4.68 | 100 | 100
162 | HOWRAH |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-II Block) | AE/Ulu | JE/USD | ORD/000345/2023-2024 | 674/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.68 | 4.68 | 100 | 100
163 | JALPAIGURI |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-II Block) | AE/Ulu | JE/USD | ORD/000345/2023-2024 | 674/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.68 | 4.68 | 100 | 100
164 | JHARGRAM |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-II Block) | AE/Ulu | JE/USD | ORD/000345/2023-2024 | 674/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.68 | 4.68 | 100 | 100
165 | KALIMPONG |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-II Block) | AE/Ulu | JE/USD | ORD/000345/2023-2024 | 674/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.68 | 4.68 | 100 | 100
166 | MALDAH |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-II Block) | AE/Ulu | JE/USD | ORD/000345/2023-2024 | 674/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.68 | 4.68 | 100 | 100
167 | MURSHIDABAD |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-II Block) | AE/Ulu | JE/USD | ORD/000345/2023-2024 | 674/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.68 | 4.68 | 100 | 100
168 | NADIA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-II Block) | AE/Ulu | JE/USD | ORD/000345/2023-2024 | 674/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.68 | 4.68 | 100 | 100
169 | NORTH 24 PARGANAS |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-II Block) | AE/Ulu | JE/USD | ORD/000345/2023-2024 | 674/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.68 | 4.68 | 100 | 100
170 | PASCHIM BARDHAMAN |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-II Block) | AE/Ulu | JE/USD | ORD/000345/2023-2024 | 674/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.68 | 4.68 | 100 | 100
171 | PASCHIM MEDINIPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-II Block) | AE/Ulu | JE/USD | ORD/000345/2023-2024 | 674/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.68 | 4.68 | 100 | 100
172 | PURBA BARDHAMAN |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-II Block) | AE/Ulu | JE/USD | ORD/000345/2023-2024 | 674/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.68 | 4.68 | 100 | 100
173 | PURBA MEDINIPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-II Block) | AE/Ulu | JE/USD | ORD/000345/2023-2024 | 674/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.68 | 4.68 | 100 | 100
174 | PURULIA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-II Block) | AE/Ulu | JE/USD | ORD/000345/2023-2024 | 674/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.68 | 4.68 | 100 | 100
175 | SOUTH 24 PARGANAS |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-II Block) | AE/Ulu | JE/USD | ORD/000345/2023-2024 | 674/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.68 | 4.68 | 100 | 100
176 | UTTAR DINAJPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Shyampur-II Block) | AE/Ulu | JE/USD | ORD/000345/2023-2024 | 674/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.68 | 4.68 | 100 | 100
177 | ALIPURDUAR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-II Block) | AE/Ulu | JE/USD | ORD/000347/2023-2024 | 676/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.81 | 4.81 | 100 | 100
178 | BANKURA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-II Block) | AE/Ulu | JE/USD | ORD/000347/2023-2024 | 676/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.81 | 4.81 | 100 | 100
179 | BIRBHUM |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-II Block) | AE/Ulu | JE/USD | ORD/000347/2023-2024 | 676/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.81 | 4.81 | 100 | 100
180 | COOCHBEHAR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-II Block) | AE/Ulu | JE/USD | ORD/000347/2023-2024 | 676/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.81 | 4.81 | 100 | 100
181 | DAKSHIN DINAJPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-II Block) | AE/Ulu | JE/USD | ORD/000347/2023-2024 | 676/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.81 | 4.81 | 100 | 100
182 | DARJEELING |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-II Block) | AE/Ulu | JE/USD | ORD/000347/2023-2024 | 676/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.81 | 4.81 | 100 | 100
183 | HOOGHLY |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-II Block) | AE/Ulu | JE/USD | ORD/000347/2023-2024 | 676/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.81 | 4.81 | 100 | 100
184 | HOWRAH |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-II Block) | AE/Ulu | JE/USD | ORD/000347/2023-2024 | 676/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.81 | 4.81 | 100 | 100
185 | JALPAIGURI |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-II Block) | AE/Ulu | JE/USD | ORD/000347/2023-2024 | 676/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.81 | 4.81 | 100 | 100
186 | JHARGRAM |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-II Block) | AE/Ulu | JE/USD | ORD/000347/2023-2024 | 676/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.81 | 4.81 | 100 | 100
187 | KALIMPONG |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-II Block) | AE/Ulu | JE/USD | ORD/000347/2023-2024 | 676/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.81 | 4.81 | 100 | 100
188 | MALDAH |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-II Block) | AE/Ulu | JE/USD | ORD/000347/2023-2024 | 676/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.81 | 4.81 | 100 | 100
189 | MURSHIDABAD |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-II Block) | AE/Ulu | JE/USD | ORD/000347/2023-2024 | 676/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.81 | 4.81 | 100 | 100
190 | NADIA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-II Block) | AE/Ulu | JE/USD | ORD/000347/2023-2024 | 676/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.81 | 4.81 | 100 | 100
191 | NORTH 24 PARGANAS |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-II Block) | AE/Ulu | JE/USD | ORD/000347/2023-2024 | 676/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.81 | 4.81 | 100 | 100
192 | PASCHIM BARDHAMAN |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-II Block) | AE/Ulu | JE/USD | ORD/000347/2023-2024 | 676/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.81 | 4.81 | 100 | 100
193 | PASCHIM MEDINIPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-II Block) | AE/Ulu | JE/USD | ORD/000347/2023-2024 | 676/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.81 | 4.81 | 100 | 100
194 | PURBA BARDHAMAN |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-II Block) | AE/Ulu | JE/USD | ORD/000347/2023-2024 | 676/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.81 | 4.81 | 100 | 100
195 | PURBA MEDINIPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-II Block) | AE/Ulu | JE/USD | ORD/000347/2023-2024 | 676/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.81 | 4.81 | 100 | 100
196 | PURULIA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-II Block) | AE/Ulu | JE/USD | ORD/000347/2023-2024 | 676/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.81 | 4.81 | 100 | 100
197 | SOUTH 24 PARGANAS |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-II Block) | AE/Ulu | JE/USD | ORD/000347/2023-2024 | 676/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.81 | 4.81 | 100 | 100
198 | UTTAR DINAJPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Uluberia-II Block) | AE/Ulu | JE/USD | ORD/000347/2023-2024 | 676/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.81 | 4.81 | 100 | 100
199 | ALIPURDUAR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-I Block) | AE/Ulu | JE/USD | ORD/000352/2023-2024 | 680/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.8 | 4.8 | 100 | 100
200 | BANKURA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-I Block) | AE/Ulu | JE/USD | ORD/000352/2023-2024 | 680/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.8 | 4.8 | 100 | 100
201 | BIRBHUM |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-I Block) | AE/Ulu | JE/USD | ORD/000352/2023-2024 | 680/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.8 | 4.8 | 100 | 100
202 | COOCHBEHAR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-I Block) | AE/Ulu | JE/USD | ORD/000352/2023-2024 | 680/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.8 | 4.8 | 100 | 100
203 | DAKSHIN DINAJPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-I Block) | AE/Ulu | JE/USD | ORD/000352/2023-2024 | 680/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.8 | 4.8 | 100 | 100
204 | DARJEELING |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-I Block) | AE/Ulu | JE/USD | ORD/000352/2023-2024 | 680/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.8 | 4.8 | 100 | 100
205 | HOOGHLY |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-I Block) | AE/Ulu | JE/USD | ORD/000352/2023-2024 | 680/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.8 | 4.8 | 100 | 100
206 | HOWRAH |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-I Block) | AE/Ulu | JE/USD | ORD/000352/2023-2024 | 680/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.8 | 4.8 | 100 | 100
207 | JALPAIGURI |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-I Block) | AE/Ulu | JE/USD | ORD/000352/2023-2024 | 680/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.8 | 4.8 | 100 | 100
208 | JHARGRAM |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-I Block) | AE/Ulu | JE/USD | ORD/000352/2023-2024 | 680/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.8 | 4.8 | 100 | 100
209 | KALIMPONG |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-I Block) | AE/Ulu | JE/USD | ORD/000352/2023-2024 | 680/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.8 | 4.8 | 100 | 100
210 | MALDAH |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-I Block) | AE/Ulu | JE/USD | ORD/000352/2023-2024 | 680/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.8 | 4.8 | 100 | 100
211 | MURSHIDABAD |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-I Block) | AE/Ulu | JE/USD | ORD/000352/2023-2024 | 680/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.8 | 4.8 | 100 | 100
212 | NADIA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-I Block) | AE/Ulu | JE/USD | ORD/000352/2023-2024 | 680/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.8 | 4.8 | 100 | 100
213 | NORTH 24 PARGANAS |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-I Block) | AE/Ulu | JE/USD | ORD/000352/2023-2024 | 680/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.8 | 4.8 | 100 | 100
214 | PASCHIM BARDHAMAN |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-I Block) | AE/Ulu | JE/USD | ORD/000352/2023-2024 | 680/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.8 | 4.8 | 100 | 100
215 | PASCHIM MEDINIPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-I Block) | AE/Ulu | JE/USD | ORD/000352/2023-2024 | 680/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.8 | 4.8 | 100 | 100
216 | PURBA BARDHAMAN |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-I Block) | AE/Ulu | JE/USD | ORD/000352/2023-2024 | 680/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.8 | 4.8 | 100 | 100
217 | PURBA MEDINIPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-I Block) | AE/Ulu | JE/USD | ORD/000352/2023-2024 | 680/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.8 | 4.8 | 100 | 100
218 | PURULIA |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-I Block) | AE/Ulu | JE/USD | ORD/000352/2023-2024 | 680/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.8 | 4.8 | 100 | 100
219 | SOUTH 24 PARGANAS |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-I Block) | AE/Ulu | JE/USD | ORD/000352/2023-2024 | 680/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.8 | 4.8 | 100 | 100
220 | UTTAR DINAJPUR |  | Howrah Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Mass awareness generation and IEC activities on 'Jal Jeevan Mission' programme within the campus of different Festive places like Pandals during Durgapuja, Dipabali, during ID-Ud-Zoha, Chirtsmas and different MELA Campus etc. at different Blocks under Uluberia Sub-Division of Howrah Division, PHE Dte. (For Bagnan-I Block) | AE/Ulu | JE/USD | ORD/000352/2023-2024 | 680/AE/USD | 06/11/2023 | 20/01/2024 | PUNAM KUMAR GUPTA | 4.8 | 4.8 | 100 | 100
221 | ALIPURDUAR |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water, water conservation under Jal Jeevan Mission (JJM) programme in Birbhum District under Birbhum Division, P.H.E Dte. | AE | JE | ORD/000448/2023-2024 | 64/BHM | 09/01/2024 | 09/01/2025 | IMAGIN | 57.14 | 56.79 | 99.4 | 100
222 | BANKURA |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water, water conservation under Jal Jeevan Mission (JJM) programme in Birbhum District under Birbhum Division, P.H.E Dte. | AE | JE | ORD/000448/2023-2024 | 64/BHM | 09/01/2024 | 09/01/2025 | IMAGIN | 57.14 | 56.79 | 99.4 | 100
223 | BIRBHUM |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water, water conservation under Jal Jeevan Mission (JJM) programme in Birbhum District under Birbhum Division, P.H.E Dte. | AE | JE | ORD/000448/2023-2024 | 64/BHM | 09/01/2024 | 09/01/2025 | IMAGIN | 57.14 | 56.79 | 99.4 | 100
224 | COOCHBEHAR |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water, water conservation under Jal Jeevan Mission (JJM) programme in Birbhum District under Birbhum Division, P.H.E Dte. | AE | JE | ORD/000448/2023-2024 | 64/BHM | 09/01/2024 | 09/01/2025 | IMAGIN | 57.14 | 56.79 | 99.4 | 100
225 | DAKSHIN DINAJPUR |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water, water conservation under Jal Jeevan Mission (JJM) programme in Birbhum District under Birbhum Division, P.H.E Dte. | AE | JE | ORD/000448/2023-2024 | 64/BHM | 09/01/2024 | 09/01/2025 | IMAGIN | 57.14 | 56.79 | 99.4 | 100
226 | DARJEELING |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water, water conservation under Jal Jeevan Mission (JJM) programme in Birbhum District under Birbhum Division, P.H.E Dte. | AE | JE | ORD/000448/2023-2024 | 64/BHM | 09/01/2024 | 09/01/2025 | IMAGIN | 57.14 | 56.79 | 99.4 | 100
227 | HOOGHLY |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water, water conservation under Jal Jeevan Mission (JJM) programme in Birbhum District under Birbhum Division, P.H.E Dte. | AE | JE | ORD/000448/2023-2024 | 64/BHM | 09/01/2024 | 09/01/2025 | IMAGIN | 57.14 | 56.79 | 99.4 | 100
228 | HOWRAH |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water, water conservation under Jal Jeevan Mission (JJM) programme in Birbhum District under Birbhum Division, P.H.E Dte. | AE | JE | ORD/000448/2023-2024 | 64/BHM | 09/01/2024 | 09/01/2025 | IMAGIN | 57.14 | 56.79 | 99.4 | 100
229 | JALPAIGURI |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water, water conservation under Jal Jeevan Mission (JJM) programme in Birbhum District under Birbhum Division, P.H.E Dte. | AE | JE | ORD/000448/2023-2024 | 64/BHM | 09/01/2024 | 09/01/2025 | IMAGIN | 57.14 | 56.79 | 99.4 | 100
230 | JHARGRAM |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water, water conservation under Jal Jeevan Mission (JJM) programme in Birbhum District under Birbhum Division, P.H.E Dte. | AE | JE | ORD/000448/2023-2024 | 64/BHM | 09/01/2024 | 09/01/2025 | IMAGIN | 57.14 | 56.79 | 99.4 | 100
231 | KALIMPONG |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water, water conservation under Jal Jeevan Mission (JJM) programme in Birbhum District under Birbhum Division, P.H.E Dte. | AE | JE | ORD/000448/2023-2024 | 64/BHM | 09/01/2024 | 09/01/2025 | IMAGIN | 57.14 | 56.79 | 99.4 | 100
232 | MALDAH |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water, water conservation under Jal Jeevan Mission (JJM) programme in Birbhum District under Birbhum Division, P.H.E Dte. | AE | JE | ORD/000448/2023-2024 | 64/BHM | 09/01/2024 | 09/01/2025 | IMAGIN | 57.14 | 56.79 | 99.4 | 100
233 | MURSHIDABAD |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water, water conservation under Jal Jeevan Mission (JJM) programme in Birbhum District under Birbhum Division, P.H.E Dte. | AE | JE | ORD/000448/2023-2024 | 64/BHM | 09/01/2024 | 09/01/2025 | IMAGIN | 57.14 | 56.79 | 99.4 | 100
234 | NADIA |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water, water conservation under Jal Jeevan Mission (JJM) programme in Birbhum District under Birbhum Division, P.H.E Dte. | AE | JE | ORD/000448/2023-2024 | 64/BHM | 09/01/2024 | 09/01/2025 | IMAGIN | 57.14 | 56.79 | 99.4 | 100
235 | NORTH 24 PARGANAS |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water, water conservation under Jal Jeevan Mission (JJM) programme in Birbhum District under Birbhum Division, P.H.E Dte. | AE | JE | ORD/000448/2023-2024 | 64/BHM | 09/01/2024 | 09/01/2025 | IMAGIN | 57.14 | 56.79 | 99.4 | 100
236 | PASCHIM BARDHAMAN |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water, water conservation under Jal Jeevan Mission (JJM) programme in Birbhum District under Birbhum Division, P.H.E Dte. | AE | JE | ORD/000448/2023-2024 | 64/BHM | 09/01/2024 | 09/01/2025 | IMAGIN | 57.14 | 56.79 | 99.4 | 100
237 | PASCHIM MEDINIPUR |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water, water conservation under Jal Jeevan Mission (JJM) programme in Birbhum District under Birbhum Division, P.H.E Dte. | AE | JE | ORD/000448/2023-2024 | 64/BHM | 09/01/2024 | 09/01/2025 | IMAGIN | 57.14 | 56.79 | 99.4 | 100
238 | PURBA BARDHAMAN |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water, water conservation under Jal Jeevan Mission (JJM) programme in Birbhum District under Birbhum Division, P.H.E Dte. | AE | JE | ORD/000448/2023-2024 | 64/BHM | 09/01/2024 | 09/01/2025 | IMAGIN | 57.14 | 56.79 | 99.4 | 100
239 | PURBA MEDINIPUR |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water, water conservation under Jal Jeevan Mission (JJM) programme in Birbhum District under Birbhum Division, P.H.E Dte. | AE | JE | ORD/000448/2023-2024 | 64/BHM | 09/01/2024 | 09/01/2025 | IMAGIN | 57.14 | 56.79 | 99.4 | 100
240 | PURULIA |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water, water conservation under Jal Jeevan Mission (JJM) programme in Birbhum District under Birbhum Division, P.H.E Dte. | AE | JE | ORD/000448/2023-2024 | 64/BHM | 09/01/2024 | 09/01/2025 | IMAGIN | 57.14 | 56.79 | 99.4 | 100
241 | SOUTH 24 PARGANAS |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water, water conservation under Jal Jeevan Mission (JJM) programme in Birbhum District under Birbhum Division, P.H.E Dte. | AE | JE | ORD/000448/2023-2024 | 64/BHM | 09/01/2024 | 09/01/2025 | IMAGIN | 57.14 | 56.79 | 99.4 | 100
242 | UTTAR DINAJPUR |  | Birbhum Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water, water conservation under Jal Jeevan Mission (JJM) programme in Birbhum District under Birbhum Division, P.H.E Dte. | AE | JE | ORD/000448/2023-2024 | 64/BHM | 09/01/2024 | 09/01/2025 | IMAGIN | 57.14 | 56.79 | 99.4 | 100
243 | ALIPURDUAR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -I and Bishnupur- I& Bishnupur -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000320/2024-2025 | 2701/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
244 | BANKURA |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -I and Bishnupur- I& Bishnupur -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000320/2024-2025 | 2701/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
245 | BIRBHUM |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -I and Bishnupur- I& Bishnupur -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000320/2024-2025 | 2701/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
246 | COOCHBEHAR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -I and Bishnupur- I& Bishnupur -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000320/2024-2025 | 2701/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
247 | DAKSHIN DINAJPUR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -I and Bishnupur- I& Bishnupur -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000320/2024-2025 | 2701/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
248 | DARJEELING |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -I and Bishnupur- I& Bishnupur -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000320/2024-2025 | 2701/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
249 | HOOGHLY |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -I and Bishnupur- I& Bishnupur -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000320/2024-2025 | 2701/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
250 | HOWRAH |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -I and Bishnupur- I& Bishnupur -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000320/2024-2025 | 2701/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
251 | JALPAIGURI |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -I and Bishnupur- I& Bishnupur -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000320/2024-2025 | 2701/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
252 | JHARGRAM |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -I and Bishnupur- I& Bishnupur -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000320/2024-2025 | 2701/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
253 | KALIMPONG |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -I and Bishnupur- I& Bishnupur -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000320/2024-2025 | 2701/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
254 | MALDAH |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -I and Bishnupur- I& Bishnupur -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000320/2024-2025 | 2701/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
255 | MURSHIDABAD |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -I and Bishnupur- I& Bishnupur -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000320/2024-2025 | 2701/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
256 | NADIA |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -I and Bishnupur- I& Bishnupur -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000320/2024-2025 | 2701/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
257 | NORTH 24 PARGANAS |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -I and Bishnupur- I& Bishnupur -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000320/2024-2025 | 2701/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
258 | PASCHIM BARDHAMAN |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -I and Bishnupur- I& Bishnupur -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000320/2024-2025 | 2701/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
259 | PASCHIM MEDINIPUR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -I and Bishnupur- I& Bishnupur -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000320/2024-2025 | 2701/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
260 | PURBA BARDHAMAN |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -I and Bishnupur- I& Bishnupur -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000320/2024-2025 | 2701/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
261 | PURBA MEDINIPUR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -I and Bishnupur- I& Bishnupur -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000320/2024-2025 | 2701/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
262 | PURULIA |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -I and Bishnupur- I& Bishnupur -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000320/2024-2025 | 2701/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
263 | SOUTH 24 PARGANAS |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -I and Bishnupur- I& Bishnupur -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000320/2024-2025 | 2701/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
264 | UTTAR DINAJPUR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -I and Bishnupur- I& Bishnupur -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000320/2024-2025 | 2701/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
265 | ALIPURDUAR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -II Joynagar-II and Kultali block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000321/2024-2025 | 2702/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
266 | BANKURA |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -II Joynagar-II and Kultali block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000321/2024-2025 | 2702/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
267 | BIRBHUM |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -II Joynagar-II and Kultali block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000321/2024-2025 | 2702/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
268 | COOCHBEHAR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -II Joynagar-II and Kultali block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000321/2024-2025 | 2702/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
269 | DAKSHIN DINAJPUR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -II Joynagar-II and Kultali block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000321/2024-2025 | 2702/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
270 | DARJEELING |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -II Joynagar-II and Kultali block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000321/2024-2025 | 2702/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
271 | HOOGHLY |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -II Joynagar-II and Kultali block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000321/2024-2025 | 2702/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
272 | HOWRAH |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -II Joynagar-II and Kultali block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000321/2024-2025 | 2702/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
273 | JALPAIGURI |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -II Joynagar-II and Kultali block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000321/2024-2025 | 2702/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
274 | JHARGRAM |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -II Joynagar-II and Kultali block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000321/2024-2025 | 2702/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
275 | KALIMPONG |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -II Joynagar-II and Kultali block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000321/2024-2025 | 2702/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
276 | MALDAH |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -II Joynagar-II and Kultali block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000321/2024-2025 | 2702/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
277 | MURSHIDABAD |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -II Joynagar-II and Kultali block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000321/2024-2025 | 2702/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
278 | NADIA |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -II Joynagar-II and Kultali block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000321/2024-2025 | 2702/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
279 | NORTH 24 PARGANAS |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -II Joynagar-II and Kultali block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000321/2024-2025 | 2702/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
280 | PASCHIM BARDHAMAN |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -II Joynagar-II and Kultali block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000321/2024-2025 | 2702/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
281 | PASCHIM MEDINIPUR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -II Joynagar-II and Kultali block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000321/2024-2025 | 2702/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
282 | PURBA BARDHAMAN |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -II Joynagar-II and Kultali block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000321/2024-2025 | 2702/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
283 | PURBA MEDINIPUR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -II Joynagar-II and Kultali block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000321/2024-2025 | 2702/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
284 | PURULIA |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -II Joynagar-II and Kultali block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000321/2024-2025 | 2702/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
285 | SOUTH 24 PARGANAS |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -II Joynagar-II and Kultali block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000321/2024-2025 | 2702/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
286 | UTTAR DINAJPUR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Magrahat -II Joynagar-II and Kultali block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000321/2024-2025 | 2702/AD | 24/06/2024 | 24/07/2024 | M & M GRAPHICS | 5.1 | 5.09 | 99.8 | 100
287 | ALIPURDUAR |  | Alipurduar Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Alipurduar II,Kumargram,Falakata & Madarihat Block under Alipurduar Division, PHE Dte, , Govt. of West Bengal. | HQ-A.E | RWS Kumargram Block | ORD/000054/2025-2026 | 680/ALD | 21/05/2025 | 18/09/2025 | DEBNATH BROTHERS | 39.09 | 0 | 0 | 0
288 | BANKURA |  | Alipurduar Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Alipurduar II,Kumargram,Falakata & Madarihat Block under Alipurduar Division, PHE Dte, , Govt. of West Bengal. | HQ-A.E | RWS Kumargram Block | ORD/000054/2025-2026 | 680/ALD | 21/05/2025 | 18/09/2025 | DEBNATH BROTHERS | 39.09 | 0 | 0 | 0
289 | BIRBHUM |  | Alipurduar Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Alipurduar II,Kumargram,Falakata & Madarihat Block under Alipurduar Division, PHE Dte, , Govt. of West Bengal. | HQ-A.E | RWS Kumargram Block | ORD/000054/2025-2026 | 680/ALD | 21/05/2025 | 18/09/2025 | DEBNATH BROTHERS | 39.09 | 0 | 0 | 0
290 | COOCHBEHAR |  | Alipurduar Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Alipurduar II,Kumargram,Falakata & Madarihat Block under Alipurduar Division, PHE Dte, , Govt. of West Bengal. | HQ-A.E | RWS Kumargram Block | ORD/000054/2025-2026 | 680/ALD | 21/05/2025 | 18/09/2025 | DEBNATH BROTHERS | 39.09 | 0 | 0 | 0
291 | DAKSHIN DINAJPUR |  | Alipurduar Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Alipurduar II,Kumargram,Falakata & Madarihat Block under Alipurduar Division, PHE Dte, , Govt. of West Bengal. | HQ-A.E | RWS Kumargram Block | ORD/000054/2025-2026 | 680/ALD | 21/05/2025 | 18/09/2025 | DEBNATH BROTHERS | 39.09 | 0 | 0 | 0
292 | DARJEELING |  | Alipurduar Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Alipurduar II,Kumargram,Falakata & Madarihat Block under Alipurduar Division, PHE Dte, , Govt. of West Bengal. | HQ-A.E | RWS Kumargram Block | ORD/000054/2025-2026 | 680/ALD | 21/05/2025 | 18/09/2025 | DEBNATH BROTHERS | 39.09 | 0 | 0 | 0
293 | HOOGHLY |  | Alipurduar Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Alipurduar II,Kumargram,Falakata & Madarihat Block under Alipurduar Division, PHE Dte, , Govt. of West Bengal. | HQ-A.E | RWS Kumargram Block | ORD/000054/2025-2026 | 680/ALD | 21/05/2025 | 18/09/2025 | DEBNATH BROTHERS | 39.09 | 0 | 0 | 0
294 | HOWRAH |  | Alipurduar Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Alipurduar II,Kumargram,Falakata & Madarihat Block under Alipurduar Division, PHE Dte, , Govt. of West Bengal. | HQ-A.E | RWS Kumargram Block | ORD/000054/2025-2026 | 680/ALD | 21/05/2025 | 18/09/2025 | DEBNATH BROTHERS | 39.09 | 0 | 0 | 0
295 | JALPAIGURI |  | Alipurduar Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Alipurduar II,Kumargram,Falakata & Madarihat Block under Alipurduar Division, PHE Dte, , Govt. of West Bengal. | HQ-A.E | RWS Kumargram Block | ORD/000054/2025-2026 | 680/ALD | 21/05/2025 | 18/09/2025 | DEBNATH BROTHERS | 39.09 | 0 | 0 | 0
296 | JHARGRAM |  | Alipurduar Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Alipurduar II,Kumargram,Falakata & Madarihat Block under Alipurduar Division, PHE Dte, , Govt. of West Bengal. | HQ-A.E | RWS Kumargram Block | ORD/000054/2025-2026 | 680/ALD | 21/05/2025 | 18/09/2025 | DEBNATH BROTHERS | 39.09 | 0 | 0 | 0
297 | KALIMPONG |  | Alipurduar Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Alipurduar II,Kumargram,Falakata & Madarihat Block under Alipurduar Division, PHE Dte, , Govt. of West Bengal. | HQ-A.E | RWS Kumargram Block | ORD/000054/2025-2026 | 680/ALD | 21/05/2025 | 18/09/2025 | DEBNATH BROTHERS | 39.09 | 0 | 0 | 0
298 | MALDAH |  | Alipurduar Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Alipurduar II,Kumargram,Falakata & Madarihat Block under Alipurduar Division, PHE Dte, , Govt. of West Bengal. | HQ-A.E | RWS Kumargram Block | ORD/000054/2025-2026 | 680/ALD | 21/05/2025 | 18/09/2025 | DEBNATH BROTHERS | 39.09 | 0 | 0 | 0
299 | MURSHIDABAD |  | Alipurduar Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Alipurduar II,Kumargram,Falakata & Madarihat Block under Alipurduar Division, PHE Dte, , Govt. of West Bengal. | HQ-A.E | RWS Kumargram Block | ORD/000054/2025-2026 | 680/ALD | 21/05/2025 | 18/09/2025 | DEBNATH BROTHERS | 39.09 | 0 | 0 | 0
300 | NADIA |  | Alipurduar Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Alipurduar II,Kumargram,Falakata & Madarihat Block under Alipurduar Division, PHE Dte, , Govt. of West Bengal. | HQ-A.E | RWS Kumargram Block | ORD/000054/2025-2026 | 680/ALD | 21/05/2025 | 18/09/2025 | DEBNATH BROTHERS | 39.09 | 0 | 0 | 0
301 | NORTH 24 PARGANAS |  | Alipurduar Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Alipurduar II,Kumargram,Falakata & Madarihat Block under Alipurduar Division, PHE Dte, , Govt. of West Bengal. | HQ-A.E | RWS Kumargram Block | ORD/000054/2025-2026 | 680/ALD | 21/05/2025 | 18/09/2025 | DEBNATH BROTHERS | 39.09 | 0 | 0 | 0
302 | PASCHIM BARDHAMAN |  | Alipurduar Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Alipurduar II,Kumargram,Falakata & Madarihat Block under Alipurduar Division, PHE Dte, , Govt. of West Bengal. | HQ-A.E | RWS Kumargram Block | ORD/000054/2025-2026 | 680/ALD | 21/05/2025 | 18/09/2025 | DEBNATH BROTHERS | 39.09 | 0 | 0 | 0
303 | PASCHIM MEDINIPUR |  | Alipurduar Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Alipurduar II,Kumargram,Falakata & Madarihat Block under Alipurduar Division, PHE Dte, , Govt. of West Bengal. | HQ-A.E | RWS Kumargram Block | ORD/000054/2025-2026 | 680/ALD | 21/05/2025 | 18/09/2025 | DEBNATH BROTHERS | 39.09 | 0 | 0 | 0
304 | PURBA BARDHAMAN |  | Alipurduar Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Alipurduar II,Kumargram,Falakata & Madarihat Block under Alipurduar Division, PHE Dte, , Govt. of West Bengal. | HQ-A.E | RWS Kumargram Block | ORD/000054/2025-2026 | 680/ALD | 21/05/2025 | 18/09/2025 | DEBNATH BROTHERS | 39.09 | 0 | 0 | 0
305 | PURBA MEDINIPUR |  | Alipurduar Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Alipurduar II,Kumargram,Falakata & Madarihat Block under Alipurduar Division, PHE Dte, , Govt. of West Bengal. | HQ-A.E | RWS Kumargram Block | ORD/000054/2025-2026 | 680/ALD | 21/05/2025 | 18/09/2025 | DEBNATH BROTHERS | 39.09 | 0 | 0 | 0
306 | PURULIA |  | Alipurduar Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Alipurduar II,Kumargram,Falakata & Madarihat Block under Alipurduar Division, PHE Dte, , Govt. of West Bengal. | HQ-A.E | RWS Kumargram Block | ORD/000054/2025-2026 | 680/ALD | 21/05/2025 | 18/09/2025 | DEBNATH BROTHERS | 39.09 | 0 | 0 | 0
307 | SOUTH 24 PARGANAS |  | Alipurduar Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Alipurduar II,Kumargram,Falakata & Madarihat Block under Alipurduar Division, PHE Dte, , Govt. of West Bengal. | HQ-A.E | RWS Kumargram Block | ORD/000054/2025-2026 | 680/ALD | 21/05/2025 | 18/09/2025 | DEBNATH BROTHERS | 39.09 | 0 | 0 | 0
308 | UTTAR DINAJPUR |  | Alipurduar Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Alipurduar II,Kumargram,Falakata & Madarihat Block under Alipurduar Division, PHE Dte, , Govt. of West Bengal. | HQ-A.E | RWS Kumargram Block | ORD/000054/2025-2026 | 680/ALD | 21/05/2025 | 18/09/2025 | DEBNATH BROTHERS | 39.09 | 0 | 0 | 0
309 | ALIPURDUAR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Erection of display board on Swajal Gram / Har Ghar Jal Village at various location within South 24 Parganas District under Alipore Division and South 24 Parganas Water Supply Division-I, PHE Dte. (2nd Call) Block Name - Canning-I, Canning-II, Sagar, Mathurapur-I, Falta, Budge Budge - II, Thakurpukur Maheshtala, Bishnupur-I Village Name : - Bayarsing, Par Kalugachhi, Ghoramara, Barasi, Sarberia, Narayanipur, Uttar Joykrishnapur, Sahapur Kamalpur, Harindanga, Chaluary, Digra, Mallikpur, Chandpala Anantapathpur, Barhay Batpur, Nityanandapur, Srirampur, Rania Gobindapur, Kuchigadi, Sankharipota, Alipore | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000452/2025-2026 | 3696/AD | 31/07/2025 | 15/08/2025 | M & M GRAPHICS | 5.04 | 0 | 0 | 100
310 | BANKURA |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Erection of display board on Swajal Gram / Har Ghar Jal Village at various location within South 24 Parganas District under Alipore Division and South 24 Parganas Water Supply Division-I, PHE Dte. (2nd Call) Block Name - Canning-I, Canning-II, Sagar, Mathurapur-I, Falta, Budge Budge - II, Thakurpukur Maheshtala, Bishnupur-I Village Name : - Bayarsing, Par Kalugachhi, Ghoramara, Barasi, Sarberia, Narayanipur, Uttar Joykrishnapur, Sahapur Kamalpur, Harindanga, Chaluary, Digra, Mallikpur, Chandpala Anantapathpur, Barhay Batpur, Nityanandapur, Srirampur, Rania Gobindapur, Kuchigadi, Sankharipota, Alipore | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000452/2025-2026 | 3696/AD | 31/07/2025 | 15/08/2025 | M & M GRAPHICS | 5.04 | 0 | 0 | 100
311 | BIRBHUM |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Erection of display board on Swajal Gram / Har Ghar Jal Village at various location within South 24 Parganas District under Alipore Division and South 24 Parganas Water Supply Division-I, PHE Dte. (2nd Call) Block Name - Canning-I, Canning-II, Sagar, Mathurapur-I, Falta, Budge Budge - II, Thakurpukur Maheshtala, Bishnupur-I Village Name : - Bayarsing, Par Kalugachhi, Ghoramara, Barasi, Sarberia, Narayanipur, Uttar Joykrishnapur, Sahapur Kamalpur, Harindanga, Chaluary, Digra, Mallikpur, Chandpala Anantapathpur, Barhay Batpur, Nityanandapur, Srirampur, Rania Gobindapur, Kuchigadi, Sankharipota, Alipore | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000452/2025-2026 | 3696/AD | 31/07/2025 | 15/08/2025 | M & M GRAPHICS | 5.04 | 0 | 0 | 100
312 | COOCHBEHAR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Erection of display board on Swajal Gram / Har Ghar Jal Village at various location within South 24 Parganas District under Alipore Division and South 24 Parganas Water Supply Division-I, PHE Dte. (2nd Call) Block Name - Canning-I, Canning-II, Sagar, Mathurapur-I, Falta, Budge Budge - II, Thakurpukur Maheshtala, Bishnupur-I Village Name : - Bayarsing, Par Kalugachhi, Ghoramara, Barasi, Sarberia, Narayanipur, Uttar Joykrishnapur, Sahapur Kamalpur, Harindanga, Chaluary, Digra, Mallikpur, Chandpala Anantapathpur, Barhay Batpur, Nityanandapur, Srirampur, Rania Gobindapur, Kuchigadi, Sankharipota, Alipore | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000452/2025-2026 | 3696/AD | 31/07/2025 | 15/08/2025 | M & M GRAPHICS | 5.04 | 0 | 0 | 100
313 | DAKSHIN DINAJPUR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Erection of display board on Swajal Gram / Har Ghar Jal Village at various location within South 24 Parganas District under Alipore Division and South 24 Parganas Water Supply Division-I, PHE Dte. (2nd Call) Block Name - Canning-I, Canning-II, Sagar, Mathurapur-I, Falta, Budge Budge - II, Thakurpukur Maheshtala, Bishnupur-I Village Name : - Bayarsing, Par Kalugachhi, Ghoramara, Barasi, Sarberia, Narayanipur, Uttar Joykrishnapur, Sahapur Kamalpur, Harindanga, Chaluary, Digra, Mallikpur, Chandpala Anantapathpur, Barhay Batpur, Nityanandapur, Srirampur, Rania Gobindapur, Kuchigadi, Sankharipota, Alipore | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000452/2025-2026 | 3696/AD | 31/07/2025 | 15/08/2025 | M & M GRAPHICS | 5.04 | 0 | 0 | 100
314 | DARJEELING |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Erection of display board on Swajal Gram / Har Ghar Jal Village at various location within South 24 Parganas District under Alipore Division and South 24 Parganas Water Supply Division-I, PHE Dte. (2nd Call) Block Name - Canning-I, Canning-II, Sagar, Mathurapur-I, Falta, Budge Budge - II, Thakurpukur Maheshtala, Bishnupur-I Village Name : - Bayarsing, Par Kalugachhi, Ghoramara, Barasi, Sarberia, Narayanipur, Uttar Joykrishnapur, Sahapur Kamalpur, Harindanga, Chaluary, Digra, Mallikpur, Chandpala Anantapathpur, Barhay Batpur, Nityanandapur, Srirampur, Rania Gobindapur, Kuchigadi, Sankharipota, Alipore | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000452/2025-2026 | 3696/AD | 31/07/2025 | 15/08/2025 | M & M GRAPHICS | 5.04 | 0 | 0 | 100
315 | HOOGHLY |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Erection of display board on Swajal Gram / Har Ghar Jal Village at various location within South 24 Parganas District under Alipore Division and South 24 Parganas Water Supply Division-I, PHE Dte. (2nd Call) Block Name - Canning-I, Canning-II, Sagar, Mathurapur-I, Falta, Budge Budge - II, Thakurpukur Maheshtala, Bishnupur-I Village Name : - Bayarsing, Par Kalugachhi, Ghoramara, Barasi, Sarberia, Narayanipur, Uttar Joykrishnapur, Sahapur Kamalpur, Harindanga, Chaluary, Digra, Mallikpur, Chandpala Anantapathpur, Barhay Batpur, Nityanandapur, Srirampur, Rania Gobindapur, Kuchigadi, Sankharipota, Alipore | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000452/2025-2026 | 3696/AD | 31/07/2025 | 15/08/2025 | M & M GRAPHICS | 5.04 | 0 | 0 | 100
316 | HOWRAH |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Erection of display board on Swajal Gram / Har Ghar Jal Village at various location within South 24 Parganas District under Alipore Division and South 24 Parganas Water Supply Division-I, PHE Dte. (2nd Call) Block Name - Canning-I, Canning-II, Sagar, Mathurapur-I, Falta, Budge Budge - II, Thakurpukur Maheshtala, Bishnupur-I Village Name : - Bayarsing, Par Kalugachhi, Ghoramara, Barasi, Sarberia, Narayanipur, Uttar Joykrishnapur, Sahapur Kamalpur, Harindanga, Chaluary, Digra, Mallikpur, Chandpala Anantapathpur, Barhay Batpur, Nityanandapur, Srirampur, Rania Gobindapur, Kuchigadi, Sankharipota, Alipore | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000452/2025-2026 | 3696/AD | 31/07/2025 | 15/08/2025 | M & M GRAPHICS | 5.04 | 0 | 0 | 100
317 | JALPAIGURI |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Erection of display board on Swajal Gram / Har Ghar Jal Village at various location within South 24 Parganas District under Alipore Division and South 24 Parganas Water Supply Division-I, PHE Dte. (2nd Call) Block Name - Canning-I, Canning-II, Sagar, Mathurapur-I, Falta, Budge Budge - II, Thakurpukur Maheshtala, Bishnupur-I Village Name : - Bayarsing, Par Kalugachhi, Ghoramara, Barasi, Sarberia, Narayanipur, Uttar Joykrishnapur, Sahapur Kamalpur, Harindanga, Chaluary, Digra, Mallikpur, Chandpala Anantapathpur, Barhay Batpur, Nityanandapur, Srirampur, Rania Gobindapur, Kuchigadi, Sankharipota, Alipore | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000452/2025-2026 | 3696/AD | 31/07/2025 | 15/08/2025 | M & M GRAPHICS | 5.04 | 0 | 0 | 100
318 | JHARGRAM |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Erection of display board on Swajal Gram / Har Ghar Jal Village at various location within South 24 Parganas District under Alipore Division and South 24 Parganas Water Supply Division-I, PHE Dte. (2nd Call) Block Name - Canning-I, Canning-II, Sagar, Mathurapur-I, Falta, Budge Budge - II, Thakurpukur Maheshtala, Bishnupur-I Village Name : - Bayarsing, Par Kalugachhi, Ghoramara, Barasi, Sarberia, Narayanipur, Uttar Joykrishnapur, Sahapur Kamalpur, Harindanga, Chaluary, Digra, Mallikpur, Chandpala Anantapathpur, Barhay Batpur, Nityanandapur, Srirampur, Rania Gobindapur, Kuchigadi, Sankharipota, Alipore | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000452/2025-2026 | 3696/AD | 31/07/2025 | 15/08/2025 | M & M GRAPHICS | 5.04 | 0 | 0 | 100
319 | KALIMPONG |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Erection of display board on Swajal Gram / Har Ghar Jal Village at various location within South 24 Parganas District under Alipore Division and South 24 Parganas Water Supply Division-I, PHE Dte. (2nd Call) Block Name - Canning-I, Canning-II, Sagar, Mathurapur-I, Falta, Budge Budge - II, Thakurpukur Maheshtala, Bishnupur-I Village Name : - Bayarsing, Par Kalugachhi, Ghoramara, Barasi, Sarberia, Narayanipur, Uttar Joykrishnapur, Sahapur Kamalpur, Harindanga, Chaluary, Digra, Mallikpur, Chandpala Anantapathpur, Barhay Batpur, Nityanandapur, Srirampur, Rania Gobindapur, Kuchigadi, Sankharipota, Alipore | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000452/2025-2026 | 3696/AD | 31/07/2025 | 15/08/2025 | M & M GRAPHICS | 5.04 | 0 | 0 | 100
320 | MALDAH |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Erection of display board on Swajal Gram / Har Ghar Jal Village at various location within South 24 Parganas District under Alipore Division and South 24 Parganas Water Supply Division-I, PHE Dte. (2nd Call) Block Name - Canning-I, Canning-II, Sagar, Mathurapur-I, Falta, Budge Budge - II, Thakurpukur Maheshtala, Bishnupur-I Village Name : - Bayarsing, Par Kalugachhi, Ghoramara, Barasi, Sarberia, Narayanipur, Uttar Joykrishnapur, Sahapur Kamalpur, Harindanga, Chaluary, Digra, Mallikpur, Chandpala Anantapathpur, Barhay Batpur, Nityanandapur, Srirampur, Rania Gobindapur, Kuchigadi, Sankharipota, Alipore | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000452/2025-2026 | 3696/AD | 31/07/2025 | 15/08/2025 | M & M GRAPHICS | 5.04 | 0 | 0 | 100
321 | MURSHIDABAD |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Erection of display board on Swajal Gram / Har Ghar Jal Village at various location within South 24 Parganas District under Alipore Division and South 24 Parganas Water Supply Division-I, PHE Dte. (2nd Call) Block Name - Canning-I, Canning-II, Sagar, Mathurapur-I, Falta, Budge Budge - II, Thakurpukur Maheshtala, Bishnupur-I Village Name : - Bayarsing, Par Kalugachhi, Ghoramara, Barasi, Sarberia, Narayanipur, Uttar Joykrishnapur, Sahapur Kamalpur, Harindanga, Chaluary, Digra, Mallikpur, Chandpala Anantapathpur, Barhay Batpur, Nityanandapur, Srirampur, Rania Gobindapur, Kuchigadi, Sankharipota, Alipore | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000452/2025-2026 | 3696/AD | 31/07/2025 | 15/08/2025 | M & M GRAPHICS | 5.04 | 0 | 0 | 100
322 | NADIA |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Erection of display board on Swajal Gram / Har Ghar Jal Village at various location within South 24 Parganas District under Alipore Division and South 24 Parganas Water Supply Division-I, PHE Dte. (2nd Call) Block Name - Canning-I, Canning-II, Sagar, Mathurapur-I, Falta, Budge Budge - II, Thakurpukur Maheshtala, Bishnupur-I Village Name : - Bayarsing, Par Kalugachhi, Ghoramara, Barasi, Sarberia, Narayanipur, Uttar Joykrishnapur, Sahapur Kamalpur, Harindanga, Chaluary, Digra, Mallikpur, Chandpala Anantapathpur, Barhay Batpur, Nityanandapur, Srirampur, Rania Gobindapur, Kuchigadi, Sankharipota, Alipore | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000452/2025-2026 | 3696/AD | 31/07/2025 | 15/08/2025 | M & M GRAPHICS | 5.04 | 0 | 0 | 100
323 | NORTH 24 PARGANAS |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Erection of display board on Swajal Gram / Har Ghar Jal Village at various location within South 24 Parganas District under Alipore Division and South 24 Parganas Water Supply Division-I, PHE Dte. (2nd Call) Block Name - Canning-I, Canning-II, Sagar, Mathurapur-I, Falta, Budge Budge - II, Thakurpukur Maheshtala, Bishnupur-I Village Name : - Bayarsing, Par Kalugachhi, Ghoramara, Barasi, Sarberia, Narayanipur, Uttar Joykrishnapur, Sahapur Kamalpur, Harindanga, Chaluary, Digra, Mallikpur, Chandpala Anantapathpur, Barhay Batpur, Nityanandapur, Srirampur, Rania Gobindapur, Kuchigadi, Sankharipota, Alipore | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000452/2025-2026 | 3696/AD | 31/07/2025 | 15/08/2025 | M & M GRAPHICS | 5.04 | 0 | 0 | 100
324 | PASCHIM BARDHAMAN |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Erection of display board on Swajal Gram / Har Ghar Jal Village at various location within South 24 Parganas District under Alipore Division and South 24 Parganas Water Supply Division-I, PHE Dte. (2nd Call) Block Name - Canning-I, Canning-II, Sagar, Mathurapur-I, Falta, Budge Budge - II, Thakurpukur Maheshtala, Bishnupur-I Village Name : - Bayarsing, Par Kalugachhi, Ghoramara, Barasi, Sarberia, Narayanipur, Uttar Joykrishnapur, Sahapur Kamalpur, Harindanga, Chaluary, Digra, Mallikpur, Chandpala Anantapathpur, Barhay Batpur, Nityanandapur, Srirampur, Rania Gobindapur, Kuchigadi, Sankharipota, Alipore | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000452/2025-2026 | 3696/AD | 31/07/2025 | 15/08/2025 | M & M GRAPHICS | 5.04 | 0 | 0 | 100
325 | PASCHIM MEDINIPUR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Erection of display board on Swajal Gram / Har Ghar Jal Village at various location within South 24 Parganas District under Alipore Division and South 24 Parganas Water Supply Division-I, PHE Dte. (2nd Call) Block Name - Canning-I, Canning-II, Sagar, Mathurapur-I, Falta, Budge Budge - II, Thakurpukur Maheshtala, Bishnupur-I Village Name : - Bayarsing, Par Kalugachhi, Ghoramara, Barasi, Sarberia, Narayanipur, Uttar Joykrishnapur, Sahapur Kamalpur, Harindanga, Chaluary, Digra, Mallikpur, Chandpala Anantapathpur, Barhay Batpur, Nityanandapur, Srirampur, Rania Gobindapur, Kuchigadi, Sankharipota, Alipore | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000452/2025-2026 | 3696/AD | 31/07/2025 | 15/08/2025 | M & M GRAPHICS | 5.04 | 0 | 0 | 100
326 | PURBA BARDHAMAN |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Erection of display board on Swajal Gram / Har Ghar Jal Village at various location within South 24 Parganas District under Alipore Division and South 24 Parganas Water Supply Division-I, PHE Dte. (2nd Call) Block Name - Canning-I, Canning-II, Sagar, Mathurapur-I, Falta, Budge Budge - II, Thakurpukur Maheshtala, Bishnupur-I Village Name : - Bayarsing, Par Kalugachhi, Ghoramara, Barasi, Sarberia, Narayanipur, Uttar Joykrishnapur, Sahapur Kamalpur, Harindanga, Chaluary, Digra, Mallikpur, Chandpala Anantapathpur, Barhay Batpur, Nityanandapur, Srirampur, Rania Gobindapur, Kuchigadi, Sankharipota, Alipore | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000452/2025-2026 | 3696/AD | 31/07/2025 | 15/08/2025 | M & M GRAPHICS | 5.04 | 0 | 0 | 100
327 | PURBA MEDINIPUR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Erection of display board on Swajal Gram / Har Ghar Jal Village at various location within South 24 Parganas District under Alipore Division and South 24 Parganas Water Supply Division-I, PHE Dte. (2nd Call) Block Name - Canning-I, Canning-II, Sagar, Mathurapur-I, Falta, Budge Budge - II, Thakurpukur Maheshtala, Bishnupur-I Village Name : - Bayarsing, Par Kalugachhi, Ghoramara, Barasi, Sarberia, Narayanipur, Uttar Joykrishnapur, Sahapur Kamalpur, Harindanga, Chaluary, Digra, Mallikpur, Chandpala Anantapathpur, Barhay Batpur, Nityanandapur, Srirampur, Rania Gobindapur, Kuchigadi, Sankharipota, Alipore | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000452/2025-2026 | 3696/AD | 31/07/2025 | 15/08/2025 | M & M GRAPHICS | 5.04 | 0 | 0 | 100
328 | PURULIA |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Erection of display board on Swajal Gram / Har Ghar Jal Village at various location within South 24 Parganas District under Alipore Division and South 24 Parganas Water Supply Division-I, PHE Dte. (2nd Call) Block Name - Canning-I, Canning-II, Sagar, Mathurapur-I, Falta, Budge Budge - II, Thakurpukur Maheshtala, Bishnupur-I Village Name : - Bayarsing, Par Kalugachhi, Ghoramara, Barasi, Sarberia, Narayanipur, Uttar Joykrishnapur, Sahapur Kamalpur, Harindanga, Chaluary, Digra, Mallikpur, Chandpala Anantapathpur, Barhay Batpur, Nityanandapur, Srirampur, Rania Gobindapur, Kuchigadi, Sankharipota, Alipore | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000452/2025-2026 | 3696/AD | 31/07/2025 | 15/08/2025 | M & M GRAPHICS | 5.04 | 0 | 0 | 100
329 | SOUTH 24 PARGANAS |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Erection of display board on Swajal Gram / Har Ghar Jal Village at various location within South 24 Parganas District under Alipore Division and South 24 Parganas Water Supply Division-I, PHE Dte. (2nd Call) Block Name - Canning-I, Canning-II, Sagar, Mathurapur-I, Falta, Budge Budge - II, Thakurpukur Maheshtala, Bishnupur-I Village Name : - Bayarsing, Par Kalugachhi, Ghoramara, Barasi, Sarberia, Narayanipur, Uttar Joykrishnapur, Sahapur Kamalpur, Harindanga, Chaluary, Digra, Mallikpur, Chandpala Anantapathpur, Barhay Batpur, Nityanandapur, Srirampur, Rania Gobindapur, Kuchigadi, Sankharipota, Alipore | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000452/2025-2026 | 3696/AD | 31/07/2025 | 15/08/2025 | M & M GRAPHICS | 5.04 | 0 | 0 | 100
330 | UTTAR DINAJPUR |  | Alipore Division | Capacity building activity & Mass Awareness generation activities (IEC) and with special emphasis on water quality under Jal Jeevan Mission (JJM) Water Quality Monitoring & Surveillance Programme(WQMSP) | SM/19068 | Support-WQMSP | Erection of display board on Swajal Gram / Har Ghar Jal Village at various location within South 24 Parganas District under Alipore Division and South 24 Parganas Water Supply Division-I, PHE Dte. (2nd Call) Block Name - Canning-I, Canning-II, Sagar, Mathurapur-I, Falta, Budge Budge - II, Thakurpukur Maheshtala, Bishnupur-I Village Name : - Bayarsing, Par Kalugachhi, Ghoramara, Barasi, Sarberia, Narayanipur, Uttar Joykrishnapur, Sahapur Kamalpur, Harindanga, Chaluary, Digra, Mallikpur, Chandpala Anantapathpur, Barhay Batpur, Nityanandapur, Srirampur, Rania Gobindapur, Kuchigadi, Sankharipota, Alipore | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000452/2025-2026 | 3696/AD | 31/07/2025 | 15/08/2025 | M & M GRAPHICS | 5.04 | 0 | 0 | 100
Total | [13 empty] | 3545.43 | 2564.09 | 72.32