## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000215/2024-2025 | 3188/RS | 30/12/2024 | 30/03/2025 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 37.23 | 0 | 0 | 99
2 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000215/2024-2025 | 3188/RS | 30/12/2024 | 30/03/2025 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 37.23 | 0 | 0 | 99
3 | DARJEELING |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000215/2024-2025 | 3188/RS | 30/12/2024 | 30/03/2025 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 37.23 | 0 | 0 | 99
4 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000215/2024-2025 | 3188/RS | 30/12/2024 | 30/03/2025 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 37.23 | 0 | 0 | 99
5 | KALIMPONG |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000215/2024-2025 | 3188/RS | 30/12/2024 | 30/03/2025 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 37.23 | 0 | 0 | 99
6 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000375/2023-2024 | 834/RS | 13/03/2024 | 13/11/2024 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 67.84 | 47.12 | 69.46 | 50
7 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000375/2023-2024 | 834/RS | 13/03/2024 | 13/11/2024 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 67.84 | 47.12 | 69.46 | 50
8 | DARJEELING |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000375/2023-2024 | 834/RS | 13/03/2024 | 13/11/2024 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 67.84 | 47.12 | 69.46 | 50
9 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000375/2023-2024 | 834/RS | 13/03/2024 | 13/11/2024 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 67.84 | 47.12 | 69.46 | 50
10 | KALIMPONG |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000375/2023-2024 | 834/RS | 13/03/2024 | 13/11/2024 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 67.84 | 47.12 | 69.46 | 50
11 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000336/2023-2024 | 779/RS | 07/03/2024 | 01/01/2025 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 217.14 | 100.58 | 46.32 | 50
12 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000336/2023-2024 | 779/RS | 07/03/2024 | 01/01/2025 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 217.14 | 100.58 | 46.32 | 50
13 | DARJEELING |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000336/2023-2024 | 779/RS | 07/03/2024 | 01/01/2025 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 217.14 | 100.58 | 46.32 | 50
14 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000336/2023-2024 | 779/RS | 07/03/2024 | 01/01/2025 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 217.14 | 100.58 | 46.32 | 50
15 | KALIMPONG |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000336/2023-2024 | 779/RS | 07/03/2024 | 01/01/2025 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 217.14 | 100.58 | 46.32 | 50
16 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000369/2023-2024 | 832/RS | 13/03/2024 | 13/11/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 129.92 | 110.1 | 84.75 | 50
17 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000369/2023-2024 | 832/RS | 13/03/2024 | 13/11/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 129.92 | 110.1 | 84.75 | 50
18 | DARJEELING |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000369/2023-2024 | 832/RS | 13/03/2024 | 13/11/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 129.92 | 110.1 | 84.75 | 50
19 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000369/2023-2024 | 832/RS | 13/03/2024 | 13/11/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 129.92 | 110.1 | 84.75 | 50
20 | KALIMPONG |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000369/2023-2024 | 832/RS | 13/03/2024 | 13/11/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 129.92 | 110.1 | 84.75 | 50
21 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000216/2024-2025 | 3183/RS | 30/12/2024 | 30/03/2025 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 71.29 | 71.29 | 100 | 99
22 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000216/2024-2025 | 3183/RS | 30/12/2024 | 30/03/2025 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 71.29 | 71.29 | 100 | 99
23 | DARJEELING |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000216/2024-2025 | 3183/RS | 30/12/2024 | 30/03/2025 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 71.29 | 71.29 | 100 | 99
24 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000216/2024-2025 | 3183/RS | 30/12/2024 | 30/03/2025 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 71.29 | 71.29 | 100 | 99
25 | KALIMPONG |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000216/2024-2025 | 3183/RS | 30/12/2024 | 30/03/2025 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 71.29 | 71.29 | 100 | 99
26 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000236/2024-2025 | 3190/RS | 31/12/2024 | 31/03/2025 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 49.93 | 4.69 | 9.4 | 99
27 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000236/2024-2025 | 3190/RS | 31/12/2024 | 31/03/2025 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 49.93 | 4.69 | 9.4 | 99
28 | DARJEELING |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000236/2024-2025 | 3190/RS | 31/12/2024 | 31/03/2025 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 49.93 | 4.69 | 9.4 | 99
29 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000236/2024-2025 | 3190/RS | 31/12/2024 | 31/03/2025 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 49.93 | 4.69 | 9.4 | 99
30 | KALIMPONG |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000236/2024-2025 | 3190/RS | 31/12/2024 | 31/03/2025 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 49.93 | 4.69 | 9.4 | 99
31 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000335/2023-2024 | 780/RS | 07/03/2024 | 01/01/2025 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 113.09 | 77.04 | 68.13 | 50
32 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000335/2023-2024 | 780/RS | 07/03/2024 | 01/01/2025 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 113.09 | 77.04 | 68.13 | 50
33 | DARJEELING |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000335/2023-2024 | 780/RS | 07/03/2024 | 01/01/2025 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 113.09 | 77.04 | 68.13 | 50
34 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000335/2023-2024 | 780/RS | 07/03/2024 | 01/01/2025 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 113.09 | 77.04 | 68.13 | 50
35 | KALIMPONG |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000335/2023-2024 | 780/RS | 07/03/2024 | 01/01/2025 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 113.09 | 77.04 | 68.13 | 50
36 | ALIPURDUAR |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization &capacity building activities at Darjeeling (Hill) & Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities. | Assistant Engineer II | Junior Engineer I | ORD/000188/2025-2026 | 82/NKWSMD | 30/01/2026 | 30/01/2027 | LIMRA SOCIAL WELFARE SOCIETY | 165.14 | 0 | 0 | 50
37 | COOCHBEHAR |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization &capacity building activities at Darjeeling (Hill) & Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities. | Assistant Engineer II | Junior Engineer I | ORD/000188/2025-2026 | 82/NKWSMD | 30/01/2026 | 30/01/2027 | LIMRA SOCIAL WELFARE SOCIETY | 165.14 | 0 | 0 | 50
38 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization &capacity building activities at Darjeeling (Hill) & Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities. | Assistant Engineer II | Junior Engineer I | ORD/000188/2025-2026 | 82/NKWSMD | 30/01/2026 | 30/01/2027 | LIMRA SOCIAL WELFARE SOCIETY | 165.14 | 0 | 0 | 50
39 | JALPAIGURI |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization &capacity building activities at Darjeeling (Hill) & Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities. | Assistant Engineer II | Junior Engineer I | ORD/000188/2025-2026 | 82/NKWSMD | 30/01/2026 | 30/01/2027 | LIMRA SOCIAL WELFARE SOCIETY | 165.14 | 0 | 0 | 50
40 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization &capacity building activities at Darjeeling (Hill) & Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities. | Assistant Engineer II | Junior Engineer I | ORD/000188/2025-2026 | 82/NKWSMD | 30/01/2026 | 30/01/2027 | LIMRA SOCIAL WELFARE SOCIETY | 165.14 | 0 | 0 | 50
Total | [13 empty] | 4257.87 | 2054.13 | 48.24