## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000375/2023-2024 | 834/RS | 13/03/2024 | 13/11/2024 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 67.84 | 0 | 0 | 50
2 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000375/2023-2024 | 834/RS | 13/03/2024 | 13/11/2024 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 67.84 | 0 | 0 | 50
3 | DARJEELING |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000375/2023-2024 | 834/RS | 13/03/2024 | 13/11/2024 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 67.84 | 0 | 0 | 50
4 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000375/2023-2024 | 834/RS | 13/03/2024 | 13/11/2024 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 67.84 | 0 | 0 | 50
5 | KALIMPONG |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000375/2023-2024 | 834/RS | 13/03/2024 | 13/11/2024 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 67.84 | 0 | 0 | 50
6 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000236/2024-2025 | 3190/RS | 31/12/2024 | 31/03/2025 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 49.93 | 0 | 0 | 99
7 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000236/2024-2025 | 3190/RS | 31/12/2024 | 31/03/2025 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 49.93 | 0 | 0 | 99
8 | DARJEELING |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000236/2024-2025 | 3190/RS | 31/12/2024 | 31/03/2025 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 49.93 | 0 | 0 | 99
9 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000236/2024-2025 | 3190/RS | 31/12/2024 | 31/03/2025 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 49.93 | 0 | 0 | 99
10 | KALIMPONG |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000236/2024-2025 | 3190/RS | 31/12/2024 | 31/03/2025 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 49.93 | 0 | 0 | 99
11 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000215/2024-2025 | 3188/RS | 30/12/2024 | 30/03/2025 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 37.23 | 0 | 0 | 99
12 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000215/2024-2025 | 3188/RS | 30/12/2024 | 30/03/2025 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 37.23 | 0 | 0 | 99
13 | DARJEELING |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000215/2024-2025 | 3188/RS | 30/12/2024 | 30/03/2025 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 37.23 | 0 | 0 | 99
14 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000215/2024-2025 | 3188/RS | 30/12/2024 | 30/03/2025 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 37.23 | 0 | 0 | 99
15 | KALIMPONG |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000215/2024-2025 | 3188/RS | 30/12/2024 | 30/03/2025 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 37.23 | 0 | 0 | 99
16 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000216/2024-2025 | 3183/RS | 30/12/2024 | 30/03/2025 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 71.29 | 0 | 0 | 99
17 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000216/2024-2025 | 3183/RS | 30/12/2024 | 30/03/2025 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 71.29 | 0 | 0 | 99
18 | DARJEELING |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000216/2024-2025 | 3183/RS | 30/12/2024 | 30/03/2025 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 71.29 | 0 | 0 | 99
19 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000216/2024-2025 | 3183/RS | 30/12/2024 | 30/03/2025 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 71.29 | 0 | 0 | 99
20 | KALIMPONG |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19231 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000216/2024-2025 | 3183/RS | 30/12/2024 | 30/03/2025 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 71.29 | 0 | 0 | 99
Total | [13 empty] | 1131.44 | 0 | 0