## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000357/2023-2024 | 701/RS | 29/02/2024 | 31/12/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 255.26 | 0 | 0 | 10
2 | BIRBHUM |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000357/2023-2024 | 701/RS | 29/02/2024 | 31/12/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 255.26 | 0 | 0 | 10
3 | COOCHBEHAR |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000357/2023-2024 | 701/RS | 29/02/2024 | 31/12/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 255.26 | 0 | 0 | 10
4 | DAKSHIN DINAJPUR |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000357/2023-2024 | 701/RS | 29/02/2024 | 31/12/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 255.26 | 0 | 0 | 10
5 | DARJEELING |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000357/2023-2024 | 701/RS | 29/02/2024 | 31/12/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 255.26 | 0 | 0 | 10
6 | JALPAIGURI |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000357/2023-2024 | 701/RS | 29/02/2024 | 31/12/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 255.26 | 0 | 0 | 10
7 | KALIMPONG |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000357/2023-2024 | 701/RS | 29/02/2024 | 31/12/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 255.26 | 0 | 0 | 10
8 | MALDAH |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000357/2023-2024 | 701/RS | 29/02/2024 | 31/12/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 255.26 | 0 | 0 | 10
9 | MURSHIDABAD |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000357/2023-2024 | 701/RS | 29/02/2024 | 31/12/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 255.26 | 0 | 0 | 10
10 | PASCHIM BARDHAMAN |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000357/2023-2024 | 701/RS | 29/02/2024 | 31/12/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 255.26 | 0 | 0 | 10
11 | PURBA BARDHAMAN |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000357/2023-2024 | 701/RS | 29/02/2024 | 31/12/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 255.26 | 0 | 0 | 10
12 | UTTAR DINAJPUR |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000357/2023-2024 | 701/RS | 29/02/2024 | 31/12/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 255.26 | 0 | 0 | 10
13 | ALIPURDUAR |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000354/2023-2024 | 698/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 251.74 | 183.94 | 73.07 | 10
14 | BIRBHUM |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000354/2023-2024 | 698/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 251.74 | 183.94 | 73.07 | 10
15 | COOCHBEHAR |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000354/2023-2024 | 698/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 251.74 | 183.94 | 73.07 | 10
16 | DAKSHIN DINAJPUR |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000354/2023-2024 | 698/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 251.74 | 183.94 | 73.07 | 10
17 | DARJEELING |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000354/2023-2024 | 698/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 251.74 | 183.94 | 73.07 | 10
18 | JALPAIGURI |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000354/2023-2024 | 698/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 251.74 | 183.94 | 73.07 | 10
19 | KALIMPONG |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000354/2023-2024 | 698/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 251.74 | 183.94 | 73.07 | 10
20 | MALDAH |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000354/2023-2024 | 698/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 251.74 | 183.94 | 73.07 | 10
21 | MURSHIDABAD |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000354/2023-2024 | 698/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 251.74 | 183.94 | 73.07 | 10
22 | PASCHIM BARDHAMAN |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000354/2023-2024 | 698/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 251.74 | 183.94 | 73.07 | 10
23 | PURBA BARDHAMAN |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000354/2023-2024 | 698/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 251.74 | 183.94 | 73.07 | 10
24 | UTTAR DINAJPUR |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000354/2023-2024 | 698/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 251.74 | 183.94 | 73.07 | 10
25 | ALIPURDUAR |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Bardhaman, Paschim Bardhaman, Birbhum, Malda, and Murshidabadunder Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000355/2023-2024 | 699/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 226.8 | 170.6 | 75.22 | 50
26 | BIRBHUM |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Bardhaman, Paschim Bardhaman, Birbhum, Malda, and Murshidabadunder Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000355/2023-2024 | 699/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 226.8 | 170.6 | 75.22 | 50
27 | COOCHBEHAR |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Bardhaman, Paschim Bardhaman, Birbhum, Malda, and Murshidabadunder Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000355/2023-2024 | 699/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 226.8 | 170.6 | 75.22 | 50
28 | DAKSHIN DINAJPUR |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Bardhaman, Paschim Bardhaman, Birbhum, Malda, and Murshidabadunder Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000355/2023-2024 | 699/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 226.8 | 170.6 | 75.22 | 50
29 | DARJEELING |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Bardhaman, Paschim Bardhaman, Birbhum, Malda, and Murshidabadunder Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000355/2023-2024 | 699/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 226.8 | 170.6 | 75.22 | 50
30 | JALPAIGURI |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Bardhaman, Paschim Bardhaman, Birbhum, Malda, and Murshidabadunder Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000355/2023-2024 | 699/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 226.8 | 170.6 | 75.22 | 50
31 | KALIMPONG |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Bardhaman, Paschim Bardhaman, Birbhum, Malda, and Murshidabadunder Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000355/2023-2024 | 699/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 226.8 | 170.6 | 75.22 | 50
32 | MALDAH |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Bardhaman, Paschim Bardhaman, Birbhum, Malda, and Murshidabadunder Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000355/2023-2024 | 699/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 226.8 | 170.6 | 75.22 | 50
33 | MURSHIDABAD |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Bardhaman, Paschim Bardhaman, Birbhum, Malda, and Murshidabadunder Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000355/2023-2024 | 699/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 226.8 | 170.6 | 75.22 | 50
34 | PASCHIM BARDHAMAN |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Bardhaman, Paschim Bardhaman, Birbhum, Malda, and Murshidabadunder Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000355/2023-2024 | 699/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 226.8 | 170.6 | 75.22 | 50
35 | PURBA BARDHAMAN |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Bardhaman, Paschim Bardhaman, Birbhum, Malda, and Murshidabadunder Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000355/2023-2024 | 699/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 226.8 | 170.6 | 75.22 | 50
36 | UTTAR DINAJPUR |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Bardhaman, Paschim Bardhaman, Birbhum, Malda, and Murshidabadunder Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000355/2023-2024 | 699/RS | 01/03/2024 | 01/01/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 226.8 | 170.6 | 75.22 | 50
37 | ALIPURDUAR |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission |  |  | ORD/000298/2024-2025 | 608/RS | 17/03/2025 | 17/03/2026 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 302.09 | 0 | 0 | 10
38 | BIRBHUM |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission |  |  | ORD/000298/2024-2025 | 608/RS | 17/03/2025 | 17/03/2026 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 302.09 | 0 | 0 | 10
39 | COOCHBEHAR |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission |  |  | ORD/000298/2024-2025 | 608/RS | 17/03/2025 | 17/03/2026 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 302.09 | 0 | 0 | 10
40 | DAKSHIN DINAJPUR |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission |  |  | ORD/000298/2024-2025 | 608/RS | 17/03/2025 | 17/03/2026 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 302.09 | 0 | 0 | 10
41 | DARJEELING |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission |  |  | ORD/000298/2024-2025 | 608/RS | 17/03/2025 | 17/03/2026 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 302.09 | 0 | 0 | 10
42 | JALPAIGURI |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission |  |  | ORD/000298/2024-2025 | 608/RS | 17/03/2025 | 17/03/2026 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 302.09 | 0 | 0 | 10
43 | KALIMPONG |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission |  |  | ORD/000298/2024-2025 | 608/RS | 17/03/2025 | 17/03/2026 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 302.09 | 0 | 0 | 10
44 | MALDAH |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission |  |  | ORD/000298/2024-2025 | 608/RS | 17/03/2025 | 17/03/2026 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 302.09 | 0 | 0 | 10
45 | MURSHIDABAD |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission |  |  | ORD/000298/2024-2025 | 608/RS | 17/03/2025 | 17/03/2026 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 302.09 | 0 | 0 | 10
46 | PASCHIM BARDHAMAN |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission |  |  | ORD/000298/2024-2025 | 608/RS | 17/03/2025 | 17/03/2026 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 302.09 | 0 | 0 | 10
47 | PURBA BARDHAMAN |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission |  |  | ORD/000298/2024-2025 | 608/RS | 17/03/2025 | 17/03/2026 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 302.09 | 0 | 0 | 10
48 | UTTAR DINAJPUR |  | Resource | Setting up of District Project Management Unit (DPMU) at Alipurduar, Jalpaiguri, Coochbehar, Darjeeling , Kalimpong, Uttar Dinajpur, Dakshin Dinajpur, Purba & Paschim Bardhaman, Birbhum and Murshidabad districts under Jal Jeevan Mission (JJM) | SM/19240 |  | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission |  |  | ORD/000298/2024-2025 | 608/RS | 17/03/2025 | 17/03/2026 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 302.09 | 0 | 0 | 10
Total | [13 empty] | 12430.64 | 4254.51 | 34.23