## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Design, Development and Implementation of Single Window Platform (SWP) for Public Health Engineering Department for Monitoring of Election Infrastructure Works. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 453/RS | 28/02/2025 | 28/02/2026 | NUMERICO INFORMATIC SYSTEMS PVT LTD | 7.75 | 0 | 0 | 5
2 | BANKURA |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Design, Development and Implementation of Single Window Platform (SWP) for Public Health Engineering Department for Monitoring of Election Infrastructure Works. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 453/RS | 28/02/2025 | 28/02/2026 | NUMERICO INFORMATIC SYSTEMS PVT LTD | 7.75 | 0 | 0 | 5
3 | BIRBHUM |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Design, Development and Implementation of Single Window Platform (SWP) for Public Health Engineering Department for Monitoring of Election Infrastructure Works. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 453/RS | 28/02/2025 | 28/02/2026 | NUMERICO INFORMATIC SYSTEMS PVT LTD | 7.75 | 0 | 0 | 5
4 | COOCHBEHAR |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Design, Development and Implementation of Single Window Platform (SWP) for Public Health Engineering Department for Monitoring of Election Infrastructure Works. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 453/RS | 28/02/2025 | 28/02/2026 | NUMERICO INFORMATIC SYSTEMS PVT LTD | 7.75 | 0 | 0 | 5
5 | DAKSHIN DINAJPUR |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Design, Development and Implementation of Single Window Platform (SWP) for Public Health Engineering Department for Monitoring of Election Infrastructure Works. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 453/RS | 28/02/2025 | 28/02/2026 | NUMERICO INFORMATIC SYSTEMS PVT LTD | 7.75 | 0 | 0 | 5
6 | DARJEELING |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Design, Development and Implementation of Single Window Platform (SWP) for Public Health Engineering Department for Monitoring of Election Infrastructure Works. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 453/RS | 28/02/2025 | 28/02/2026 | NUMERICO INFORMATIC SYSTEMS PVT LTD | 7.75 | 0 | 0 | 5
7 | HOOGHLY |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Design, Development and Implementation of Single Window Platform (SWP) for Public Health Engineering Department for Monitoring of Election Infrastructure Works. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 453/RS | 28/02/2025 | 28/02/2026 | NUMERICO INFORMATIC SYSTEMS PVT LTD | 7.75 | 0 | 0 | 5
8 | HOWRAH |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Design, Development and Implementation of Single Window Platform (SWP) for Public Health Engineering Department for Monitoring of Election Infrastructure Works. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 453/RS | 28/02/2025 | 28/02/2026 | NUMERICO INFORMATIC SYSTEMS PVT LTD | 7.75 | 0 | 0 | 5
9 | JALPAIGURI |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Design, Development and Implementation of Single Window Platform (SWP) for Public Health Engineering Department for Monitoring of Election Infrastructure Works. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 453/RS | 28/02/2025 | 28/02/2026 | NUMERICO INFORMATIC SYSTEMS PVT LTD | 7.75 | 0 | 0 | 5
10 | JHARGRAM |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Design, Development and Implementation of Single Window Platform (SWP) for Public Health Engineering Department for Monitoring of Election Infrastructure Works. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 453/RS | 28/02/2025 | 28/02/2026 | NUMERICO INFORMATIC SYSTEMS PVT LTD | 7.75 | 0 | 0 | 5
11 | KALIMPONG |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Design, Development and Implementation of Single Window Platform (SWP) for Public Health Engineering Department for Monitoring of Election Infrastructure Works. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 453/RS | 28/02/2025 | 28/02/2026 | NUMERICO INFORMATIC SYSTEMS PVT LTD | 7.75 | 0 | 0 | 5
12 | MALDAH |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Design, Development and Implementation of Single Window Platform (SWP) for Public Health Engineering Department for Monitoring of Election Infrastructure Works. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 453/RS | 28/02/2025 | 28/02/2026 | NUMERICO INFORMATIC SYSTEMS PVT LTD | 7.75 | 0 | 0 | 5
13 | MURSHIDABAD |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Design, Development and Implementation of Single Window Platform (SWP) for Public Health Engineering Department for Monitoring of Election Infrastructure Works. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 453/RS | 28/02/2025 | 28/02/2026 | NUMERICO INFORMATIC SYSTEMS PVT LTD | 7.75 | 0 | 0 | 5
14 | NADIA |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Design, Development and Implementation of Single Window Platform (SWP) for Public Health Engineering Department for Monitoring of Election Infrastructure Works. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 453/RS | 28/02/2025 | 28/02/2026 | NUMERICO INFORMATIC SYSTEMS PVT LTD | 7.75 | 0 | 0 | 5
15 | NORTH 24 PARGANAS |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Design, Development and Implementation of Single Window Platform (SWP) for Public Health Engineering Department for Monitoring of Election Infrastructure Works. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 453/RS | 28/02/2025 | 28/02/2026 | NUMERICO INFORMATIC SYSTEMS PVT LTD | 7.75 | 0 | 0 | 5
16 | PASCHIM BARDHAMAN |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Design, Development and Implementation of Single Window Platform (SWP) for Public Health Engineering Department for Monitoring of Election Infrastructure Works. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 453/RS | 28/02/2025 | 28/02/2026 | NUMERICO INFORMATIC SYSTEMS PVT LTD | 7.75 | 0 | 0 | 5
17 | PASCHIM MEDINIPUR |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Design, Development and Implementation of Single Window Platform (SWP) for Public Health Engineering Department for Monitoring of Election Infrastructure Works. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 453/RS | 28/02/2025 | 28/02/2026 | NUMERICO INFORMATIC SYSTEMS PVT LTD | 7.75 | 0 | 0 | 5
18 | PURBA BARDHAMAN |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Design, Development and Implementation of Single Window Platform (SWP) for Public Health Engineering Department for Monitoring of Election Infrastructure Works. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 453/RS | 28/02/2025 | 28/02/2026 | NUMERICO INFORMATIC SYSTEMS PVT LTD | 7.75 | 0 | 0 | 5
19 | PURBA MEDINIPUR |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Design, Development and Implementation of Single Window Platform (SWP) for Public Health Engineering Department for Monitoring of Election Infrastructure Works. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 453/RS | 28/02/2025 | 28/02/2026 | NUMERICO INFORMATIC SYSTEMS PVT LTD | 7.75 | 0 | 0 | 5
20 | PURULIA |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Design, Development and Implementation of Single Window Platform (SWP) for Public Health Engineering Department for Monitoring of Election Infrastructure Works. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 453/RS | 28/02/2025 | 28/02/2026 | NUMERICO INFORMATIC SYSTEMS PVT LTD | 7.75 | 0 | 0 | 5
21 | SOUTH 24 PARGANAS |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Design, Development and Implementation of Single Window Platform (SWP) for Public Health Engineering Department for Monitoring of Election Infrastructure Works. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 453/RS | 28/02/2025 | 28/02/2026 | NUMERICO INFORMATIC SYSTEMS PVT LTD | 7.75 | 0 | 0 | 5
22 | UTTAR DINAJPUR |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Design, Development and Implementation of Single Window Platform (SWP) for Public Health Engineering Department for Monitoring of Election Infrastructure Works. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 453/RS | 28/02/2025 | 28/02/2026 | NUMERICO INFORMATIC SYSTEMS PVT LTD | 7.75 | 0 | 0 | 5
23 | ALIPURDUAR |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Providing facilities to Push SMS Content and Bulk Push SMS Service, Supply of SAP Crystal Server 2020 (user) and SAP Crystal Reports 2020 licenses and other software and hardware for Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 2368/RS | 10/11/2025 | 10/12/2025 | APPLET PROJECTS & ENGINEERING PRIVATE LIMITED | 46.03 | 0 | 0 | 94
24 | BANKURA |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Providing facilities to Push SMS Content and Bulk Push SMS Service, Supply of SAP Crystal Server 2020 (user) and SAP Crystal Reports 2020 licenses and other software and hardware for Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 2368/RS | 10/11/2025 | 10/12/2025 | APPLET PROJECTS & ENGINEERING PRIVATE LIMITED | 46.03 | 0 | 0 | 94
25 | BIRBHUM |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Providing facilities to Push SMS Content and Bulk Push SMS Service, Supply of SAP Crystal Server 2020 (user) and SAP Crystal Reports 2020 licenses and other software and hardware for Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 2368/RS | 10/11/2025 | 10/12/2025 | APPLET PROJECTS & ENGINEERING PRIVATE LIMITED | 46.03 | 0 | 0 | 94
26 | COOCHBEHAR |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Providing facilities to Push SMS Content and Bulk Push SMS Service, Supply of SAP Crystal Server 2020 (user) and SAP Crystal Reports 2020 licenses and other software and hardware for Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 2368/RS | 10/11/2025 | 10/12/2025 | APPLET PROJECTS & ENGINEERING PRIVATE LIMITED | 46.03 | 0 | 0 | 94
27 | DAKSHIN DINAJPUR |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Providing facilities to Push SMS Content and Bulk Push SMS Service, Supply of SAP Crystal Server 2020 (user) and SAP Crystal Reports 2020 licenses and other software and hardware for Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 2368/RS | 10/11/2025 | 10/12/2025 | APPLET PROJECTS & ENGINEERING PRIVATE LIMITED | 46.03 | 0 | 0 | 94
28 | DARJEELING |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Providing facilities to Push SMS Content and Bulk Push SMS Service, Supply of SAP Crystal Server 2020 (user) and SAP Crystal Reports 2020 licenses and other software and hardware for Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 2368/RS | 10/11/2025 | 10/12/2025 | APPLET PROJECTS & ENGINEERING PRIVATE LIMITED | 46.03 | 0 | 0 | 94
29 | HOOGHLY |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Providing facilities to Push SMS Content and Bulk Push SMS Service, Supply of SAP Crystal Server 2020 (user) and SAP Crystal Reports 2020 licenses and other software and hardware for Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 2368/RS | 10/11/2025 | 10/12/2025 | APPLET PROJECTS & ENGINEERING PRIVATE LIMITED | 46.03 | 0 | 0 | 94
30 | HOWRAH |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Providing facilities to Push SMS Content and Bulk Push SMS Service, Supply of SAP Crystal Server 2020 (user) and SAP Crystal Reports 2020 licenses and other software and hardware for Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 2368/RS | 10/11/2025 | 10/12/2025 | APPLET PROJECTS & ENGINEERING PRIVATE LIMITED | 46.03 | 0 | 0 | 94
31 | JALPAIGURI |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Providing facilities to Push SMS Content and Bulk Push SMS Service, Supply of SAP Crystal Server 2020 (user) and SAP Crystal Reports 2020 licenses and other software and hardware for Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 2368/RS | 10/11/2025 | 10/12/2025 | APPLET PROJECTS & ENGINEERING PRIVATE LIMITED | 46.03 | 0 | 0 | 94
32 | JHARGRAM |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Providing facilities to Push SMS Content and Bulk Push SMS Service, Supply of SAP Crystal Server 2020 (user) and SAP Crystal Reports 2020 licenses and other software and hardware for Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 2368/RS | 10/11/2025 | 10/12/2025 | APPLET PROJECTS & ENGINEERING PRIVATE LIMITED | 46.03 | 0 | 0 | 94
33 | KALIMPONG |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Providing facilities to Push SMS Content and Bulk Push SMS Service, Supply of SAP Crystal Server 2020 (user) and SAP Crystal Reports 2020 licenses and other software and hardware for Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 2368/RS | 10/11/2025 | 10/12/2025 | APPLET PROJECTS & ENGINEERING PRIVATE LIMITED | 46.03 | 0 | 0 | 94
34 | MALDAH |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Providing facilities to Push SMS Content and Bulk Push SMS Service, Supply of SAP Crystal Server 2020 (user) and SAP Crystal Reports 2020 licenses and other software and hardware for Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 2368/RS | 10/11/2025 | 10/12/2025 | APPLET PROJECTS & ENGINEERING PRIVATE LIMITED | 46.03 | 0 | 0 | 94
35 | MURSHIDABAD |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Providing facilities to Push SMS Content and Bulk Push SMS Service, Supply of SAP Crystal Server 2020 (user) and SAP Crystal Reports 2020 licenses and other software and hardware for Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 2368/RS | 10/11/2025 | 10/12/2025 | APPLET PROJECTS & ENGINEERING PRIVATE LIMITED | 46.03 | 0 | 0 | 94
36 | NADIA |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Providing facilities to Push SMS Content and Bulk Push SMS Service, Supply of SAP Crystal Server 2020 (user) and SAP Crystal Reports 2020 licenses and other software and hardware for Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 2368/RS | 10/11/2025 | 10/12/2025 | APPLET PROJECTS & ENGINEERING PRIVATE LIMITED | 46.03 | 0 | 0 | 94
37 | NORTH 24 PARGANAS |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Providing facilities to Push SMS Content and Bulk Push SMS Service, Supply of SAP Crystal Server 2020 (user) and SAP Crystal Reports 2020 licenses and other software and hardware for Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 2368/RS | 10/11/2025 | 10/12/2025 | APPLET PROJECTS & ENGINEERING PRIVATE LIMITED | 46.03 | 0 | 0 | 94
38 | PASCHIM BARDHAMAN |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Providing facilities to Push SMS Content and Bulk Push SMS Service, Supply of SAP Crystal Server 2020 (user) and SAP Crystal Reports 2020 licenses and other software and hardware for Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 2368/RS | 10/11/2025 | 10/12/2025 | APPLET PROJECTS & ENGINEERING PRIVATE LIMITED | 46.03 | 0 | 0 | 94
39 | PASCHIM MEDINIPUR |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Providing facilities to Push SMS Content and Bulk Push SMS Service, Supply of SAP Crystal Server 2020 (user) and SAP Crystal Reports 2020 licenses and other software and hardware for Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 2368/RS | 10/11/2025 | 10/12/2025 | APPLET PROJECTS & ENGINEERING PRIVATE LIMITED | 46.03 | 0 | 0 | 94
40 | PURBA BARDHAMAN |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Providing facilities to Push SMS Content and Bulk Push SMS Service, Supply of SAP Crystal Server 2020 (user) and SAP Crystal Reports 2020 licenses and other software and hardware for Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 2368/RS | 10/11/2025 | 10/12/2025 | APPLET PROJECTS & ENGINEERING PRIVATE LIMITED | 46.03 | 0 | 0 | 94
41 | PURBA MEDINIPUR |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Providing facilities to Push SMS Content and Bulk Push SMS Service, Supply of SAP Crystal Server 2020 (user) and SAP Crystal Reports 2020 licenses and other software and hardware for Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 2368/RS | 10/11/2025 | 10/12/2025 | APPLET PROJECTS & ENGINEERING PRIVATE LIMITED | 46.03 | 0 | 0 | 94
42 | PURULIA |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Providing facilities to Push SMS Content and Bulk Push SMS Service, Supply of SAP Crystal Server 2020 (user) and SAP Crystal Reports 2020 licenses and other software and hardware for Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 2368/RS | 10/11/2025 | 10/12/2025 | APPLET PROJECTS & ENGINEERING PRIVATE LIMITED | 46.03 | 0 | 0 | 94
43 | SOUTH 24 PARGANAS |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Providing facilities to Push SMS Content and Bulk Push SMS Service, Supply of SAP Crystal Server 2020 (user) and SAP Crystal Reports 2020 licenses and other software and hardware for Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 2368/RS | 10/11/2025 | 10/12/2025 | APPLET PROJECTS & ENGINEERING PRIVATE LIMITED | 46.03 | 0 | 0 | 94
44 | UTTAR DINAJPUR |  | Resource | Procurement & Installation of various Digital equipments and Subscription to various services for IT Infrastructure of PHED, West Bengal | SM/19255 | Support-MIS | Providing facilities to Push SMS Content and Bulk Push SMS Service, Supply of SAP Crystal Server 2020 (user) and SAP Crystal Reports 2020 licenses and other software and hardware for Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 2368/RS | 10/11/2025 | 10/12/2025 | APPLET PROJECTS & ENGINEERING PRIVATE LIMITED | 46.03 | 0 | 0 | 94
Total | [13 empty] | 1183.05 | 0 | 0