## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeeping, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 12 months for PHED, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1042/RS | 15/05/2025 | 15/05/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 460.12 | 0 | 0 | 17
2 | BANKURA |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeeping, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 12 months for PHED, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1042/RS | 15/05/2025 | 15/05/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 460.12 | 0 | 0 | 17
3 | BIRBHUM |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeeping, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 12 months for PHED, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1042/RS | 15/05/2025 | 15/05/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 460.12 | 0 | 0 | 17
4 | COOCHBEHAR |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeeping, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 12 months for PHED, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1042/RS | 15/05/2025 | 15/05/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 460.12 | 0 | 0 | 17
5 | DAKSHIN DINAJPUR |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeeping, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 12 months for PHED, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1042/RS | 15/05/2025 | 15/05/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 460.12 | 0 | 0 | 17
6 | DARJEELING |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeeping, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 12 months for PHED, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1042/RS | 15/05/2025 | 15/05/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 460.12 | 0 | 0 | 17
7 | HOOGHLY |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeeping, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 12 months for PHED, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1042/RS | 15/05/2025 | 15/05/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 460.12 | 0 | 0 | 17
8 | HOWRAH |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeeping, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 12 months for PHED, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1042/RS | 15/05/2025 | 15/05/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 460.12 | 0 | 0 | 17
9 | JALPAIGURI |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeeping, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 12 months for PHED, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1042/RS | 15/05/2025 | 15/05/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 460.12 | 0 | 0 | 17
10 | JHARGRAM |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeeping, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 12 months for PHED, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1042/RS | 15/05/2025 | 15/05/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 460.12 | 0 | 0 | 17
11 | KALIMPONG |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeeping, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 12 months for PHED, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1042/RS | 15/05/2025 | 15/05/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 460.12 | 0 | 0 | 17
12 | MALDAH |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeeping, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 12 months for PHED, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1042/RS | 15/05/2025 | 15/05/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 460.12 | 0 | 0 | 17
13 | MURSHIDABAD |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeeping, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 12 months for PHED, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1042/RS | 15/05/2025 | 15/05/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 460.12 | 0 | 0 | 17
14 | NADIA |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeeping, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 12 months for PHED, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1042/RS | 15/05/2025 | 15/05/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 460.12 | 0 | 0 | 17
15 | NORTH 24 PARGANAS |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeeping, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 12 months for PHED, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1042/RS | 15/05/2025 | 15/05/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 460.12 | 0 | 0 | 17
16 | PASCHIM BARDHAMAN |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeeping, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 12 months for PHED, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1042/RS | 15/05/2025 | 15/05/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 460.12 | 0 | 0 | 17
17 | PASCHIM MEDINIPUR |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeeping, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 12 months for PHED, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1042/RS | 15/05/2025 | 15/05/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 460.12 | 0 | 0 | 17
18 | PURBA BARDHAMAN |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeeping, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 12 months for PHED, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1042/RS | 15/05/2025 | 15/05/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 460.12 | 0 | 0 | 17
19 | PURBA MEDINIPUR |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeeping, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 12 months for PHED, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1042/RS | 15/05/2025 | 15/05/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 460.12 | 0 | 0 | 17
20 | PURULIA |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeeping, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 12 months for PHED, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1042/RS | 15/05/2025 | 15/05/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 460.12 | 0 | 0 | 17
21 | SOUTH 24 PARGANAS |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeeping, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 12 months for PHED, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1042/RS | 15/05/2025 | 15/05/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 460.12 | 0 | 0 | 17
22 | UTTAR DINAJPUR |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeeping, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 12 months for PHED, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1042/RS | 15/05/2025 | 15/05/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 460.12 | 0 | 0 | 17
23 | ALIPURDUAR |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeep, upgradation & management of Analytical Dashboard of the State related to WQMSP under Jal Jeevan Mission for 12 months. | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 84/RS | 10/01/2025 | 10/01/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 28.51 | 0 | 0 | 83
24 | BANKURA |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeep, upgradation & management of Analytical Dashboard of the State related to WQMSP under Jal Jeevan Mission for 12 months. | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 84/RS | 10/01/2025 | 10/01/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 28.51 | 0 | 0 | 83
25 | BIRBHUM |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeep, upgradation & management of Analytical Dashboard of the State related to WQMSP under Jal Jeevan Mission for 12 months. | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 84/RS | 10/01/2025 | 10/01/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 28.51 | 0 | 0 | 83
26 | COOCHBEHAR |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeep, upgradation & management of Analytical Dashboard of the State related to WQMSP under Jal Jeevan Mission for 12 months. | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 84/RS | 10/01/2025 | 10/01/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 28.51 | 0 | 0 | 83
27 | DAKSHIN DINAJPUR |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeep, upgradation & management of Analytical Dashboard of the State related to WQMSP under Jal Jeevan Mission for 12 months. | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 84/RS | 10/01/2025 | 10/01/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 28.51 | 0 | 0 | 83
28 | DARJEELING |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeep, upgradation & management of Analytical Dashboard of the State related to WQMSP under Jal Jeevan Mission for 12 months. | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 84/RS | 10/01/2025 | 10/01/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 28.51 | 0 | 0 | 83
29 | HOOGHLY |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeep, upgradation & management of Analytical Dashboard of the State related to WQMSP under Jal Jeevan Mission for 12 months. | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 84/RS | 10/01/2025 | 10/01/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 28.51 | 0 | 0 | 83
30 | HOWRAH |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeep, upgradation & management of Analytical Dashboard of the State related to WQMSP under Jal Jeevan Mission for 12 months. | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 84/RS | 10/01/2025 | 10/01/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 28.51 | 0 | 0 | 83
31 | JALPAIGURI |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeep, upgradation & management of Analytical Dashboard of the State related to WQMSP under Jal Jeevan Mission for 12 months. | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 84/RS | 10/01/2025 | 10/01/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 28.51 | 0 | 0 | 83
32 | JHARGRAM |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeep, upgradation & management of Analytical Dashboard of the State related to WQMSP under Jal Jeevan Mission for 12 months. | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 84/RS | 10/01/2025 | 10/01/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 28.51 | 0 | 0 | 83
33 | KALIMPONG |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeep, upgradation & management of Analytical Dashboard of the State related to WQMSP under Jal Jeevan Mission for 12 months. | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 84/RS | 10/01/2025 | 10/01/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 28.51 | 0 | 0 | 83
34 | MALDAH |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeep, upgradation & management of Analytical Dashboard of the State related to WQMSP under Jal Jeevan Mission for 12 months. | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 84/RS | 10/01/2025 | 10/01/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 28.51 | 0 | 0 | 83
35 | MURSHIDABAD |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeep, upgradation & management of Analytical Dashboard of the State related to WQMSP under Jal Jeevan Mission for 12 months. | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 84/RS | 10/01/2025 | 10/01/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 28.51 | 0 | 0 | 83
36 | NADIA |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeep, upgradation & management of Analytical Dashboard of the State related to WQMSP under Jal Jeevan Mission for 12 months. | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 84/RS | 10/01/2025 | 10/01/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 28.51 | 0 | 0 | 83
37 | NORTH 24 PARGANAS |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeep, upgradation & management of Analytical Dashboard of the State related to WQMSP under Jal Jeevan Mission for 12 months. | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 84/RS | 10/01/2025 | 10/01/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 28.51 | 0 | 0 | 83
38 | PASCHIM BARDHAMAN |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeep, upgradation & management of Analytical Dashboard of the State related to WQMSP under Jal Jeevan Mission for 12 months. | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 84/RS | 10/01/2025 | 10/01/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 28.51 | 0 | 0 | 83
39 | PASCHIM MEDINIPUR |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeep, upgradation & management of Analytical Dashboard of the State related to WQMSP under Jal Jeevan Mission for 12 months. | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 84/RS | 10/01/2025 | 10/01/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 28.51 | 0 | 0 | 83
40 | PURBA BARDHAMAN |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeep, upgradation & management of Analytical Dashboard of the State related to WQMSP under Jal Jeevan Mission for 12 months. | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 84/RS | 10/01/2025 | 10/01/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 28.51 | 0 | 0 | 83
41 | PURBA MEDINIPUR |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeep, upgradation & management of Analytical Dashboard of the State related to WQMSP under Jal Jeevan Mission for 12 months. | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 84/RS | 10/01/2025 | 10/01/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 28.51 | 0 | 0 | 83
42 | PURULIA |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeep, upgradation & management of Analytical Dashboard of the State related to WQMSP under Jal Jeevan Mission for 12 months. | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 84/RS | 10/01/2025 | 10/01/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 28.51 | 0 | 0 | 83
43 | SOUTH 24 PARGANAS |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeep, upgradation & management of Analytical Dashboard of the State related to WQMSP under Jal Jeevan Mission for 12 months. | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 84/RS | 10/01/2025 | 10/01/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 28.51 | 0 | 0 | 83
44 | UTTAR DINAJPUR |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Regular upkeep, upgradation & management of Analytical Dashboard of the State related to WQMSP under Jal Jeevan Mission for 12 months. | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 84/RS | 10/01/2025 | 10/01/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 28.51 | 0 | 0 | 83
45 | ALIPURDUAR |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Development of PWSS Data Repository System for Pre & Post Monsoon and Creating an Indicator for assessment of Chemical & Bacteriological Contamination along with the Development of Special Drive Section: Health Care Survey, covering all the Laboratories in entire State of West Bengal | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 315/RS | 10/02/2025 | 11/05/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 44.09 | 0 | 0 | 99
46 | BANKURA |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Development of PWSS Data Repository System for Pre & Post Monsoon and Creating an Indicator for assessment of Chemical & Bacteriological Contamination along with the Development of Special Drive Section: Health Care Survey, covering all the Laboratories in entire State of West Bengal | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 315/RS | 10/02/2025 | 11/05/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 44.09 | 0 | 0 | 99
47 | BIRBHUM |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Development of PWSS Data Repository System for Pre & Post Monsoon and Creating an Indicator for assessment of Chemical & Bacteriological Contamination along with the Development of Special Drive Section: Health Care Survey, covering all the Laboratories in entire State of West Bengal | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 315/RS | 10/02/2025 | 11/05/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 44.09 | 0 | 0 | 99
48 | COOCHBEHAR |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Development of PWSS Data Repository System for Pre & Post Monsoon and Creating an Indicator for assessment of Chemical & Bacteriological Contamination along with the Development of Special Drive Section: Health Care Survey, covering all the Laboratories in entire State of West Bengal | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 315/RS | 10/02/2025 | 11/05/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 44.09 | 0 | 0 | 99
49 | DAKSHIN DINAJPUR |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Development of PWSS Data Repository System for Pre & Post Monsoon and Creating an Indicator for assessment of Chemical & Bacteriological Contamination along with the Development of Special Drive Section: Health Care Survey, covering all the Laboratories in entire State of West Bengal | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 315/RS | 10/02/2025 | 11/05/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 44.09 | 0 | 0 | 99
50 | DARJEELING |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Development of PWSS Data Repository System for Pre & Post Monsoon and Creating an Indicator for assessment of Chemical & Bacteriological Contamination along with the Development of Special Drive Section: Health Care Survey, covering all the Laboratories in entire State of West Bengal | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 315/RS | 10/02/2025 | 11/05/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 44.09 | 0 | 0 | 99
51 | HOOGHLY |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Development of PWSS Data Repository System for Pre & Post Monsoon and Creating an Indicator for assessment of Chemical & Bacteriological Contamination along with the Development of Special Drive Section: Health Care Survey, covering all the Laboratories in entire State of West Bengal | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 315/RS | 10/02/2025 | 11/05/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 44.09 | 0 | 0 | 99
52 | HOWRAH |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Development of PWSS Data Repository System for Pre & Post Monsoon and Creating an Indicator for assessment of Chemical & Bacteriological Contamination along with the Development of Special Drive Section: Health Care Survey, covering all the Laboratories in entire State of West Bengal | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 315/RS | 10/02/2025 | 11/05/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 44.09 | 0 | 0 | 99
53 | JALPAIGURI |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Development of PWSS Data Repository System for Pre & Post Monsoon and Creating an Indicator for assessment of Chemical & Bacteriological Contamination along with the Development of Special Drive Section: Health Care Survey, covering all the Laboratories in entire State of West Bengal | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 315/RS | 10/02/2025 | 11/05/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 44.09 | 0 | 0 | 99
54 | JHARGRAM |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Development of PWSS Data Repository System for Pre & Post Monsoon and Creating an Indicator for assessment of Chemical & Bacteriological Contamination along with the Development of Special Drive Section: Health Care Survey, covering all the Laboratories in entire State of West Bengal | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 315/RS | 10/02/2025 | 11/05/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 44.09 | 0 | 0 | 99
55 | KALIMPONG |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Development of PWSS Data Repository System for Pre & Post Monsoon and Creating an Indicator for assessment of Chemical & Bacteriological Contamination along with the Development of Special Drive Section: Health Care Survey, covering all the Laboratories in entire State of West Bengal | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 315/RS | 10/02/2025 | 11/05/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 44.09 | 0 | 0 | 99
56 | MALDAH |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Development of PWSS Data Repository System for Pre & Post Monsoon and Creating an Indicator for assessment of Chemical & Bacteriological Contamination along with the Development of Special Drive Section: Health Care Survey, covering all the Laboratories in entire State of West Bengal | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 315/RS | 10/02/2025 | 11/05/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 44.09 | 0 | 0 | 99
57 | MURSHIDABAD |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Development of PWSS Data Repository System for Pre & Post Monsoon and Creating an Indicator for assessment of Chemical & Bacteriological Contamination along with the Development of Special Drive Section: Health Care Survey, covering all the Laboratories in entire State of West Bengal | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 315/RS | 10/02/2025 | 11/05/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 44.09 | 0 | 0 | 99
58 | NADIA |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Development of PWSS Data Repository System for Pre & Post Monsoon and Creating an Indicator for assessment of Chemical & Bacteriological Contamination along with the Development of Special Drive Section: Health Care Survey, covering all the Laboratories in entire State of West Bengal | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 315/RS | 10/02/2025 | 11/05/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 44.09 | 0 | 0 | 99
59 | NORTH 24 PARGANAS |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Development of PWSS Data Repository System for Pre & Post Monsoon and Creating an Indicator for assessment of Chemical & Bacteriological Contamination along with the Development of Special Drive Section: Health Care Survey, covering all the Laboratories in entire State of West Bengal | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 315/RS | 10/02/2025 | 11/05/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 44.09 | 0 | 0 | 99
60 | PASCHIM BARDHAMAN |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Development of PWSS Data Repository System for Pre & Post Monsoon and Creating an Indicator for assessment of Chemical & Bacteriological Contamination along with the Development of Special Drive Section: Health Care Survey, covering all the Laboratories in entire State of West Bengal | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 315/RS | 10/02/2025 | 11/05/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 44.09 | 0 | 0 | 99
61 | PASCHIM MEDINIPUR |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Development of PWSS Data Repository System for Pre & Post Monsoon and Creating an Indicator for assessment of Chemical & Bacteriological Contamination along with the Development of Special Drive Section: Health Care Survey, covering all the Laboratories in entire State of West Bengal | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 315/RS | 10/02/2025 | 11/05/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 44.09 | 0 | 0 | 99
62 | PURBA BARDHAMAN |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Development of PWSS Data Repository System for Pre & Post Monsoon and Creating an Indicator for assessment of Chemical & Bacteriological Contamination along with the Development of Special Drive Section: Health Care Survey, covering all the Laboratories in entire State of West Bengal | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 315/RS | 10/02/2025 | 11/05/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 44.09 | 0 | 0 | 99
63 | PURBA MEDINIPUR |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Development of PWSS Data Repository System for Pre & Post Monsoon and Creating an Indicator for assessment of Chemical & Bacteriological Contamination along with the Development of Special Drive Section: Health Care Survey, covering all the Laboratories in entire State of West Bengal | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 315/RS | 10/02/2025 | 11/05/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 44.09 | 0 | 0 | 99
64 | PURULIA |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Development of PWSS Data Repository System for Pre & Post Monsoon and Creating an Indicator for assessment of Chemical & Bacteriological Contamination along with the Development of Special Drive Section: Health Care Survey, covering all the Laboratories in entire State of West Bengal | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 315/RS | 10/02/2025 | 11/05/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 44.09 | 0 | 0 | 99
65 | SOUTH 24 PARGANAS |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Development of PWSS Data Repository System for Pre & Post Monsoon and Creating an Indicator for assessment of Chemical & Bacteriological Contamination along with the Development of Special Drive Section: Health Care Survey, covering all the Laboratories in entire State of West Bengal | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 315/RS | 10/02/2025 | 11/05/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 44.09 | 0 | 0 | 99
66 | UTTAR DINAJPUR |  | Resource | Water Quality Monitoring, Programme Management & its implementation in the State related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19277 | Support-WQMSP | Development of PWSS Data Repository System for Pre & Post Monsoon and Creating an Indicator for assessment of Chemical & Bacteriological Contamination along with the Development of Special Drive Section: Health Care Survey, covering all the Laboratories in entire State of West Bengal | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 315/RS | 10/02/2025 | 11/05/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 44.09 | 0 | 0 | 99
Total | [13 empty] | 11719.75 | 0 | 0