## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Upgradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19298 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000227/2024-2025 | 181/RS | 24/01/2025 | 24/01/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 187.39 | 0 | 0 | 85
2 | BANKURA |  | Resource | Upgradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19298 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000227/2024-2025 | 181/RS | 24/01/2025 | 24/01/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 187.39 | 0 | 0 | 85
3 | BIRBHUM |  | Resource | Upgradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19298 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000227/2024-2025 | 181/RS | 24/01/2025 | 24/01/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 187.39 | 0 | 0 | 85
4 | COOCHBEHAR |  | Resource | Upgradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19298 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000227/2024-2025 | 181/RS | 24/01/2025 | 24/01/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 187.39 | 0 | 0 | 85
5 | DAKSHIN DINAJPUR |  | Resource | Upgradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19298 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000227/2024-2025 | 181/RS | 24/01/2025 | 24/01/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 187.39 | 0 | 0 | 85
6 | DARJEELING |  | Resource | Upgradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19298 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000227/2024-2025 | 181/RS | 24/01/2025 | 24/01/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 187.39 | 0 | 0 | 85
7 | HOOGHLY |  | Resource | Upgradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19298 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000227/2024-2025 | 181/RS | 24/01/2025 | 24/01/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 187.39 | 0 | 0 | 85
8 | HOWRAH |  | Resource | Upgradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19298 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000227/2024-2025 | 181/RS | 24/01/2025 | 24/01/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 187.39 | 0 | 0 | 85
9 | JALPAIGURI |  | Resource | Upgradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19298 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000227/2024-2025 | 181/RS | 24/01/2025 | 24/01/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 187.39 | 0 | 0 | 85
10 | JHARGRAM |  | Resource | Upgradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19298 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000227/2024-2025 | 181/RS | 24/01/2025 | 24/01/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 187.39 | 0 | 0 | 85
11 | KALIMPONG |  | Resource | Upgradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19298 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000227/2024-2025 | 181/RS | 24/01/2025 | 24/01/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 187.39 | 0 | 0 | 85
12 | MALDAH |  | Resource | Upgradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19298 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000227/2024-2025 | 181/RS | 24/01/2025 | 24/01/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 187.39 | 0 | 0 | 85
13 | MURSHIDABAD |  | Resource | Upgradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19298 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000227/2024-2025 | 181/RS | 24/01/2025 | 24/01/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 187.39 | 0 | 0 | 85
14 | NADIA |  | Resource | Upgradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19298 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000227/2024-2025 | 181/RS | 24/01/2025 | 24/01/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 187.39 | 0 | 0 | 85
15 | NORTH 24 PARGANAS |  | Resource | Upgradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19298 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000227/2024-2025 | 181/RS | 24/01/2025 | 24/01/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 187.39 | 0 | 0 | 85
16 | PASCHIM BARDHAMAN |  | Resource | Upgradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19298 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000227/2024-2025 | 181/RS | 24/01/2025 | 24/01/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 187.39 | 0 | 0 | 85
17 | PASCHIM MEDINIPUR |  | Resource | Upgradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19298 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000227/2024-2025 | 181/RS | 24/01/2025 | 24/01/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 187.39 | 0 | 0 | 85
18 | PURBA BARDHAMAN |  | Resource | Upgradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19298 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000227/2024-2025 | 181/RS | 24/01/2025 | 24/01/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 187.39 | 0 | 0 | 85
19 | PURBA MEDINIPUR |  | Resource | Upgradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19298 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000227/2024-2025 | 181/RS | 24/01/2025 | 24/01/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 187.39 | 0 | 0 | 85
20 | PURULIA |  | Resource | Upgradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19298 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000227/2024-2025 | 181/RS | 24/01/2025 | 24/01/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 187.39 | 0 | 0 | 85
21 | SOUTH 24 PARGANAS |  | Resource | Upgradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19298 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000227/2024-2025 | 181/RS | 24/01/2025 | 24/01/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 187.39 | 0 | 0 | 85
22 | UTTAR DINAJPUR |  | Resource | Upgradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19298 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000227/2024-2025 | 181/RS | 24/01/2025 | 24/01/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 187.39 | 0 | 0 | 85
Total | [13 empty] | 4122.54 | 0 | 0