## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
2 | BANKURA |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
3 | BIRBHUM |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
4 | COOCHBEHAR |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
6 | DARJEELING |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
7 | HOOGHLY |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
8 | HOWRAH |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
9 | JALPAIGURI |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
10 | JHARGRAM |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
11 | KALIMPONG |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
12 | MALDAH |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
13 | MURSHIDABAD |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
14 | NADIA |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
16 | PASCHIM BARDHAMAN |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
17 | PASCHIM MEDINIPUR |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
18 | PURBA BARDHAMAN |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
19 | PURBA MEDINIPUR |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
20 | PURULIA |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
21 | SOUTH 24 PARGANAS |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
22 | UTTAR DINAJPUR |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
23 | ALIPURDUAR |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
24 | BANKURA |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
25 | BIRBHUM |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
26 | COOCHBEHAR |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
27 | DAKSHIN DINAJPUR |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
28 | DARJEELING |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
29 | HOOGHLY |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
30 | HOWRAH |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
31 | JALPAIGURI |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
32 | JHARGRAM |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
33 | KALIMPONG |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
34 | MALDAH |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
35 | MURSHIDABAD |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
36 | NADIA |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
37 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
38 | PASCHIM BARDHAMAN |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
39 | PASCHIM MEDINIPUR |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
40 | PURBA BARDHAMAN |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
41 | PURBA MEDINIPUR |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
42 | PURULIA |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
43 | SOUTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
44 | UTTAR DINAJPUR |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
45 | ALIPURDUAR |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
46 | BANKURA |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
47 | BIRBHUM |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
48 | COOCHBEHAR |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
49 | DAKSHIN DINAJPUR |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
50 | DARJEELING |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
51 | HOOGHLY |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
52 | HOWRAH |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
53 | JALPAIGURI |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
54 | JHARGRAM |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
55 | KALIMPONG |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
56 | MALDAH |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
57 | MURSHIDABAD |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
58 | NADIA |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
59 | NORTH 24 PARGANAS |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
60 | PASCHIM BARDHAMAN |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
61 | PASCHIM MEDINIPUR |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
62 | PURBA BARDHAMAN |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
63 | PURBA MEDINIPUR |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
64 | PURULIA |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
65 | SOUTH 24 PARGANAS |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
66 | UTTAR DINAJPUR |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
67 | ALIPURDUAR |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
68 | BANKURA |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
69 | BIRBHUM |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
70 | COOCHBEHAR |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
71 | DAKSHIN DINAJPUR |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
72 | DARJEELING |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
73 | HOOGHLY |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
74 | HOWRAH |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
75 | JALPAIGURI |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
76 | JHARGRAM |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
77 | KALIMPONG |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
78 | MALDAH |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
79 | MURSHIDABAD |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
80 | NADIA |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
81 | NORTH 24 PARGANAS |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
82 | PASCHIM BARDHAMAN |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
83 | PASCHIM MEDINIPUR |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
84 | PURBA BARDHAMAN |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
85 | PURBA MEDINIPUR |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
86 | PURULIA |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
87 | SOUTH 24 PARGANAS |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
88 | UTTAR DINAJPUR |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
89 | ALIPURDUAR |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
90 | BANKURA |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
91 | BIRBHUM |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
92 | COOCHBEHAR |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
93 | DAKSHIN DINAJPUR |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
94 | DARJEELING |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
95 | HOOGHLY |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
96 | HOWRAH |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
97 | JALPAIGURI |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
98 | JHARGRAM |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
99 | KALIMPONG |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
100 | MALDAH |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
101 | MURSHIDABAD |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
102 | NADIA |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
103 | NORTH 24 PARGANAS |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
104 | PASCHIM BARDHAMAN |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
105 | PASCHIM MEDINIPUR |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
106 | PURBA BARDHAMAN |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
107 | PURBA MEDINIPUR |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
108 | PURULIA |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
109 | SOUTH 24 PARGANAS |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
110 | UTTAR DINAJPUR |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
111 | ALIPURDUAR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
112 | BANKURA |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
113 | BIRBHUM |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
114 | COOCHBEHAR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
115 | DAKSHIN DINAJPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
116 | DARJEELING |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
117 | HOOGHLY |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
118 | HOWRAH |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
119 | JALPAIGURI |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
120 | JHARGRAM |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
121 | KALIMPONG |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
122 | MALDAH |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
123 | MURSHIDABAD |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
124 | NADIA |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
125 | NORTH 24 PARGANAS |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
126 | PASCHIM BARDHAMAN |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
127 | PASCHIM MEDINIPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
128 | PURBA BARDHAMAN |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
129 | PURBA MEDINIPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
130 | PURULIA |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
131 | SOUTH 24 PARGANAS |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
132 | UTTAR DINAJPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
133 | ALIPURDUAR |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
134 | BANKURA |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
135 | BIRBHUM |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
136 | COOCHBEHAR |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
137 | DAKSHIN DINAJPUR |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
138 | DARJEELING |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
139 | HOOGHLY |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
140 | HOWRAH |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
141 | JALPAIGURI |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
142 | JHARGRAM |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
143 | KALIMPONG |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
144 | MALDAH |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
145 | MURSHIDABAD |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
146 | NADIA |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
147 | NORTH 24 PARGANAS |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
148 | PASCHIM BARDHAMAN |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
149 | PASCHIM MEDINIPUR |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
150 | PURBA BARDHAMAN |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
151 | PURBA MEDINIPUR |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
152 | PURULIA |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
153 | SOUTH 24 PARGANAS |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
154 | UTTAR DINAJPUR |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
155 | ALIPURDUAR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
156 | BANKURA |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
157 | BIRBHUM |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
158 | COOCHBEHAR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
159 | DAKSHIN DINAJPUR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
160 | DARJEELING |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
161 | HOOGHLY |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
162 | HOWRAH |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
163 | JALPAIGURI |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
164 | JHARGRAM |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
165 | KALIMPONG |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
166 | MALDAH |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
167 | MURSHIDABAD |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
168 | NADIA |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
169 | NORTH 24 PARGANAS |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
170 | PASCHIM BARDHAMAN |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
171 | PASCHIM MEDINIPUR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
172 | PURBA BARDHAMAN |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
173 | PURBA MEDINIPUR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
174 | PURULIA |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
175 | SOUTH 24 PARGANAS |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
176 | UTTAR DINAJPUR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
177 | ALIPURDUAR |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
178 | BANKURA |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
179 | BIRBHUM |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
180 | COOCHBEHAR |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
181 | DAKSHIN DINAJPUR |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
182 | DARJEELING |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
183 | HOOGHLY |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
184 | HOWRAH |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
185 | JALPAIGURI |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
186 | JHARGRAM |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
187 | KALIMPONG |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
188 | MALDAH |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
189 | MURSHIDABAD |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
190 | NADIA |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
191 | NORTH 24 PARGANAS |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
192 | PASCHIM BARDHAMAN |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
193 | PASCHIM MEDINIPUR |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
194 | PURBA BARDHAMAN |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
195 | PURBA MEDINIPUR |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
196 | PURULIA |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
197 | SOUTH 24 PARGANAS |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
198 | UTTAR DINAJPUR |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
199 | ALIPURDUAR |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
200 | BANKURA |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
201 | BIRBHUM |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
202 | COOCHBEHAR |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
203 | DAKSHIN DINAJPUR |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
204 | DARJEELING |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
205 | HOOGHLY |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
206 | HOWRAH |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
207 | JALPAIGURI |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
208 | JHARGRAM |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
209 | KALIMPONG |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
210 | MALDAH |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
211 | MURSHIDABAD |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
212 | NADIA |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
213 | NORTH 24 PARGANAS |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
214 | PASCHIM BARDHAMAN |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
215 | PASCHIM MEDINIPUR |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
216 | PURBA BARDHAMAN |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
217 | PURBA MEDINIPUR |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
218 | PURULIA |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
219 | SOUTH 24 PARGANAS |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
220 | UTTAR DINAJPUR |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
221 | ALIPURDUAR |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
222 | BANKURA |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
223 | BIRBHUM |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
224 | COOCHBEHAR |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
225 | DAKSHIN DINAJPUR |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
226 | DARJEELING |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
227 | HOOGHLY |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
228 | HOWRAH |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
229 | JALPAIGURI |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
230 | JHARGRAM |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
231 | KALIMPONG |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
232 | MALDAH |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
233 | MURSHIDABAD |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
234 | NADIA |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
235 | NORTH 24 PARGANAS |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
236 | PASCHIM BARDHAMAN |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
237 | PASCHIM MEDINIPUR |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
238 | PURBA BARDHAMAN |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
239 | PURBA MEDINIPUR |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
240 | PURULIA |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
241 | SOUTH 24 PARGANAS |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
242 | UTTAR DINAJPUR |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
243 | ALIPURDUAR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
244 | BANKURA |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
245 | BIRBHUM |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
246 | COOCHBEHAR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
247 | DAKSHIN DINAJPUR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
248 | DARJEELING |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
249 | HOOGHLY |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
250 | HOWRAH |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
251 | JALPAIGURI |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
252 | JHARGRAM |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
253 | KALIMPONG |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
254 | MALDAH |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
255 | MURSHIDABAD |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
256 | NADIA |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
257 | NORTH 24 PARGANAS |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
258 | PASCHIM BARDHAMAN |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
259 | PASCHIM MEDINIPUR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
260 | PURBA BARDHAMAN |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
261 | PURBA MEDINIPUR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
262 | PURULIA |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
263 | SOUTH 24 PARGANAS |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
264 | UTTAR DINAJPUR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
265 | ALIPURDUAR |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
266 | BANKURA |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
267 | BIRBHUM |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
268 | COOCHBEHAR |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
269 | DAKSHIN DINAJPUR |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
270 | DARJEELING |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
271 | HOOGHLY |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
272 | HOWRAH |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
273 | JALPAIGURI |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
274 | JHARGRAM |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
275 | KALIMPONG |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
276 | MALDAH |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
277 | MURSHIDABAD |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
278 | NADIA |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
279 | NORTH 24 PARGANAS |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
280 | PASCHIM BARDHAMAN |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
281 | PASCHIM MEDINIPUR |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
282 | PURBA BARDHAMAN |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
283 | PURBA MEDINIPUR |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
284 | PURULIA |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
285 | SOUTH 24 PARGANAS |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
286 | UTTAR DINAJPUR |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
287 | ALIPURDUAR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
288 | BANKURA |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
289 | BIRBHUM |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
290 | COOCHBEHAR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
291 | DAKSHIN DINAJPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
292 | DARJEELING |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
293 | HOOGHLY |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
294 | HOWRAH |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
295 | JALPAIGURI |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
296 | JHARGRAM |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
297 | KALIMPONG |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
298 | MALDAH |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
299 | MURSHIDABAD |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
300 | NADIA |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
301 | NORTH 24 PARGANAS |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
302 | PASCHIM BARDHAMAN |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
303 | PASCHIM MEDINIPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
304 | PURBA BARDHAMAN |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
305 | PURBA MEDINIPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
306 | PURULIA |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
307 | SOUTH 24 PARGANAS |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
308 | UTTAR DINAJPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
309 | ALIPURDUAR |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
310 | BANKURA |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
311 | BIRBHUM |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
312 | COOCHBEHAR |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
313 | DAKSHIN DINAJPUR |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
314 | DARJEELING |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
315 | HOOGHLY |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
316 | HOWRAH |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
317 | JALPAIGURI |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
318 | JHARGRAM |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
319 | KALIMPONG |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
320 | MALDAH |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
321 | MURSHIDABAD |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
322 | NADIA |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
323 | NORTH 24 PARGANAS |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
324 | PASCHIM BARDHAMAN |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
325 | PASCHIM MEDINIPUR |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
326 | PURBA BARDHAMAN |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
327 | PURBA MEDINIPUR |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
328 | PURULIA |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
329 | SOUTH 24 PARGANAS |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
330 | UTTAR DINAJPUR |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
331 | ALIPURDUAR |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
332 | BANKURA |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
333 | BIRBHUM |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
334 | COOCHBEHAR |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
335 | DAKSHIN DINAJPUR |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
336 | DARJEELING |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
337 | HOOGHLY |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
338 | HOWRAH |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
339 | JALPAIGURI |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
340 | JHARGRAM |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
341 | KALIMPONG |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
342 | MALDAH |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
343 | MURSHIDABAD |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
344 | NADIA |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
345 | NORTH 24 PARGANAS |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
346 | PASCHIM BARDHAMAN |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
347 | PASCHIM MEDINIPUR |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
348 | PURBA BARDHAMAN |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
349 | PURBA MEDINIPUR |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
350 | PURULIA |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
351 | SOUTH 24 PARGANAS |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
352 | UTTAR DINAJPUR |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
353 | ALIPURDUAR |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
354 | BANKURA |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
355 | BIRBHUM |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
356 | COOCHBEHAR |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
357 | DAKSHIN DINAJPUR |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
358 | DARJEELING |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
359 | HOOGHLY |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
360 | HOWRAH |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
361 | JALPAIGURI |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
362 | JHARGRAM |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
363 | KALIMPONG |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
364 | MALDAH |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
365 | MURSHIDABAD |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
366 | NADIA |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
367 | NORTH 24 PARGANAS |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
368 | PASCHIM BARDHAMAN |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
369 | PASCHIM MEDINIPUR |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
370 | PURBA BARDHAMAN |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
371 | PURBA MEDINIPUR |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
372 | PURULIA |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
373 | SOUTH 24 PARGANAS |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
374 | UTTAR DINAJPUR |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
375 | ALIPURDUAR |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
376 | BANKURA |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
377 | BIRBHUM |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
378 | COOCHBEHAR |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
379 | DAKSHIN DINAJPUR |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
380 | DARJEELING |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
381 | HOOGHLY |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
382 | HOWRAH |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
383 | JALPAIGURI |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
384 | JHARGRAM |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
385 | KALIMPONG |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
386 | MALDAH |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
387 | MURSHIDABAD |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
388 | NADIA |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
389 | NORTH 24 PARGANAS |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
390 | PASCHIM BARDHAMAN |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
391 | PASCHIM MEDINIPUR |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
392 | PURBA BARDHAMAN |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
393 | PURBA MEDINIPUR |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
394 | PURULIA |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
395 | SOUTH 24 PARGANAS |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
396 | UTTAR DINAJPUR |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
Total | [13 empty] | 5900.14 | 61.39 | 1.04