## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 23/02/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
2 | BANKURA |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 23/02/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
3 | BIRBHUM |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 23/02/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
4 | COOCHBEHAR |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 23/02/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 23/02/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
6 | DARJEELING |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 23/02/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
7 | HOOGHLY |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 23/02/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
8 | HOWRAH |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 23/02/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
9 | JALPAIGURI |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 23/02/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
10 | JHARGRAM |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 23/02/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
11 | KALIMPONG |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 23/02/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
12 | MALDAH |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 23/02/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
13 | MURSHIDABAD |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 23/02/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
14 | NADIA |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 23/02/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 23/02/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
16 | PASCHIM BARDHAMAN |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 23/02/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
17 | PASCHIM MEDINIPUR |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 23/02/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
18 | PURBA BARDHAMAN |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 23/02/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
19 | PURBA MEDINIPUR |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 23/02/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
20 | PURULIA |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 23/02/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
21 | SOUTH 24 PARGANAS |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 23/02/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
22 | UTTAR DINAJPUR |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 23/02/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
23 | ALIPURDUAR |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 01/09/2026 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 100
24 | BANKURA |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 01/09/2026 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 100
25 | BIRBHUM |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 01/09/2026 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 100
26 | COOCHBEHAR |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 01/09/2026 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 100
27 | DAKSHIN DINAJPUR |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 01/09/2026 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 100
28 | DARJEELING |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 01/09/2026 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 100
29 | HOOGHLY |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 01/09/2026 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 100
30 | HOWRAH |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 01/09/2026 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 100
31 | JALPAIGURI |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 01/09/2026 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 100
32 | JHARGRAM |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 01/09/2026 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 100
33 | KALIMPONG |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 01/09/2026 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 100
34 | MALDAH |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 01/09/2026 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 100
35 | MURSHIDABAD |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 01/09/2026 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 100
36 | NADIA |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 01/09/2026 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 100
37 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 01/09/2026 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 100
38 | PASCHIM BARDHAMAN |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 01/09/2026 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 100
39 | PASCHIM MEDINIPUR |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 01/09/2026 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 100
40 | PURBA BARDHAMAN |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 01/09/2026 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 100
41 | PURBA MEDINIPUR |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 01/09/2026 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 100
42 | PURULIA |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 01/09/2026 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 100
43 | SOUTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 01/09/2026 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 100
44 | UTTAR DINAJPUR |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 01/09/2026 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 100
45 | ALIPURDUAR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
46 | BANKURA |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
47 | BIRBHUM |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
48 | COOCHBEHAR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
49 | DAKSHIN DINAJPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
50 | DARJEELING |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
51 | HOOGHLY |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
52 | HOWRAH |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
53 | JALPAIGURI |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
54 | JHARGRAM |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
55 | KALIMPONG |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
56 | MALDAH |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
57 | MURSHIDABAD |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
58 | NADIA |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
59 | NORTH 24 PARGANAS |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
60 | PASCHIM BARDHAMAN |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
61 | PASCHIM MEDINIPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
62 | PURBA BARDHAMAN |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
63 | PURBA MEDINIPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
64 | PURULIA |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
65 | SOUTH 24 PARGANAS |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
66 | UTTAR DINAJPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 100
67 | ALIPURDUAR |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
68 | BANKURA |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
69 | BIRBHUM |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
70 | COOCHBEHAR |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
71 | DAKSHIN DINAJPUR |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
72 | DARJEELING |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
73 | HOOGHLY |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
74 | HOWRAH |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
75 | JALPAIGURI |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
76 | JHARGRAM |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
77 | KALIMPONG |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
78 | MALDAH |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
79 | MURSHIDABAD |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
80 | NADIA |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
81 | NORTH 24 PARGANAS |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
82 | PASCHIM BARDHAMAN |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
83 | PASCHIM MEDINIPUR |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
84 | PURBA BARDHAMAN |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
85 | PURBA MEDINIPUR |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
86 | PURULIA |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
87 | SOUTH 24 PARGANAS |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
88 | UTTAR DINAJPUR |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
89 | ALIPURDUAR |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/11/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
90 | BANKURA |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/11/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
91 | BIRBHUM |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/11/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
92 | COOCHBEHAR |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/11/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
93 | DAKSHIN DINAJPUR |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/11/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
94 | DARJEELING |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/11/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
95 | HOOGHLY |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/11/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
96 | HOWRAH |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/11/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
97 | JALPAIGURI |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/11/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
98 | JHARGRAM |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/11/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
99 | KALIMPONG |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/11/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
100 | MALDAH |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/11/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
101 | MURSHIDABAD |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/11/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
102 | NADIA |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/11/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
103 | NORTH 24 PARGANAS |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/11/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
104 | PASCHIM BARDHAMAN |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/11/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
105 | PASCHIM MEDINIPUR |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/11/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
106 | PURBA BARDHAMAN |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/11/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
107 | PURBA MEDINIPUR |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/11/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
108 | PURULIA |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/11/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
109 | SOUTH 24 PARGANAS |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/11/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
110 | UTTAR DINAJPUR |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/11/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
111 | ALIPURDUAR |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
112 | BANKURA |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
113 | BIRBHUM |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
114 | COOCHBEHAR |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
115 | DAKSHIN DINAJPUR |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
116 | DARJEELING |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
117 | HOOGHLY |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
118 | HOWRAH |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
119 | JALPAIGURI |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
120 | JHARGRAM |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
121 | KALIMPONG |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
122 | MALDAH |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
123 | MURSHIDABAD |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
124 | NADIA |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
125 | NORTH 24 PARGANAS |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
126 | PASCHIM BARDHAMAN |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
127 | PASCHIM MEDINIPUR |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
128 | PURBA BARDHAMAN |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
129 | PURBA MEDINIPUR |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
130 | PURULIA |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
131 | SOUTH 24 PARGANAS |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
132 | UTTAR DINAJPUR |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 15/12/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
133 | ALIPURDUAR |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Alipurduar district PHED laboratory building under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000447/2024-2025 | 5060/ALD | 18/02/2025 | 17/08/2025 | SATYABRATA BHATTACHERJEE | 20.55 | 0 | 0 | 0
134 | BANKURA |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Alipurduar district PHED laboratory building under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000447/2024-2025 | 5060/ALD | 18/02/2025 | 17/08/2025 | SATYABRATA BHATTACHERJEE | 20.55 | 0 | 0 | 0
135 | BIRBHUM |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Alipurduar district PHED laboratory building under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000447/2024-2025 | 5060/ALD | 18/02/2025 | 17/08/2025 | SATYABRATA BHATTACHERJEE | 20.55 | 0 | 0 | 0
136 | COOCHBEHAR |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Alipurduar district PHED laboratory building under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000447/2024-2025 | 5060/ALD | 18/02/2025 | 17/08/2025 | SATYABRATA BHATTACHERJEE | 20.55 | 0 | 0 | 0
137 | DAKSHIN DINAJPUR |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Alipurduar district PHED laboratory building under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000447/2024-2025 | 5060/ALD | 18/02/2025 | 17/08/2025 | SATYABRATA BHATTACHERJEE | 20.55 | 0 | 0 | 0
138 | DARJEELING |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Alipurduar district PHED laboratory building under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000447/2024-2025 | 5060/ALD | 18/02/2025 | 17/08/2025 | SATYABRATA BHATTACHERJEE | 20.55 | 0 | 0 | 0
139 | HOOGHLY |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Alipurduar district PHED laboratory building under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000447/2024-2025 | 5060/ALD | 18/02/2025 | 17/08/2025 | SATYABRATA BHATTACHERJEE | 20.55 | 0 | 0 | 0
140 | HOWRAH |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Alipurduar district PHED laboratory building under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000447/2024-2025 | 5060/ALD | 18/02/2025 | 17/08/2025 | SATYABRATA BHATTACHERJEE | 20.55 | 0 | 0 | 0
141 | JALPAIGURI |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Alipurduar district PHED laboratory building under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000447/2024-2025 | 5060/ALD | 18/02/2025 | 17/08/2025 | SATYABRATA BHATTACHERJEE | 20.55 | 0 | 0 | 0
142 | JHARGRAM |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Alipurduar district PHED laboratory building under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000447/2024-2025 | 5060/ALD | 18/02/2025 | 17/08/2025 | SATYABRATA BHATTACHERJEE | 20.55 | 0 | 0 | 0
143 | KALIMPONG |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Alipurduar district PHED laboratory building under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000447/2024-2025 | 5060/ALD | 18/02/2025 | 17/08/2025 | SATYABRATA BHATTACHERJEE | 20.55 | 0 | 0 | 0
144 | MALDAH |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Alipurduar district PHED laboratory building under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000447/2024-2025 | 5060/ALD | 18/02/2025 | 17/08/2025 | SATYABRATA BHATTACHERJEE | 20.55 | 0 | 0 | 0
145 | MURSHIDABAD |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Alipurduar district PHED laboratory building under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000447/2024-2025 | 5060/ALD | 18/02/2025 | 17/08/2025 | SATYABRATA BHATTACHERJEE | 20.55 | 0 | 0 | 0
146 | NADIA |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Alipurduar district PHED laboratory building under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000447/2024-2025 | 5060/ALD | 18/02/2025 | 17/08/2025 | SATYABRATA BHATTACHERJEE | 20.55 | 0 | 0 | 0
147 | NORTH 24 PARGANAS |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Alipurduar district PHED laboratory building under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000447/2024-2025 | 5060/ALD | 18/02/2025 | 17/08/2025 | SATYABRATA BHATTACHERJEE | 20.55 | 0 | 0 | 0
148 | PASCHIM BARDHAMAN |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Alipurduar district PHED laboratory building under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000447/2024-2025 | 5060/ALD | 18/02/2025 | 17/08/2025 | SATYABRATA BHATTACHERJEE | 20.55 | 0 | 0 | 0
149 | PASCHIM MEDINIPUR |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Alipurduar district PHED laboratory building under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000447/2024-2025 | 5060/ALD | 18/02/2025 | 17/08/2025 | SATYABRATA BHATTACHERJEE | 20.55 | 0 | 0 | 0
150 | PURBA BARDHAMAN |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Alipurduar district PHED laboratory building under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000447/2024-2025 | 5060/ALD | 18/02/2025 | 17/08/2025 | SATYABRATA BHATTACHERJEE | 20.55 | 0 | 0 | 0
151 | PURBA MEDINIPUR |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Alipurduar district PHED laboratory building under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000447/2024-2025 | 5060/ALD | 18/02/2025 | 17/08/2025 | SATYABRATA BHATTACHERJEE | 20.55 | 0 | 0 | 0
152 | PURULIA |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Alipurduar district PHED laboratory building under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000447/2024-2025 | 5060/ALD | 18/02/2025 | 17/08/2025 | SATYABRATA BHATTACHERJEE | 20.55 | 0 | 0 | 0
153 | SOUTH 24 PARGANAS |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Alipurduar district PHED laboratory building under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000447/2024-2025 | 5060/ALD | 18/02/2025 | 17/08/2025 | SATYABRATA BHATTACHERJEE | 20.55 | 0 | 0 | 0
154 | UTTAR DINAJPUR |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Alipurduar district PHED laboratory building under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000447/2024-2025 | 5060/ALD | 18/02/2025 | 17/08/2025 | SATYABRATA BHATTACHERJEE | 20.55 | 0 | 0 | 0
155 | ALIPURDUAR |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
156 | BANKURA |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
157 | BIRBHUM |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
158 | COOCHBEHAR |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
159 | DAKSHIN DINAJPUR |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
160 | DARJEELING |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
161 | HOOGHLY |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
162 | HOWRAH |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
163 | JALPAIGURI |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
164 | JHARGRAM |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
165 | KALIMPONG |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
166 | MALDAH |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
167 | MURSHIDABAD |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
168 | NADIA |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
169 | NORTH 24 PARGANAS |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
170 | PASCHIM BARDHAMAN |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
171 | PASCHIM MEDINIPUR |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
172 | PURBA BARDHAMAN |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
173 | PURBA MEDINIPUR |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
174 | PURULIA |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
175 | SOUTH 24 PARGANAS |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
176 | UTTAR DINAJPUR |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
177 | ALIPURDUAR |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
178 | BANKURA |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
179 | BIRBHUM |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
180 | COOCHBEHAR |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
181 | DAKSHIN DINAJPUR |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
182 | DARJEELING |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
183 | HOOGHLY |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
184 | HOWRAH |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
185 | JALPAIGURI |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
186 | JHARGRAM |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
187 | KALIMPONG |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
188 | MALDAH |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
189 | MURSHIDABAD |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
190 | NADIA |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
191 | NORTH 24 PARGANAS |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
192 | PASCHIM BARDHAMAN |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
193 | PASCHIM MEDINIPUR |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
194 | PURBA BARDHAMAN |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
195 | PURBA MEDINIPUR |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
196 | PURULIA |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
197 | SOUTH 24 PARGANAS |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
198 | UTTAR DINAJPUR |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 23/07/2026 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 25
199 | ALIPURDUAR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
200 | BANKURA |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
201 | BIRBHUM |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
202 | COOCHBEHAR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
203 | DAKSHIN DINAJPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
204 | DARJEELING |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
205 | HOOGHLY |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
206 | HOWRAH |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
207 | JALPAIGURI |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
208 | JHARGRAM |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
209 | KALIMPONG |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
210 | MALDAH |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
211 | MURSHIDABAD |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
212 | NADIA |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
213 | NORTH 24 PARGANAS |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
214 | PASCHIM BARDHAMAN |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
215 | PASCHIM MEDINIPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
216 | PURBA BARDHAMAN |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
217 | PURBA MEDINIPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
218 | PURULIA |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
219 | SOUTH 24 PARGANAS |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
220 | UTTAR DINAJPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
221 | ALIPURDUAR |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
222 | BANKURA |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
223 | BIRBHUM |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
224 | COOCHBEHAR |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
225 | DAKSHIN DINAJPUR |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
226 | DARJEELING |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
227 | HOOGHLY |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
228 | HOWRAH |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
229 | JALPAIGURI |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
230 | JHARGRAM |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
231 | KALIMPONG |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
232 | MALDAH |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
233 | MURSHIDABAD |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
234 | NADIA |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
235 | NORTH 24 PARGANAS |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
236 | PASCHIM BARDHAMAN |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
237 | PASCHIM MEDINIPUR |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
238 | PURBA BARDHAMAN |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
239 | PURBA MEDINIPUR |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
240 | PURULIA |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
241 | SOUTH 24 PARGANAS |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
242 | UTTAR DINAJPUR |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
243 | ALIPURDUAR |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
244 | BANKURA |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
245 | BIRBHUM |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
246 | COOCHBEHAR |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
247 | DAKSHIN DINAJPUR |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
248 | DARJEELING |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
249 | HOOGHLY |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
250 | HOWRAH |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
251 | JALPAIGURI |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
252 | JHARGRAM |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
253 | KALIMPONG |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
254 | MALDAH |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
255 | MURSHIDABAD |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
256 | NADIA |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
257 | NORTH 24 PARGANAS |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
258 | PASCHIM BARDHAMAN |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
259 | PASCHIM MEDINIPUR |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
260 | PURBA BARDHAMAN |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
261 | PURBA MEDINIPUR |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
262 | PURULIA |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
263 | SOUTH 24 PARGANAS |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
264 | UTTAR DINAJPUR |  | Coochbehar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | EXECUTION OF DIFFERENT WORKS RELATED TO MICROBIOLOGICAL LAB UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000702/2024-2025 | 224/CD | 12/02/2025 | 17/01/2026 | BIJOY ROY | 15.76 | 0 | 0 | 80
265 | ALIPURDUAR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 100
266 | BANKURA |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 100
267 | BIRBHUM |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 100
268 | COOCHBEHAR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 100
269 | DAKSHIN DINAJPUR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 100
270 | DARJEELING |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 100
271 | HOOGHLY |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 100
272 | HOWRAH |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 100
273 | JALPAIGURI |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 100
274 | JHARGRAM |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 100
275 | KALIMPONG |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 100
276 | MALDAH |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 100
277 | MURSHIDABAD |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 100
278 | NADIA |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 100
279 | NORTH 24 PARGANAS |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 100
280 | PASCHIM BARDHAMAN |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 100
281 | PASCHIM MEDINIPUR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 100
282 | PURBA BARDHAMAN |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 100
283 | PURBA MEDINIPUR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 100
284 | PURULIA |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 100
285 | SOUTH 24 PARGANAS |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 100
286 | UTTAR DINAJPUR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 100
287 | ALIPURDUAR |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
288 | BANKURA |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
289 | BIRBHUM |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
290 | COOCHBEHAR |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
291 | DAKSHIN DINAJPUR |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
292 | DARJEELING |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
293 | HOOGHLY |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
294 | HOWRAH |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
295 | JALPAIGURI |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
296 | JHARGRAM |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
297 | KALIMPONG |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
298 | MALDAH |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
299 | MURSHIDABAD |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
300 | NADIA |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
301 | NORTH 24 PARGANAS |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
302 | PASCHIM BARDHAMAN |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
303 | PASCHIM MEDINIPUR |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
304 | PURBA BARDHAMAN |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
305 | PURBA MEDINIPUR |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
306 | PURULIA |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
307 | SOUTH 24 PARGANAS |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
308 | UTTAR DINAJPUR |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
309 | ALIPURDUAR |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
310 | BANKURA |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
311 | BIRBHUM |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
312 | COOCHBEHAR |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
313 | DAKSHIN DINAJPUR |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
314 | DARJEELING |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
315 | HOOGHLY |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
316 | HOWRAH |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
317 | JALPAIGURI |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
318 | JHARGRAM |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
319 | KALIMPONG |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
320 | MALDAH |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
321 | MURSHIDABAD |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
322 | NADIA |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
323 | NORTH 24 PARGANAS |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
324 | PASCHIM BARDHAMAN |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
325 | PASCHIM MEDINIPUR |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
326 | PURBA BARDHAMAN |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
327 | PURBA MEDINIPUR |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
328 | PURULIA |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
329 | SOUTH 24 PARGANAS |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
330 | UTTAR DINAJPUR |  | Malda Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Bacteriological laboratory and renovation of water sample collection room, office room, toilet and other ancillary work as per NABL guideline at RWS campus under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000809/2024-2025 | 448/MD | 06/02/2025 | 21/06/2025 | BINA CONSTRUCTION | 23.03 | 0 | 0 | 69
331 | ALIPURDUAR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
332 | BANKURA |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
333 | BIRBHUM |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
334 | COOCHBEHAR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
335 | DAKSHIN DINAJPUR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
336 | DARJEELING |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
337 | HOOGHLY |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
338 | HOWRAH |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
339 | JALPAIGURI |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
340 | JHARGRAM |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
341 | KALIMPONG |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
342 | MALDAH |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
343 | MURSHIDABAD |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
344 | NADIA |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
345 | NORTH 24 PARGANAS |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
346 | PASCHIM BARDHAMAN |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
347 | PASCHIM MEDINIPUR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
348 | PURBA BARDHAMAN |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
349 | PURBA MEDINIPUR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
350 | PURULIA |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
351 | SOUTH 24 PARGANAS |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
352 | UTTAR DINAJPUR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter under Burdwan Division,PHE Dte. (Fund-JJM) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001197/2024-2025 | 41/RWS | 12/02/2025 | 14/03/2025 | JAYANTA CHAKRABORTY | 4.25 | 0 | 0 | 100
353 | ALIPURDUAR |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
354 | BANKURA |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
355 | BIRBHUM |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
356 | COOCHBEHAR |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
357 | DAKSHIN DINAJPUR |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
358 | DARJEELING |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
359 | HOOGHLY |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
360 | HOWRAH |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
361 | JALPAIGURI |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
362 | JHARGRAM |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
363 | KALIMPONG |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
364 | MALDAH |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
365 | MURSHIDABAD |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
366 | NADIA |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
367 | NORTH 24 PARGANAS |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
368 | PASCHIM BARDHAMAN |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
369 | PASCHIM MEDINIPUR |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
370 | PURBA BARDHAMAN |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
371 | PURBA MEDINIPUR |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
372 | PURULIA |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
373 | SOUTH 24 PARGANAS |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
374 | UTTAR DINAJPUR |  | Nadia Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Krishnanagar District Water Testing Laboratory under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000798/2024-2025 | 221/KlySD-I | 05/02/2025 | 07/03/2025 | DEBASHISH DEY | 10.54 | 2.79 | 26.48 | 100
375 | ALIPURDUAR |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
376 | BANKURA |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
377 | BIRBHUM |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
378 | COOCHBEHAR |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
379 | DAKSHIN DINAJPUR |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
380 | DARJEELING |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
381 | HOOGHLY |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
382 | HOWRAH |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
383 | JALPAIGURI |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
384 | JHARGRAM |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
385 | KALIMPONG |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
386 | MALDAH |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
387 | MURSHIDABAD |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
388 | NADIA |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
389 | NORTH 24 PARGANAS |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
390 | PASCHIM BARDHAMAN |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
391 | PASCHIM MEDINIPUR |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
392 | PURBA BARDHAMAN |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
393 | PURBA MEDINIPUR |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
394 | PURULIA |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
395 | SOUTH 24 PARGANAS |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
396 | UTTAR DINAJPUR |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 25/06/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 100
397 | ALIPURDUAR |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
398 | BANKURA |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
399 | BIRBHUM |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
400 | COOCHBEHAR |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
401 | DAKSHIN DINAJPUR |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
402 | DARJEELING |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
403 | HOOGHLY |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
404 | HOWRAH |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
405 | JALPAIGURI |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
406 | JHARGRAM |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
407 | KALIMPONG |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
408 | MALDAH |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
409 | MURSHIDABAD |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
410 | NADIA |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
411 | NORTH 24 PARGANAS |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
412 | PASCHIM BARDHAMAN |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
413 | PASCHIM MEDINIPUR |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
414 | PURBA BARDHAMAN |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
415 | PURBA MEDINIPUR |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
416 | PURULIA |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
417 | SOUTH 24 PARGANAS |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
418 | UTTAR DINAJPUR |  | Alipurduar Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Shifting of LT pole for continuation of the district laboratory extension work and ensure the safety for worker under Alipurduar Division, PHE Dte. |  |  | BILL/00047/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 1.46 | 0 | 0 | 0
Total | [13 empty] | 6352.27 | 61.39 | 0.97