## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
2 | BANKURA |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
3 | BIRBHUM |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
4 | COOCHBEHAR |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
6 | DARJEELING |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
7 | HOOGHLY |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
8 | HOWRAH |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
9 | JALPAIGURI |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
10 | JHARGRAM |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
11 | KALIMPONG |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
12 | MALDAH |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
13 | MURSHIDABAD |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
14 | NADIA |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
16 | PASCHIM BARDHAMAN |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
17 | PASCHIM MEDINIPUR |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
18 | PURBA BARDHAMAN |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
19 | PURBA MEDINIPUR |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
20 | PURULIA |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
21 | SOUTH 24 PARGANAS |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
22 | UTTAR DINAJPUR |  | Alipore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | proposed Microbiological Room for NABL accrediation of South 24 Parganas District Water Testing Laboratory in the Dist.of South 24 Parganas under Alipore Division,P.H.E. Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000857/2024-2025 | 634/RWS | 25/11/2024 | 09/01/2025 | G.G. PROJECT | 3.87 | 0 | 0 | 0
23 | ALIPURDUAR |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
24 | BANKURA |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
25 | BIRBHUM |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
26 | COOCHBEHAR |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
27 | DAKSHIN DINAJPUR |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
28 | DARJEELING |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
29 | HOOGHLY |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
30 | HOWRAH |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
31 | JALPAIGURI |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
32 | JHARGRAM |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
33 | KALIMPONG |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
34 | MALDAH |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
35 | MURSHIDABAD |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
36 | NADIA |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
37 | NORTH 24 PARGANAS |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
38 | PASCHIM BARDHAMAN |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
39 | PASCHIM MEDINIPUR |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
40 | PURBA BARDHAMAN |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
41 | PURBA MEDINIPUR |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
42 | PURULIA |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
43 | SOUTH 24 PARGANAS |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
44 | UTTAR DINAJPUR |  | Howrah Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Addition and alteration of Bacteriological Laboratory as per scope of NABL at Domjur District Laboratory under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000367/2024-2025 | 685/HD | 29/01/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 7.43 | 0 | 0 | 100
45 | ALIPURDUAR |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
46 | BANKURA |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
47 | BIRBHUM |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
48 | COOCHBEHAR |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
49 | DAKSHIN DINAJPUR |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
50 | DARJEELING |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
51 | HOOGHLY |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
52 | HOWRAH |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
53 | JALPAIGURI |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
54 | JHARGRAM |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
55 | KALIMPONG |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
56 | MALDAH |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
57 | MURSHIDABAD |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
58 | NADIA |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
59 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
60 | PASCHIM BARDHAMAN |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
61 | PASCHIM MEDINIPUR |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
62 | PURBA BARDHAMAN |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
63 | PURBA MEDINIPUR |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
64 | PURULIA |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
65 | SOUTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
66 | UTTAR DINAJPUR |  | North 24 Pgs W/S Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of partition wall for accommodation of Bacteriological Laboratory as per specification of NABL at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000120/2024-2025 | 48/NWSD-I | 09/01/2025 | 06/10/2025 | SCIENTIFIC VENTURES | 13.78 | 0 | 0 | 0
67 | ALIPURDUAR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 80
68 | BANKURA |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 80
69 | BIRBHUM |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 80
70 | COOCHBEHAR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 80
71 | DAKSHIN DINAJPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 80
72 | DARJEELING |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 80
73 | HOOGHLY |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 80
74 | HOWRAH |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 80
75 | JALPAIGURI |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 80
76 | JHARGRAM |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 80
77 | KALIMPONG |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 80
78 | MALDAH |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 80
79 | MURSHIDABAD |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 80
80 | NADIA |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 80
81 | NORTH 24 PARGANAS |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 80
82 | PASCHIM BARDHAMAN |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 80
83 | PASCHIM MEDINIPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 80
84 | PURBA BARDHAMAN |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 80
85 | PURBA MEDINIPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 80
86 | PURULIA |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 80
87 | SOUTH 24 PARGANAS |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 80
88 | UTTAR DINAJPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural Development of Bacteriological Laboratory with extension of existing Lab of Jalpaiguri District in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E Directorate. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 610/JD | 26/03/2025 | 01/11/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 12.31 | 0 | 0 | 80
89 | ALIPURDUAR |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 07/04/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 0
90 | BANKURA |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 07/04/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 0
91 | BIRBHUM |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 07/04/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 0
92 | COOCHBEHAR |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 07/04/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 0
93 | DAKSHIN DINAJPUR |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 07/04/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 0
94 | DARJEELING |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 07/04/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 0
95 | HOOGHLY |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 07/04/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 0
96 | HOWRAH |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 07/04/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 0
97 | JALPAIGURI |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 07/04/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 0
98 | JHARGRAM |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 07/04/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 0
99 | KALIMPONG |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 07/04/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 0
100 | MALDAH |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 07/04/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 0
101 | MURSHIDABAD |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 07/04/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 0
102 | NADIA |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 07/04/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 0
103 | NORTH 24 PARGANAS |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 07/04/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 0
104 | PASCHIM BARDHAMAN |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 07/04/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 0
105 | PASCHIM MEDINIPUR |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 07/04/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 0
106 | PURBA BARDHAMAN |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 07/04/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 0
107 | PURBA MEDINIPUR |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 07/04/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 0
108 | PURULIA |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 07/04/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 0
109 | SOUTH 24 PARGANAS |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 07/04/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 0
110 | UTTAR DINAJPUR |  | Nadia Arsenic Division I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural developments and strengthening of Kalyani State Referral Laboratory for addition of microbiological water quality parameters under existing scope of accreditation certified by NABL, under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000192/2024-2025 | 2285/NAD-I | 07/01/2025 | 07/04/2025 | CHINMOY BISWAS | 24.27 | 0 | 0 | 0
111 | ALIPURDUAR |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
112 | BANKURA |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
113 | BIRBHUM |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
114 | COOCHBEHAR |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
115 | DAKSHIN DINAJPUR |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
116 | DARJEELING |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
117 | HOOGHLY |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
118 | HOWRAH |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
119 | JALPAIGURI |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
120 | JHARGRAM |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
121 | KALIMPONG |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
122 | MALDAH |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
123 | MURSHIDABAD |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
124 | NADIA |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
125 | NORTH 24 PARGANAS |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
126 | PASCHIM BARDHAMAN |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
127 | PASCHIM MEDINIPUR |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
128 | PURBA BARDHAMAN |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
129 | PURBA MEDINIPUR |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
130 | PURULIA |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
131 | SOUTH 24 PARGANAS |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
132 | UTTAR DINAJPUR |  | Hooghly Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructural modifications of Hooghly District Laboratory to accommodate Separate Bacteriological Lab required for NABL Accreditation under Hooghly District. |  |  | ORD/002161/2024-2025 | 504/HUG | 25/02/2025 | 25/06/2025 | PRADIP KUMAR ADHYA (PARTNERSHIP) | 24.81 | 0 | 0 | 0
133 | ALIPURDUAR |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
134 | BANKURA |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
135 | BIRBHUM |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
136 | COOCHBEHAR |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
137 | DAKSHIN DINAJPUR |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
138 | DARJEELING |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
139 | HOOGHLY |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
140 | HOWRAH |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
141 | JALPAIGURI |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
142 | JHARGRAM |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
143 | KALIMPONG |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
144 | MALDAH |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
145 | MURSHIDABAD |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
146 | NADIA |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
147 | NORTH 24 PARGANAS |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
148 | PASCHIM BARDHAMAN |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
149 | PASCHIM MEDINIPUR |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
150 | PURBA BARDHAMAN |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
151 | PURBA MEDINIPUR |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
152 | PURULIA |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
153 | SOUTH 24 PARGANAS |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
154 | UTTAR DINAJPUR |  | Murshidabad Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Extension of Building at 2nd floor for accommodation of Bacteriological Testing at Murshidabad District Water Testing Laboratory under Murshidabad Division , P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000008/2025-2026 | 890/MURD | 22/04/2025 | 01/04/2026 | DAS CONSTRACTION (MUNNA DAS) | 36 | 0 | 0 | 0
155 | ALIPURDUAR |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 18/07/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
156 | BANKURA |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 18/07/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
157 | BIRBHUM |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 18/07/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
158 | COOCHBEHAR |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 18/07/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
159 | DAKSHIN DINAJPUR |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 18/07/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
160 | DARJEELING |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 18/07/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
161 | HOOGHLY |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 18/07/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
162 | HOWRAH |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 18/07/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
163 | JALPAIGURI |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 18/07/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
164 | JHARGRAM |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 18/07/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
165 | KALIMPONG |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 18/07/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
166 | MALDAH |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 18/07/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
167 | MURSHIDABAD |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 18/07/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
168 | NADIA |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 18/07/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
169 | NORTH 24 PARGANAS |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 18/07/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
170 | PASCHIM BARDHAMAN |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 18/07/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
171 | PASCHIM MEDINIPUR |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 18/07/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
172 | PURBA BARDHAMAN |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 18/07/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
173 | PURBA MEDINIPUR |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 18/07/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
174 | PURULIA |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 18/07/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
175 | SOUTH 24 PARGANAS |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 18/07/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
176 | UTTAR DINAJPUR |  | Midnapore Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Construction of Additional Laboratory Room along with Electrical work for Bacteriological testing of water samples at first floor attached to Midnapore District Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000484/2024-2025 | 512/MD | 18/02/2025 | 18/07/2025 | UTTAM KUMAR BHUNIA | 24.04 | 0 | 0 | 80
177 | ALIPURDUAR |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
178 | BANKURA |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
179 | BIRBHUM |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
180 | COOCHBEHAR |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
181 | DAKSHIN DINAJPUR |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
182 | DARJEELING |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
183 | HOOGHLY |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
184 | HOWRAH |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
185 | JALPAIGURI |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
186 | JHARGRAM |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
187 | KALIMPONG |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
188 | MALDAH |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
189 | MURSHIDABAD |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
190 | NADIA |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
191 | NORTH 24 PARGANAS |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
192 | PASCHIM BARDHAMAN |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
193 | PASCHIM MEDINIPUR |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
194 | PURBA BARDHAMAN |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
195 | PURBA MEDINIPUR |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
196 | PURULIA |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
197 | SOUTH 24 PARGANAS |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
198 | UTTAR DINAJPUR |  | Bankura Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Infrastructual Development of District Laboratory for addition of Microbiological Water Quality Parameter Under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001787/2024-2025 | 498/BQA | 25/02/2025 | 24/08/2025 | GOUR GORAI | 19.99 | 0 | 0 | 90
199 | ALIPURDUAR |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 26/10/2025 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 0
200 | BANKURA |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 26/10/2025 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 0
201 | BIRBHUM |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 26/10/2025 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 0
202 | COOCHBEHAR |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 26/10/2025 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 0
203 | DAKSHIN DINAJPUR |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 26/10/2025 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 0
204 | DARJEELING |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 26/10/2025 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 0
205 | HOOGHLY |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 26/10/2025 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 0
206 | HOWRAH |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 26/10/2025 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 0
207 | JALPAIGURI |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 26/10/2025 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 0
208 | JHARGRAM |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 26/10/2025 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 0
209 | KALIMPONG |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 26/10/2025 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 0
210 | MALDAH |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 26/10/2025 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 0
211 | MURSHIDABAD |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 26/10/2025 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 0
212 | NADIA |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 26/10/2025 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 0
213 | NORTH 24 PARGANAS |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 26/10/2025 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 0
214 | PASCHIM BARDHAMAN |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 26/10/2025 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 0
215 | PASCHIM MEDINIPUR |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 26/10/2025 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 0
216 | PURBA BARDHAMAN |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 26/10/2025 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 0
217 | PURBA MEDINIPUR |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 26/10/2025 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 0
218 | PURULIA |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 26/10/2025 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 0
219 | SOUTH 24 PARGANAS |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 26/10/2025 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 0
220 | UTTAR DINAJPUR |  | Balurghat Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Renovation & infrastructural development of Dakshin Dinajpur District Water Testing Laboratory for NABL Accreditation of Bacteriological Parameters, Under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000242/2024-2025 | 176/BD | 29/01/2025 | 26/10/2025 | S.C. ROY & OTHERS | 9.73 | 0 | 0 | 0
221 | ALIPURDUAR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
222 | BANKURA |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
223 | BIRBHUM |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
224 | COOCHBEHAR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
225 | DAKSHIN DINAJPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
226 | DARJEELING |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
227 | HOOGHLY |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
228 | HOWRAH |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
229 | JALPAIGURI |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
230 | JHARGRAM |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
231 | KALIMPONG |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
232 | MALDAH |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
233 | MURSHIDABAD |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
234 | NADIA |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
235 | NORTH 24 PARGANAS |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
236 | PASCHIM BARDHAMAN |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
237 | PASCHIM MEDINIPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
238 | PURBA BARDHAMAN |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
239 | PURBA MEDINIPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
240 | PURULIA |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
241 | SOUTH 24 PARGANAS |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
242 | UTTAR DINAJPUR |  | Jalpaiguri Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Electrical installation work of Jalpaiguri District Water Testing Lab on First Floor of Main Office Building, Jalpaiguri Division P.H.E. Dte. at Club Road (Near PD Women's college), Jalpaiguri. | Assistant Engineer |  | ORD/000145/2025-2026 | 1657/JD | 21/07/2025 | 20/08/2025 | M/S. BHOWMIK & CO. | 10.13 | 0 | 0 | 0
243 | ALIPURDUAR |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
244 | BANKURA |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
245 | BIRBHUM |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
246 | COOCHBEHAR |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
247 | DAKSHIN DINAJPUR |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
248 | DARJEELING |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
249 | HOOGHLY |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
250 | HOWRAH |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
251 | JALPAIGURI |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
252 | JHARGRAM |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
253 | KALIMPONG |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
254 | MALDAH |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
255 | MURSHIDABAD |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
256 | NADIA |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
257 | NORTH 24 PARGANAS |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
258 | PASCHIM BARDHAMAN |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
259 | PASCHIM MEDINIPUR |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
260 | PURBA BARDHAMAN |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
261 | PURBA MEDINIPUR |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
262 | PURULIA |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
263 | SOUTH 24 PARGANAS |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
264 | UTTAR DINAJPUR |  | RCFA Division -I | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Acceptance cum work order for Balance work of construction of water sample collection cum laboratory cum ISA & DPMU activity center as well as training hall in the premises of RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000490/2025-2026 | 2065/RCD-I | 16/07/2025 | 30/08/2025 | M/S CHANDI CHARAN ROY | 24.7 | 0 | 0 | 70
265 | ALIPURDUAR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
266 | BANKURA |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
267 | BIRBHUM |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
268 | COOCHBEHAR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
269 | DAKSHIN DINAJPUR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
270 | DARJEELING |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
271 | HOOGHLY |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
272 | HOWRAH |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
273 | JALPAIGURI |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
274 | JHARGRAM |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
275 | KALIMPONG |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
276 | MALDAH |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
277 | MURSHIDABAD |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
278 | NADIA |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
279 | NORTH 24 PARGANAS |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
280 | PASCHIM BARDHAMAN |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
281 | PASCHIM MEDINIPUR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
282 | PURBA BARDHAMAN |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
283 | PURBA MEDINIPUR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
284 | PURULIA |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
285 | SOUTH 24 PARGANAS |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
286 | UTTAR DINAJPUR |  | Burdwan Division | Strengthening of State & District level rural water quality testing laboratories for certification of Bacteriological Water Quality Parameters in accordance to IS 15185 : 2016 for accreditation as per ISO/IEC 17025: 2017 by NABL related to Water Quality | SM/19299 | Support-WQMSP | Supplying of necessary ancillaries for Microbiological water quality parameter laboratory under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000330/2025-2026 | 184/RWS | 06/08/2025 | 21/08/2025 | GHOSH ENTERPRISE | 2.08 | 0 | 0 | 0
Total | [13 empty] | 4689.31 | 0 | 0