## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000174/2024-2025 | 3003/RS | 03/12/2024 | 03/02/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 64
2 | BANKURA |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000174/2024-2025 | 3003/RS | 03/12/2024 | 03/02/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 64
3 | BIRBHUM |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000174/2024-2025 | 3003/RS | 03/12/2024 | 03/02/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 64
4 | COOCHBEHAR |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000174/2024-2025 | 3003/RS | 03/12/2024 | 03/02/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 64
5 | DAKSHIN DINAJPUR |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000174/2024-2025 | 3003/RS | 03/12/2024 | 03/02/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 64
6 | DARJEELING |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000174/2024-2025 | 3003/RS | 03/12/2024 | 03/02/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 64
7 | HOOGHLY |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000174/2024-2025 | 3003/RS | 03/12/2024 | 03/02/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 64
8 | HOWRAH |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000174/2024-2025 | 3003/RS | 03/12/2024 | 03/02/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 64
9 | JALPAIGURI |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000174/2024-2025 | 3003/RS | 03/12/2024 | 03/02/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 64
10 | JHARGRAM |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000174/2024-2025 | 3003/RS | 03/12/2024 | 03/02/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 64
11 | KALIMPONG |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000174/2024-2025 | 3003/RS | 03/12/2024 | 03/02/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 64
12 | MALDAH |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000174/2024-2025 | 3003/RS | 03/12/2024 | 03/02/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 64
13 | MURSHIDABAD |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000174/2024-2025 | 3003/RS | 03/12/2024 | 03/02/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 64
14 | NADIA |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000174/2024-2025 | 3003/RS | 03/12/2024 | 03/02/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 64
15 | NORTH 24 PARGANAS |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000174/2024-2025 | 3003/RS | 03/12/2024 | 03/02/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 64
16 | PASCHIM BARDHAMAN |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000174/2024-2025 | 3003/RS | 03/12/2024 | 03/02/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 64
17 | PASCHIM MEDINIPUR |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000174/2024-2025 | 3003/RS | 03/12/2024 | 03/02/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 64
18 | PURBA BARDHAMAN |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000174/2024-2025 | 3003/RS | 03/12/2024 | 03/02/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 64
19 | PURBA MEDINIPUR |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000174/2024-2025 | 3003/RS | 03/12/2024 | 03/02/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 64
20 | PURULIA |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000174/2024-2025 | 3003/RS | 03/12/2024 | 03/02/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 64
21 | SOUTH 24 PARGANAS |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000174/2024-2025 | 3003/RS | 03/12/2024 | 03/02/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 64
22 | UTTAR DINAJPUR |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000174/2024-2025 | 3003/RS | 03/12/2024 | 03/02/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 64
23 | ALIPURDUAR |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000004/2025-2026 | 805/RS | 09/04/2025 | 09/04/2026 | HORIZEN | 229.27 | 32.06 | 13.98 | 7
24 | BANKURA |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000004/2025-2026 | 805/RS | 09/04/2025 | 09/04/2026 | HORIZEN | 229.27 | 32.06 | 13.98 | 7
25 | BIRBHUM |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000004/2025-2026 | 805/RS | 09/04/2025 | 09/04/2026 | HORIZEN | 229.27 | 32.06 | 13.98 | 7
26 | COOCHBEHAR |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000004/2025-2026 | 805/RS | 09/04/2025 | 09/04/2026 | HORIZEN | 229.27 | 32.06 | 13.98 | 7
27 | DAKSHIN DINAJPUR |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000004/2025-2026 | 805/RS | 09/04/2025 | 09/04/2026 | HORIZEN | 229.27 | 32.06 | 13.98 | 7
28 | DARJEELING |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000004/2025-2026 | 805/RS | 09/04/2025 | 09/04/2026 | HORIZEN | 229.27 | 32.06 | 13.98 | 7
29 | HOOGHLY |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000004/2025-2026 | 805/RS | 09/04/2025 | 09/04/2026 | HORIZEN | 229.27 | 32.06 | 13.98 | 7
30 | HOWRAH |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000004/2025-2026 | 805/RS | 09/04/2025 | 09/04/2026 | HORIZEN | 229.27 | 32.06 | 13.98 | 7
31 | JALPAIGURI |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000004/2025-2026 | 805/RS | 09/04/2025 | 09/04/2026 | HORIZEN | 229.27 | 32.06 | 13.98 | 7
32 | JHARGRAM |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000004/2025-2026 | 805/RS | 09/04/2025 | 09/04/2026 | HORIZEN | 229.27 | 32.06 | 13.98 | 7
33 | KALIMPONG |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000004/2025-2026 | 805/RS | 09/04/2025 | 09/04/2026 | HORIZEN | 229.27 | 32.06 | 13.98 | 7
34 | MALDAH |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000004/2025-2026 | 805/RS | 09/04/2025 | 09/04/2026 | HORIZEN | 229.27 | 32.06 | 13.98 | 7
35 | MURSHIDABAD |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000004/2025-2026 | 805/RS | 09/04/2025 | 09/04/2026 | HORIZEN | 229.27 | 32.06 | 13.98 | 7
36 | NADIA |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000004/2025-2026 | 805/RS | 09/04/2025 | 09/04/2026 | HORIZEN | 229.27 | 32.06 | 13.98 | 7
37 | NORTH 24 PARGANAS |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000004/2025-2026 | 805/RS | 09/04/2025 | 09/04/2026 | HORIZEN | 229.27 | 32.06 | 13.98 | 7
38 | PASCHIM BARDHAMAN |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000004/2025-2026 | 805/RS | 09/04/2025 | 09/04/2026 | HORIZEN | 229.27 | 32.06 | 13.98 | 7
39 | PASCHIM MEDINIPUR |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000004/2025-2026 | 805/RS | 09/04/2025 | 09/04/2026 | HORIZEN | 229.27 | 32.06 | 13.98 | 7
40 | PURBA BARDHAMAN |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000004/2025-2026 | 805/RS | 09/04/2025 | 09/04/2026 | HORIZEN | 229.27 | 32.06 | 13.98 | 7
41 | PURBA MEDINIPUR |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000004/2025-2026 | 805/RS | 09/04/2025 | 09/04/2026 | HORIZEN | 229.27 | 32.06 | 13.98 | 7
42 | PURULIA |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000004/2025-2026 | 805/RS | 09/04/2025 | 09/04/2026 | HORIZEN | 229.27 | 32.06 | 13.98 | 7
43 | SOUTH 24 PARGANAS |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000004/2025-2026 | 805/RS | 09/04/2025 | 09/04/2026 | HORIZEN | 229.27 | 32.06 | 13.98 | 7
44 | UTTAR DINAJPUR |  | Resource | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | SM/19332 | Support-MIS | Upkeepment and Management of WB-JJM Applications & Dashboard through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000004/2025-2026 | 805/RS | 09/04/2025 | 09/04/2026 | HORIZEN | 229.27 | 32.06 | 13.98 | 7
Total | [13 empty] | 5849.01 | 1387.63 | 23.72