## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000289/2024-2025 | 603/RS | 17/03/2025 | 17/03/2026 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 216.23 | 0 | 0 | 25
2 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000289/2024-2025 | 603/RS | 17/03/2025 | 17/03/2026 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 216.23 | 0 | 0 | 25
3 | DARJEELING |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000289/2024-2025 | 603/RS | 17/03/2025 | 17/03/2026 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 216.23 | 0 | 0 | 25
4 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000289/2024-2025 | 603/RS | 17/03/2025 | 17/03/2026 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 216.23 | 0 | 0 | 25
5 | KALIMPONG |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000289/2024-2025 | 603/RS | 17/03/2025 | 17/03/2026 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 216.23 | 0 | 0 | 25
6 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000294/2024-2025 | 606/RS | 17/03/2025 | 17/03/2026 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 80.17 | 0 | 0 | 50
7 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000294/2024-2025 | 606/RS | 17/03/2025 | 17/03/2026 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 80.17 | 0 | 0 | 50
8 | DARJEELING |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000294/2024-2025 | 606/RS | 17/03/2025 | 17/03/2026 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 80.17 | 0 | 0 | 50
9 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000294/2024-2025 | 606/RS | 17/03/2025 | 17/03/2026 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 80.17 | 0 | 0 | 50
10 | KALIMPONG |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000294/2024-2025 | 606/RS | 17/03/2025 | 17/03/2026 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 80.17 | 0 | 0 | 50
11 | ALIPURDUAR |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | (Continuation) Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Darjeeling (Hill) & Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. (from 01.10.2025 to 31.12.2025). | Assistant Engineer II | Junior Engineer I | ORD/000171/2025-2026 | 1509/NKWSMD | 24/09/2025 | 24/12/2025 | LIMRA SOCIAL WELFARE SOCIETY | 41.28 | 0 | 0 | 100
12 | COOCHBEHAR |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | (Continuation) Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Darjeeling (Hill) & Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. (from 01.10.2025 to 31.12.2025). | Assistant Engineer II | Junior Engineer I | ORD/000171/2025-2026 | 1509/NKWSMD | 24/09/2025 | 24/12/2025 | LIMRA SOCIAL WELFARE SOCIETY | 41.28 | 0 | 0 | 100
13 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | (Continuation) Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Darjeeling (Hill) & Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. (from 01.10.2025 to 31.12.2025). | Assistant Engineer II | Junior Engineer I | ORD/000171/2025-2026 | 1509/NKWSMD | 24/09/2025 | 24/12/2025 | LIMRA SOCIAL WELFARE SOCIETY | 41.28 | 0 | 0 | 100
14 | JALPAIGURI |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | (Continuation) Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Darjeeling (Hill) & Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. (from 01.10.2025 to 31.12.2025). | Assistant Engineer II | Junior Engineer I | ORD/000171/2025-2026 | 1509/NKWSMD | 24/09/2025 | 24/12/2025 | LIMRA SOCIAL WELFARE SOCIETY | 41.28 | 0 | 0 | 100
15 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | (Continuation) Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Darjeeling (Hill) & Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. (from 01.10.2025 to 31.12.2025). | Assistant Engineer II | Junior Engineer I | ORD/000171/2025-2026 | 1509/NKWSMD | 24/09/2025 | 24/12/2025 | LIMRA SOCIAL WELFARE SOCIETY | 41.28 | 0 | 0 | 100
16 | ALIPURDUAR |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | (Continuation) Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Darjeeling (Hill) & Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. (from 01.01.2026 to 31.01.2026) (1 month). | Assistant Engineer II | Junior Engineer I | ORD/000183/2025-2026 | 1839/NKWSMD | 31/12/2025 | 31/01/2026 | LIMRA SOCIAL WELFARE SOCIETY | 13.8 | 0 | 0 | 100
17 | COOCHBEHAR |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | (Continuation) Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Darjeeling (Hill) & Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. (from 01.01.2026 to 31.01.2026) (1 month). | Assistant Engineer II | Junior Engineer I | ORD/000183/2025-2026 | 1839/NKWSMD | 31/12/2025 | 31/01/2026 | LIMRA SOCIAL WELFARE SOCIETY | 13.8 | 0 | 0 | 100
18 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | (Continuation) Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Darjeeling (Hill) & Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. (from 01.01.2026 to 31.01.2026) (1 month). | Assistant Engineer II | Junior Engineer I | ORD/000183/2025-2026 | 1839/NKWSMD | 31/12/2025 | 31/01/2026 | LIMRA SOCIAL WELFARE SOCIETY | 13.8 | 0 | 0 | 100
19 | JALPAIGURI |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | (Continuation) Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Darjeeling (Hill) & Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. (from 01.01.2026 to 31.01.2026) (1 month). | Assistant Engineer II | Junior Engineer I | ORD/000183/2025-2026 | 1839/NKWSMD | 31/12/2025 | 31/01/2026 | LIMRA SOCIAL WELFARE SOCIETY | 13.8 | 0 | 0 | 100
20 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | (Continuation) Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Darjeeling (Hill) & Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. (from 01.01.2026 to 31.01.2026) (1 month). | Assistant Engineer II | Junior Engineer I | ORD/000183/2025-2026 | 1839/NKWSMD | 31/12/2025 | 31/01/2026 | LIMRA SOCIAL WELFARE SOCIETY | 13.8 | 0 | 0 | 100
21 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000223/2024-2025 | 09/RS | 02/01/2025 | 02/04/2025 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 29.13 | 0 | 0 | 99
22 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000223/2024-2025 | 09/RS | 02/01/2025 | 02/04/2025 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 29.13 | 0 | 0 | 99
23 | DARJEELING |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000223/2024-2025 | 09/RS | 02/01/2025 | 02/04/2025 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 29.13 | 0 | 0 | 99
24 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000223/2024-2025 | 09/RS | 02/01/2025 | 02/04/2025 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 29.13 | 0 | 0 | 99
25 | KALIMPONG |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000223/2024-2025 | 09/RS | 02/01/2025 | 02/04/2025 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 29.13 | 0 | 0 | 99
26 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000293/2024-2025 | 610/RS | 17/03/2025 | 17/03/2026 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 158.24 | 0 | 0 | 25
27 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000293/2024-2025 | 610/RS | 17/03/2025 | 17/03/2026 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 158.24 | 0 | 0 | 25
28 | DARJEELING |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000293/2024-2025 | 610/RS | 17/03/2025 | 17/03/2026 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 158.24 | 0 | 0 | 25
29 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000293/2024-2025 | 610/RS | 17/03/2025 | 17/03/2026 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 158.24 | 0 | 0 | 25
30 | KALIMPONG |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000293/2024-2025 | 610/RS | 17/03/2025 | 17/03/2026 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 158.24 | 0 | 0 | 25
31 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000290/2024-2025 | 612/RS | 17/03/2025 | 17/03/2026 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 112.58 | 0 | 0 | 25
32 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000290/2024-2025 | 612/RS | 17/03/2025 | 17/03/2026 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 112.58 | 0 | 0 | 25
33 | DARJEELING |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000290/2024-2025 | 612/RS | 17/03/2025 | 17/03/2026 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 112.58 | 0 | 0 | 25
34 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000290/2024-2025 | 612/RS | 17/03/2025 | 17/03/2026 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 112.58 | 0 | 0 | 25
35 | KALIMPONG |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Coochbehar , Jalpaiguri, Alipurduar, Darjeeling and Kalimpong districts under Jal Jeevan Mission (JJM) Support Activities. | SM/19361 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000290/2024-2025 | 612/RS | 17/03/2025 | 17/03/2026 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 112.58 | 0 | 0 | 25
Total | [13 empty] | 3257.15 | 0 | 0