## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Inspection and testing for quality monitoring of pipe materials delivered at site of various ongoing contract under Jal Jeevan Project of PHE Dte. in the State of West Bengal. | SM/09346 | Support-M&E | Engagement of Third Party Agency for inspection, Monitoring and Quality assurance of different type of pipe materials delivered site for various ongoing project in different zone under Jal Swapna Project of PHE Directorate in state of West Bengal. |  |  | ORD/000009/2021-2022 | 1058/RS | 17/06/2021 | 14/12/2021 | DR AMIN CONTROLLERS PVT. LTD. | 80 | 35.24 | 44.05 | 0
2 | BANKURA |  | Resource | Inspection and testing for quality monitoring of pipe materials delivered at site of various ongoing contract under Jal Jeevan Project of PHE Dte. in the State of West Bengal. | SM/09346 | Support-M&E | Engagement of Third Party Agency for inspection, Monitoring and Quality assurance of different type of pipe materials delivered site for various ongoing project in different zone under Jal Swapna Project of PHE Directorate in state of West Bengal. |  |  | ORD/000009/2021-2022 | 1058/RS | 17/06/2021 | 14/12/2021 | DR AMIN CONTROLLERS PVT. LTD. | 80 | 35.24 | 44.05 | 0
3 | BIRBHUM |  | Resource | Inspection and testing for quality monitoring of pipe materials delivered at site of various ongoing contract under Jal Jeevan Project of PHE Dte. in the State of West Bengal. | SM/09346 | Support-M&E | Engagement of Third Party Agency for inspection, Monitoring and Quality assurance of different type of pipe materials delivered site for various ongoing project in different zone under Jal Swapna Project of PHE Directorate in state of West Bengal. |  |  | ORD/000009/2021-2022 | 1058/RS | 17/06/2021 | 14/12/2021 | DR AMIN CONTROLLERS PVT. LTD. | 80 | 35.24 | 44.05 | 0
4 | COOCHBEHAR |  | Resource | Inspection and testing for quality monitoring of pipe materials delivered at site of various ongoing contract under Jal Jeevan Project of PHE Dte. in the State of West Bengal. | SM/09346 | Support-M&E | Engagement of Third Party Agency for inspection, Monitoring and Quality assurance of different type of pipe materials delivered site for various ongoing project in different zone under Jal Swapna Project of PHE Directorate in state of West Bengal. |  |  | ORD/000009/2021-2022 | 1058/RS | 17/06/2021 | 14/12/2021 | DR AMIN CONTROLLERS PVT. LTD. | 80 | 35.24 | 44.05 | 0
5 | DAKSHIN DINAJPUR |  | Resource | Inspection and testing for quality monitoring of pipe materials delivered at site of various ongoing contract under Jal Jeevan Project of PHE Dte. in the State of West Bengal. | SM/09346 | Support-M&E | Engagement of Third Party Agency for inspection, Monitoring and Quality assurance of different type of pipe materials delivered site for various ongoing project in different zone under Jal Swapna Project of PHE Directorate in state of West Bengal. |  |  | ORD/000009/2021-2022 | 1058/RS | 17/06/2021 | 14/12/2021 | DR AMIN CONTROLLERS PVT. LTD. | 80 | 35.24 | 44.05 | 0
6 | DARJEELING |  | Resource | Inspection and testing for quality monitoring of pipe materials delivered at site of various ongoing contract under Jal Jeevan Project of PHE Dte. in the State of West Bengal. | SM/09346 | Support-M&E | Engagement of Third Party Agency for inspection, Monitoring and Quality assurance of different type of pipe materials delivered site for various ongoing project in different zone under Jal Swapna Project of PHE Directorate in state of West Bengal. |  |  | ORD/000009/2021-2022 | 1058/RS | 17/06/2021 | 14/12/2021 | DR AMIN CONTROLLERS PVT. LTD. | 80 | 35.24 | 44.05 | 0
7 | HOOGHLY |  | Resource | Inspection and testing for quality monitoring of pipe materials delivered at site of various ongoing contract under Jal Jeevan Project of PHE Dte. in the State of West Bengal. | SM/09346 | Support-M&E | Engagement of Third Party Agency for inspection, Monitoring and Quality assurance of different type of pipe materials delivered site for various ongoing project in different zone under Jal Swapna Project of PHE Directorate in state of West Bengal. |  |  | ORD/000009/2021-2022 | 1058/RS | 17/06/2021 | 14/12/2021 | DR AMIN CONTROLLERS PVT. LTD. | 80 | 35.24 | 44.05 | 0
8 | HOWRAH |  | Resource | Inspection and testing for quality monitoring of pipe materials delivered at site of various ongoing contract under Jal Jeevan Project of PHE Dte. in the State of West Bengal. | SM/09346 | Support-M&E | Engagement of Third Party Agency for inspection, Monitoring and Quality assurance of different type of pipe materials delivered site for various ongoing project in different zone under Jal Swapna Project of PHE Directorate in state of West Bengal. |  |  | ORD/000009/2021-2022 | 1058/RS | 17/06/2021 | 14/12/2021 | DR AMIN CONTROLLERS PVT. LTD. | 80 | 35.24 | 44.05 | 0
9 | JALPAIGURI |  | Resource | Inspection and testing for quality monitoring of pipe materials delivered at site of various ongoing contract under Jal Jeevan Project of PHE Dte. in the State of West Bengal. | SM/09346 | Support-M&E | Engagement of Third Party Agency for inspection, Monitoring and Quality assurance of different type of pipe materials delivered site for various ongoing project in different zone under Jal Swapna Project of PHE Directorate in state of West Bengal. |  |  | ORD/000009/2021-2022 | 1058/RS | 17/06/2021 | 14/12/2021 | DR AMIN CONTROLLERS PVT. LTD. | 80 | 35.24 | 44.05 | 0
10 | JHARGRAM |  | Resource | Inspection and testing for quality monitoring of pipe materials delivered at site of various ongoing contract under Jal Jeevan Project of PHE Dte. in the State of West Bengal. | SM/09346 | Support-M&E | Engagement of Third Party Agency for inspection, Monitoring and Quality assurance of different type of pipe materials delivered site for various ongoing project in different zone under Jal Swapna Project of PHE Directorate in state of West Bengal. |  |  | ORD/000009/2021-2022 | 1058/RS | 17/06/2021 | 14/12/2021 | DR AMIN CONTROLLERS PVT. LTD. | 80 | 35.24 | 44.05 | 0
11 | KALIMPONG |  | Resource | Inspection and testing for quality monitoring of pipe materials delivered at site of various ongoing contract under Jal Jeevan Project of PHE Dte. in the State of West Bengal. | SM/09346 | Support-M&E | Engagement of Third Party Agency for inspection, Monitoring and Quality assurance of different type of pipe materials delivered site for various ongoing project in different zone under Jal Swapna Project of PHE Directorate in state of West Bengal. |  |  | ORD/000009/2021-2022 | 1058/RS | 17/06/2021 | 14/12/2021 | DR AMIN CONTROLLERS PVT. LTD. | 80 | 35.24 | 44.05 | 0
12 | MALDAH |  | Resource | Inspection and testing for quality monitoring of pipe materials delivered at site of various ongoing contract under Jal Jeevan Project of PHE Dte. in the State of West Bengal. | SM/09346 | Support-M&E | Engagement of Third Party Agency for inspection, Monitoring and Quality assurance of different type of pipe materials delivered site for various ongoing project in different zone under Jal Swapna Project of PHE Directorate in state of West Bengal. |  |  | ORD/000009/2021-2022 | 1058/RS | 17/06/2021 | 14/12/2021 | DR AMIN CONTROLLERS PVT. LTD. | 80 | 35.24 | 44.05 | 0
13 | MURSHIDABAD |  | Resource | Inspection and testing for quality monitoring of pipe materials delivered at site of various ongoing contract under Jal Jeevan Project of PHE Dte. in the State of West Bengal. | SM/09346 | Support-M&E | Engagement of Third Party Agency for inspection, Monitoring and Quality assurance of different type of pipe materials delivered site for various ongoing project in different zone under Jal Swapna Project of PHE Directorate in state of West Bengal. |  |  | ORD/000009/2021-2022 | 1058/RS | 17/06/2021 | 14/12/2021 | DR AMIN CONTROLLERS PVT. LTD. | 80 | 35.24 | 44.05 | 0
14 | NADIA |  | Resource | Inspection and testing for quality monitoring of pipe materials delivered at site of various ongoing contract under Jal Jeevan Project of PHE Dte. in the State of West Bengal. | SM/09346 | Support-M&E | Engagement of Third Party Agency for inspection, Monitoring and Quality assurance of different type of pipe materials delivered site for various ongoing project in different zone under Jal Swapna Project of PHE Directorate in state of West Bengal. |  |  | ORD/000009/2021-2022 | 1058/RS | 17/06/2021 | 14/12/2021 | DR AMIN CONTROLLERS PVT. LTD. | 80 | 35.24 | 44.05 | 0
15 | NORTH 24 PARGANAS |  | Resource | Inspection and testing for quality monitoring of pipe materials delivered at site of various ongoing contract under Jal Jeevan Project of PHE Dte. in the State of West Bengal. | SM/09346 | Support-M&E | Engagement of Third Party Agency for inspection, Monitoring and Quality assurance of different type of pipe materials delivered site for various ongoing project in different zone under Jal Swapna Project of PHE Directorate in state of West Bengal. |  |  | ORD/000009/2021-2022 | 1058/RS | 17/06/2021 | 14/12/2021 | DR AMIN CONTROLLERS PVT. LTD. | 80 | 35.24 | 44.05 | 0
16 | PASCHIM BARDHAMAN |  | Resource | Inspection and testing for quality monitoring of pipe materials delivered at site of various ongoing contract under Jal Jeevan Project of PHE Dte. in the State of West Bengal. | SM/09346 | Support-M&E | Engagement of Third Party Agency for inspection, Monitoring and Quality assurance of different type of pipe materials delivered site for various ongoing project in different zone under Jal Swapna Project of PHE Directorate in state of West Bengal. |  |  | ORD/000009/2021-2022 | 1058/RS | 17/06/2021 | 14/12/2021 | DR AMIN CONTROLLERS PVT. LTD. | 80 | 35.24 | 44.05 | 0
17 | PASCHIM MEDINIPUR |  | Resource | Inspection and testing for quality monitoring of pipe materials delivered at site of various ongoing contract under Jal Jeevan Project of PHE Dte. in the State of West Bengal. | SM/09346 | Support-M&E | Engagement of Third Party Agency for inspection, Monitoring and Quality assurance of different type of pipe materials delivered site for various ongoing project in different zone under Jal Swapna Project of PHE Directorate in state of West Bengal. |  |  | ORD/000009/2021-2022 | 1058/RS | 17/06/2021 | 14/12/2021 | DR AMIN CONTROLLERS PVT. LTD. | 80 | 35.24 | 44.05 | 0
18 | PURBA BARDHAMAN |  | Resource | Inspection and testing for quality monitoring of pipe materials delivered at site of various ongoing contract under Jal Jeevan Project of PHE Dte. in the State of West Bengal. | SM/09346 | Support-M&E | Engagement of Third Party Agency for inspection, Monitoring and Quality assurance of different type of pipe materials delivered site for various ongoing project in different zone under Jal Swapna Project of PHE Directorate in state of West Bengal. |  |  | ORD/000009/2021-2022 | 1058/RS | 17/06/2021 | 14/12/2021 | DR AMIN CONTROLLERS PVT. LTD. | 80 | 35.24 | 44.05 | 0
Total | [13 empty] | 1439.91 | 634.29 | 44.05