## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Preparation of sectional drawings to identify the PWD and PW (Roads) jurisdiction along the different roads and identify the related land marks for laying pipes at different locations for Surface Water Based Water Supply Scheme for Rajarhat, Haroa and Bhangore-II Block of North and South 24 Parganas Districts under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000045/2022-2023 | 1320/B.Ar.D | 19/07/2022 | 09/08/2022 | HORIZEN | 4.61 | 0 | 0 | 0
2 | BANKURA |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Preparation of sectional drawings to identify the PWD and PW (Roads) jurisdiction along the different roads and identify the related land marks for laying pipes at different locations for Surface Water Based Water Supply Scheme for Rajarhat, Haroa and Bhangore-II Block of North and South 24 Parganas Districts under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000045/2022-2023 | 1320/B.Ar.D | 19/07/2022 | 09/08/2022 | HORIZEN | 4.61 | 0 | 0 | 0
3 | BIRBHUM |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Preparation of sectional drawings to identify the PWD and PW (Roads) jurisdiction along the different roads and identify the related land marks for laying pipes at different locations for Surface Water Based Water Supply Scheme for Rajarhat, Haroa and Bhangore-II Block of North and South 24 Parganas Districts under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000045/2022-2023 | 1320/B.Ar.D | 19/07/2022 | 09/08/2022 | HORIZEN | 4.61 | 0 | 0 | 0
4 | COOCHBEHAR |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Preparation of sectional drawings to identify the PWD and PW (Roads) jurisdiction along the different roads and identify the related land marks for laying pipes at different locations for Surface Water Based Water Supply Scheme for Rajarhat, Haroa and Bhangore-II Block of North and South 24 Parganas Districts under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000045/2022-2023 | 1320/B.Ar.D | 19/07/2022 | 09/08/2022 | HORIZEN | 4.61 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Preparation of sectional drawings to identify the PWD and PW (Roads) jurisdiction along the different roads and identify the related land marks for laying pipes at different locations for Surface Water Based Water Supply Scheme for Rajarhat, Haroa and Bhangore-II Block of North and South 24 Parganas Districts under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000045/2022-2023 | 1320/B.Ar.D | 19/07/2022 | 09/08/2022 | HORIZEN | 4.61 | 0 | 0 | 0
6 | DARJEELING |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Preparation of sectional drawings to identify the PWD and PW (Roads) jurisdiction along the different roads and identify the related land marks for laying pipes at different locations for Surface Water Based Water Supply Scheme for Rajarhat, Haroa and Bhangore-II Block of North and South 24 Parganas Districts under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000045/2022-2023 | 1320/B.Ar.D | 19/07/2022 | 09/08/2022 | HORIZEN | 4.61 | 0 | 0 | 0
7 | HOOGHLY |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Preparation of sectional drawings to identify the PWD and PW (Roads) jurisdiction along the different roads and identify the related land marks for laying pipes at different locations for Surface Water Based Water Supply Scheme for Rajarhat, Haroa and Bhangore-II Block of North and South 24 Parganas Districts under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000045/2022-2023 | 1320/B.Ar.D | 19/07/2022 | 09/08/2022 | HORIZEN | 4.61 | 0 | 0 | 0
8 | HOWRAH |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Preparation of sectional drawings to identify the PWD and PW (Roads) jurisdiction along the different roads and identify the related land marks for laying pipes at different locations for Surface Water Based Water Supply Scheme for Rajarhat, Haroa and Bhangore-II Block of North and South 24 Parganas Districts under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000045/2022-2023 | 1320/B.Ar.D | 19/07/2022 | 09/08/2022 | HORIZEN | 4.61 | 0 | 0 | 0
9 | JALPAIGURI |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Preparation of sectional drawings to identify the PWD and PW (Roads) jurisdiction along the different roads and identify the related land marks for laying pipes at different locations for Surface Water Based Water Supply Scheme for Rajarhat, Haroa and Bhangore-II Block of North and South 24 Parganas Districts under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000045/2022-2023 | 1320/B.Ar.D | 19/07/2022 | 09/08/2022 | HORIZEN | 4.61 | 0 | 0 | 0
10 | JHARGRAM |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Preparation of sectional drawings to identify the PWD and PW (Roads) jurisdiction along the different roads and identify the related land marks for laying pipes at different locations for Surface Water Based Water Supply Scheme for Rajarhat, Haroa and Bhangore-II Block of North and South 24 Parganas Districts under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000045/2022-2023 | 1320/B.Ar.D | 19/07/2022 | 09/08/2022 | HORIZEN | 4.61 | 0 | 0 | 0
11 | KALIMPONG |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Preparation of sectional drawings to identify the PWD and PW (Roads) jurisdiction along the different roads and identify the related land marks for laying pipes at different locations for Surface Water Based Water Supply Scheme for Rajarhat, Haroa and Bhangore-II Block of North and South 24 Parganas Districts under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000045/2022-2023 | 1320/B.Ar.D | 19/07/2022 | 09/08/2022 | HORIZEN | 4.61 | 0 | 0 | 0
12 | MALDAH |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Preparation of sectional drawings to identify the PWD and PW (Roads) jurisdiction along the different roads and identify the related land marks for laying pipes at different locations for Surface Water Based Water Supply Scheme for Rajarhat, Haroa and Bhangore-II Block of North and South 24 Parganas Districts under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000045/2022-2023 | 1320/B.Ar.D | 19/07/2022 | 09/08/2022 | HORIZEN | 4.61 | 0 | 0 | 0
13 | MURSHIDABAD |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Preparation of sectional drawings to identify the PWD and PW (Roads) jurisdiction along the different roads and identify the related land marks for laying pipes at different locations for Surface Water Based Water Supply Scheme for Rajarhat, Haroa and Bhangore-II Block of North and South 24 Parganas Districts under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000045/2022-2023 | 1320/B.Ar.D | 19/07/2022 | 09/08/2022 | HORIZEN | 4.61 | 0 | 0 | 0
14 | NADIA |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Preparation of sectional drawings to identify the PWD and PW (Roads) jurisdiction along the different roads and identify the related land marks for laying pipes at different locations for Surface Water Based Water Supply Scheme for Rajarhat, Haroa and Bhangore-II Block of North and South 24 Parganas Districts under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000045/2022-2023 | 1320/B.Ar.D | 19/07/2022 | 09/08/2022 | HORIZEN | 4.61 | 0 | 0 | 0
15 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Preparation of sectional drawings to identify the PWD and PW (Roads) jurisdiction along the different roads and identify the related land marks for laying pipes at different locations for Surface Water Based Water Supply Scheme for Rajarhat, Haroa and Bhangore-II Block of North and South 24 Parganas Districts under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000045/2022-2023 | 1320/B.Ar.D | 19/07/2022 | 09/08/2022 | HORIZEN | 4.61 | 0 | 0 | 0
16 | PASCHIM BARDHAMAN |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Preparation of sectional drawings to identify the PWD and PW (Roads) jurisdiction along the different roads and identify the related land marks for laying pipes at different locations for Surface Water Based Water Supply Scheme for Rajarhat, Haroa and Bhangore-II Block of North and South 24 Parganas Districts under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000045/2022-2023 | 1320/B.Ar.D | 19/07/2022 | 09/08/2022 | HORIZEN | 4.61 | 0 | 0 | 0
17 | PASCHIM MEDINIPUR |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Preparation of sectional drawings to identify the PWD and PW (Roads) jurisdiction along the different roads and identify the related land marks for laying pipes at different locations for Surface Water Based Water Supply Scheme for Rajarhat, Haroa and Bhangore-II Block of North and South 24 Parganas Districts under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000045/2022-2023 | 1320/B.Ar.D | 19/07/2022 | 09/08/2022 | HORIZEN | 4.61 | 0 | 0 | 0
18 | PURBA BARDHAMAN |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Preparation of sectional drawings to identify the PWD and PW (Roads) jurisdiction along the different roads and identify the related land marks for laying pipes at different locations for Surface Water Based Water Supply Scheme for Rajarhat, Haroa and Bhangore-II Block of North and South 24 Parganas Districts under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000045/2022-2023 | 1320/B.Ar.D | 19/07/2022 | 09/08/2022 | HORIZEN | 4.61 | 0 | 0 | 0
19 | PURBA MEDINIPUR |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Preparation of sectional drawings to identify the PWD and PW (Roads) jurisdiction along the different roads and identify the related land marks for laying pipes at different locations for Surface Water Based Water Supply Scheme for Rajarhat, Haroa and Bhangore-II Block of North and South 24 Parganas Districts under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000045/2022-2023 | 1320/B.Ar.D | 19/07/2022 | 09/08/2022 | HORIZEN | 4.61 | 0 | 0 | 0
20 | PURULIA |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Preparation of sectional drawings to identify the PWD and PW (Roads) jurisdiction along the different roads and identify the related land marks for laying pipes at different locations for Surface Water Based Water Supply Scheme for Rajarhat, Haroa and Bhangore-II Block of North and South 24 Parganas Districts under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000045/2022-2023 | 1320/B.Ar.D | 19/07/2022 | 09/08/2022 | HORIZEN | 4.61 | 0 | 0 | 0
21 | SOUTH 24 PARAGANAS |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Preparation of sectional drawings to identify the PWD and PW (Roads) jurisdiction along the different roads and identify the related land marks for laying pipes at different locations for Surface Water Based Water Supply Scheme for Rajarhat, Haroa and Bhangore-II Block of North and South 24 Parganas Districts under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000045/2022-2023 | 1320/B.Ar.D | 19/07/2022 | 09/08/2022 | HORIZEN | 4.61 | 0 | 0 | 0
22 | UTTAR DINAJPUR |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Preparation of sectional drawings to identify the PWD and PW (Roads) jurisdiction along the different roads and identify the related land marks for laying pipes at different locations for Surface Water Based Water Supply Scheme for Rajarhat, Haroa and Bhangore-II Block of North and South 24 Parganas Districts under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000045/2022-2023 | 1320/B.Ar.D | 19/07/2022 | 09/08/2022 | HORIZEN | 4.61 | 0 | 0 | 0
23 | ALIPURDUAR |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Continuation Order for the work "Upkeepment, redesigning & time to time updation of different modules of map domain in official website of PHED, Govt. of West Bengal under Support Activities related to Jal Jeevan Mission". (w.e.f. 03.03.2022 to 02.06.2022) | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000306/2021-2022 | 357/B.Ar.D. | 02/03/2022 | 31/05/2022 | HORIZEN | 22.69 | 5.2 | 22.93 | 0
24 | BANKURA |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Continuation Order for the work "Upkeepment, redesigning & time to time updation of different modules of map domain in official website of PHED, Govt. of West Bengal under Support Activities related to Jal Jeevan Mission". (w.e.f. 03.03.2022 to 02.06.2022) | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000306/2021-2022 | 357/B.Ar.D. | 02/03/2022 | 31/05/2022 | HORIZEN | 22.69 | 5.2 | 22.93 | 0
25 | BIRBHUM |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Continuation Order for the work "Upkeepment, redesigning & time to time updation of different modules of map domain in official website of PHED, Govt. of West Bengal under Support Activities related to Jal Jeevan Mission". (w.e.f. 03.03.2022 to 02.06.2022) | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000306/2021-2022 | 357/B.Ar.D. | 02/03/2022 | 31/05/2022 | HORIZEN | 22.69 | 5.2 | 22.93 | 0
26 | COOCHBEHAR |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Continuation Order for the work "Upkeepment, redesigning & time to time updation of different modules of map domain in official website of PHED, Govt. of West Bengal under Support Activities related to Jal Jeevan Mission". (w.e.f. 03.03.2022 to 02.06.2022) | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000306/2021-2022 | 357/B.Ar.D. | 02/03/2022 | 31/05/2022 | HORIZEN | 22.69 | 5.2 | 22.93 | 0
27 | DAKSHIN DINAJPUR |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Continuation Order for the work "Upkeepment, redesigning & time to time updation of different modules of map domain in official website of PHED, Govt. of West Bengal under Support Activities related to Jal Jeevan Mission". (w.e.f. 03.03.2022 to 02.06.2022) | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000306/2021-2022 | 357/B.Ar.D. | 02/03/2022 | 31/05/2022 | HORIZEN | 22.69 | 5.2 | 22.93 | 0
28 | DARJEELING |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Continuation Order for the work "Upkeepment, redesigning & time to time updation of different modules of map domain in official website of PHED, Govt. of West Bengal under Support Activities related to Jal Jeevan Mission". (w.e.f. 03.03.2022 to 02.06.2022) | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000306/2021-2022 | 357/B.Ar.D. | 02/03/2022 | 31/05/2022 | HORIZEN | 22.69 | 5.2 | 22.93 | 0
29 | HOOGHLY |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Continuation Order for the work "Upkeepment, redesigning & time to time updation of different modules of map domain in official website of PHED, Govt. of West Bengal under Support Activities related to Jal Jeevan Mission". (w.e.f. 03.03.2022 to 02.06.2022) | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000306/2021-2022 | 357/B.Ar.D. | 02/03/2022 | 31/05/2022 | HORIZEN | 22.69 | 5.2 | 22.93 | 0
30 | HOWRAH |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Continuation Order for the work "Upkeepment, redesigning & time to time updation of different modules of map domain in official website of PHED, Govt. of West Bengal under Support Activities related to Jal Jeevan Mission". (w.e.f. 03.03.2022 to 02.06.2022) | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000306/2021-2022 | 357/B.Ar.D. | 02/03/2022 | 31/05/2022 | HORIZEN | 22.69 | 5.2 | 22.93 | 0
31 | JALPAIGURI |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Continuation Order for the work "Upkeepment, redesigning & time to time updation of different modules of map domain in official website of PHED, Govt. of West Bengal under Support Activities related to Jal Jeevan Mission". (w.e.f. 03.03.2022 to 02.06.2022) | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000306/2021-2022 | 357/B.Ar.D. | 02/03/2022 | 31/05/2022 | HORIZEN | 22.69 | 5.2 | 22.93 | 0
32 | JHARGRAM |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Continuation Order for the work "Upkeepment, redesigning & time to time updation of different modules of map domain in official website of PHED, Govt. of West Bengal under Support Activities related to Jal Jeevan Mission". (w.e.f. 03.03.2022 to 02.06.2022) | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000306/2021-2022 | 357/B.Ar.D. | 02/03/2022 | 31/05/2022 | HORIZEN | 22.69 | 5.2 | 22.93 | 0
33 | KALIMPONG |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Continuation Order for the work "Upkeepment, redesigning & time to time updation of different modules of map domain in official website of PHED, Govt. of West Bengal under Support Activities related to Jal Jeevan Mission". (w.e.f. 03.03.2022 to 02.06.2022) | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000306/2021-2022 | 357/B.Ar.D. | 02/03/2022 | 31/05/2022 | HORIZEN | 22.69 | 5.2 | 22.93 | 0
34 | MALDAH |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Continuation Order for the work "Upkeepment, redesigning & time to time updation of different modules of map domain in official website of PHED, Govt. of West Bengal under Support Activities related to Jal Jeevan Mission". (w.e.f. 03.03.2022 to 02.06.2022) | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000306/2021-2022 | 357/B.Ar.D. | 02/03/2022 | 31/05/2022 | HORIZEN | 22.69 | 5.2 | 22.93 | 0
35 | MURSHIDABAD |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Continuation Order for the work "Upkeepment, redesigning & time to time updation of different modules of map domain in official website of PHED, Govt. of West Bengal under Support Activities related to Jal Jeevan Mission". (w.e.f. 03.03.2022 to 02.06.2022) | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000306/2021-2022 | 357/B.Ar.D. | 02/03/2022 | 31/05/2022 | HORIZEN | 22.69 | 5.2 | 22.93 | 0
36 | NADIA |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Continuation Order for the work "Upkeepment, redesigning & time to time updation of different modules of map domain in official website of PHED, Govt. of West Bengal under Support Activities related to Jal Jeevan Mission". (w.e.f. 03.03.2022 to 02.06.2022) | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000306/2021-2022 | 357/B.Ar.D. | 02/03/2022 | 31/05/2022 | HORIZEN | 22.69 | 5.2 | 22.93 | 0
37 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Continuation Order for the work "Upkeepment, redesigning & time to time updation of different modules of map domain in official website of PHED, Govt. of West Bengal under Support Activities related to Jal Jeevan Mission". (w.e.f. 03.03.2022 to 02.06.2022) | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000306/2021-2022 | 357/B.Ar.D. | 02/03/2022 | 31/05/2022 | HORIZEN | 22.69 | 5.2 | 22.93 | 0
38 | PASCHIM BARDHAMAN |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Continuation Order for the work "Upkeepment, redesigning & time to time updation of different modules of map domain in official website of PHED, Govt. of West Bengal under Support Activities related to Jal Jeevan Mission". (w.e.f. 03.03.2022 to 02.06.2022) | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000306/2021-2022 | 357/B.Ar.D. | 02/03/2022 | 31/05/2022 | HORIZEN | 22.69 | 5.2 | 22.93 | 0
39 | PASCHIM MEDINIPUR |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Continuation Order for the work "Upkeepment, redesigning & time to time updation of different modules of map domain in official website of PHED, Govt. of West Bengal under Support Activities related to Jal Jeevan Mission". (w.e.f. 03.03.2022 to 02.06.2022) | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000306/2021-2022 | 357/B.Ar.D. | 02/03/2022 | 31/05/2022 | HORIZEN | 22.69 | 5.2 | 22.93 | 0
40 | PURBA BARDHAMAN |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Continuation Order for the work "Upkeepment, redesigning & time to time updation of different modules of map domain in official website of PHED, Govt. of West Bengal under Support Activities related to Jal Jeevan Mission". (w.e.f. 03.03.2022 to 02.06.2022) | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000306/2021-2022 | 357/B.Ar.D. | 02/03/2022 | 31/05/2022 | HORIZEN | 22.69 | 5.2 | 22.93 | 0
41 | PURBA MEDINIPUR |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Continuation Order for the work "Upkeepment, redesigning & time to time updation of different modules of map domain in official website of PHED, Govt. of West Bengal under Support Activities related to Jal Jeevan Mission". (w.e.f. 03.03.2022 to 02.06.2022) | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000306/2021-2022 | 357/B.Ar.D. | 02/03/2022 | 31/05/2022 | HORIZEN | 22.69 | 5.2 | 22.93 | 0
42 | PURULIA |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Continuation Order for the work "Upkeepment, redesigning & time to time updation of different modules of map domain in official website of PHED, Govt. of West Bengal under Support Activities related to Jal Jeevan Mission". (w.e.f. 03.03.2022 to 02.06.2022) | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000306/2021-2022 | 357/B.Ar.D. | 02/03/2022 | 31/05/2022 | HORIZEN | 22.69 | 5.2 | 22.93 | 0
43 | SOUTH 24 PARAGANAS |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Continuation Order for the work "Upkeepment, redesigning & time to time updation of different modules of map domain in official website of PHED, Govt. of West Bengal under Support Activities related to Jal Jeevan Mission". (w.e.f. 03.03.2022 to 02.06.2022) | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000306/2021-2022 | 357/B.Ar.D. | 02/03/2022 | 31/05/2022 | HORIZEN | 22.69 | 5.2 | 22.93 | 0
44 | UTTAR DINAJPUR |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Continuation Order for the work "Upkeepment, redesigning & time to time updation of different modules of map domain in official website of PHED, Govt. of West Bengal under Support Activities related to Jal Jeevan Mission". (w.e.f. 03.03.2022 to 02.06.2022) | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000306/2021-2022 | 357/B.Ar.D. | 02/03/2022 | 31/05/2022 | HORIZEN | 22.69 | 5.2 | 22.93 | 0
45 | ALIPURDUAR |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Restructuring, redesigning, adaptation of new technologies with up-dation, modification & maintenance of different modules of Map Domain along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical presentations; upload & hosting of high quality Web GIS compatible based maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes which are to be used as a Decision Support System. (w.e.f. 03.06.2022 to 02.06.2023) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000025/2022-2023 | 865/B.Ar.D. | 11/05/2022 | 06/05/2023 | HORIZEN | 97.13 | 72.73 | 74.88 | 100
46 | BANKURA |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Restructuring, redesigning, adaptation of new technologies with up-dation, modification & maintenance of different modules of Map Domain along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical presentations; upload & hosting of high quality Web GIS compatible based maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes which are to be used as a Decision Support System. (w.e.f. 03.06.2022 to 02.06.2023) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000025/2022-2023 | 865/B.Ar.D. | 11/05/2022 | 06/05/2023 | HORIZEN | 97.13 | 72.73 | 74.88 | 100
47 | BIRBHUM |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Restructuring, redesigning, adaptation of new technologies with up-dation, modification & maintenance of different modules of Map Domain along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical presentations; upload & hosting of high quality Web GIS compatible based maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes which are to be used as a Decision Support System. (w.e.f. 03.06.2022 to 02.06.2023) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000025/2022-2023 | 865/B.Ar.D. | 11/05/2022 | 06/05/2023 | HORIZEN | 97.13 | 72.73 | 74.88 | 100
48 | COOCHBEHAR |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Restructuring, redesigning, adaptation of new technologies with up-dation, modification & maintenance of different modules of Map Domain along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical presentations; upload & hosting of high quality Web GIS compatible based maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes which are to be used as a Decision Support System. (w.e.f. 03.06.2022 to 02.06.2023) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000025/2022-2023 | 865/B.Ar.D. | 11/05/2022 | 06/05/2023 | HORIZEN | 97.13 | 72.73 | 74.88 | 100
49 | DAKSHIN DINAJPUR |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Restructuring, redesigning, adaptation of new technologies with up-dation, modification & maintenance of different modules of Map Domain along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical presentations; upload & hosting of high quality Web GIS compatible based maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes which are to be used as a Decision Support System. (w.e.f. 03.06.2022 to 02.06.2023) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000025/2022-2023 | 865/B.Ar.D. | 11/05/2022 | 06/05/2023 | HORIZEN | 97.13 | 72.73 | 74.88 | 100
50 | DARJEELING |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Restructuring, redesigning, adaptation of new technologies with up-dation, modification & maintenance of different modules of Map Domain along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical presentations; upload & hosting of high quality Web GIS compatible based maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes which are to be used as a Decision Support System. (w.e.f. 03.06.2022 to 02.06.2023) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000025/2022-2023 | 865/B.Ar.D. | 11/05/2022 | 06/05/2023 | HORIZEN | 97.13 | 72.73 | 74.88 | 100
51 | HOOGHLY |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Restructuring, redesigning, adaptation of new technologies with up-dation, modification & maintenance of different modules of Map Domain along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical presentations; upload & hosting of high quality Web GIS compatible based maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes which are to be used as a Decision Support System. (w.e.f. 03.06.2022 to 02.06.2023) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000025/2022-2023 | 865/B.Ar.D. | 11/05/2022 | 06/05/2023 | HORIZEN | 97.13 | 72.73 | 74.88 | 100
52 | HOWRAH |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Restructuring, redesigning, adaptation of new technologies with up-dation, modification & maintenance of different modules of Map Domain along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical presentations; upload & hosting of high quality Web GIS compatible based maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes which are to be used as a Decision Support System. (w.e.f. 03.06.2022 to 02.06.2023) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000025/2022-2023 | 865/B.Ar.D. | 11/05/2022 | 06/05/2023 | HORIZEN | 97.13 | 72.73 | 74.88 | 100
53 | JALPAIGURI |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Restructuring, redesigning, adaptation of new technologies with up-dation, modification & maintenance of different modules of Map Domain along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical presentations; upload & hosting of high quality Web GIS compatible based maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes which are to be used as a Decision Support System. (w.e.f. 03.06.2022 to 02.06.2023) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000025/2022-2023 | 865/B.Ar.D. | 11/05/2022 | 06/05/2023 | HORIZEN | 97.13 | 72.73 | 74.88 | 100
54 | JHARGRAM |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Restructuring, redesigning, adaptation of new technologies with up-dation, modification & maintenance of different modules of Map Domain along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical presentations; upload & hosting of high quality Web GIS compatible based maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes which are to be used as a Decision Support System. (w.e.f. 03.06.2022 to 02.06.2023) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000025/2022-2023 | 865/B.Ar.D. | 11/05/2022 | 06/05/2023 | HORIZEN | 97.13 | 72.73 | 74.88 | 100
55 | KALIMPONG |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Restructuring, redesigning, adaptation of new technologies with up-dation, modification & maintenance of different modules of Map Domain along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical presentations; upload & hosting of high quality Web GIS compatible based maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes which are to be used as a Decision Support System. (w.e.f. 03.06.2022 to 02.06.2023) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000025/2022-2023 | 865/B.Ar.D. | 11/05/2022 | 06/05/2023 | HORIZEN | 97.13 | 72.73 | 74.88 | 100
56 | MALDAH |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Restructuring, redesigning, adaptation of new technologies with up-dation, modification & maintenance of different modules of Map Domain along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical presentations; upload & hosting of high quality Web GIS compatible based maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes which are to be used as a Decision Support System. (w.e.f. 03.06.2022 to 02.06.2023) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000025/2022-2023 | 865/B.Ar.D. | 11/05/2022 | 06/05/2023 | HORIZEN | 97.13 | 72.73 | 74.88 | 100
57 | MURSHIDABAD |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Restructuring, redesigning, adaptation of new technologies with up-dation, modification & maintenance of different modules of Map Domain along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical presentations; upload & hosting of high quality Web GIS compatible based maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes which are to be used as a Decision Support System. (w.e.f. 03.06.2022 to 02.06.2023) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000025/2022-2023 | 865/B.Ar.D. | 11/05/2022 | 06/05/2023 | HORIZEN | 97.13 | 72.73 | 74.88 | 100
58 | NADIA |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Restructuring, redesigning, adaptation of new technologies with up-dation, modification & maintenance of different modules of Map Domain along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical presentations; upload & hosting of high quality Web GIS compatible based maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes which are to be used as a Decision Support System. (w.e.f. 03.06.2022 to 02.06.2023) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000025/2022-2023 | 865/B.Ar.D. | 11/05/2022 | 06/05/2023 | HORIZEN | 97.13 | 72.73 | 74.88 | 100
59 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Restructuring, redesigning, adaptation of new technologies with up-dation, modification & maintenance of different modules of Map Domain along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical presentations; upload & hosting of high quality Web GIS compatible based maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes which are to be used as a Decision Support System. (w.e.f. 03.06.2022 to 02.06.2023) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000025/2022-2023 | 865/B.Ar.D. | 11/05/2022 | 06/05/2023 | HORIZEN | 97.13 | 72.73 | 74.88 | 100
60 | PASCHIM BARDHAMAN |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Restructuring, redesigning, adaptation of new technologies with up-dation, modification & maintenance of different modules of Map Domain along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical presentations; upload & hosting of high quality Web GIS compatible based maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes which are to be used as a Decision Support System. (w.e.f. 03.06.2022 to 02.06.2023) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000025/2022-2023 | 865/B.Ar.D. | 11/05/2022 | 06/05/2023 | HORIZEN | 97.13 | 72.73 | 74.88 | 100
61 | PASCHIM MEDINIPUR |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Restructuring, redesigning, adaptation of new technologies with up-dation, modification & maintenance of different modules of Map Domain along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical presentations; upload & hosting of high quality Web GIS compatible based maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes which are to be used as a Decision Support System. (w.e.f. 03.06.2022 to 02.06.2023) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000025/2022-2023 | 865/B.Ar.D. | 11/05/2022 | 06/05/2023 | HORIZEN | 97.13 | 72.73 | 74.88 | 100
62 | PURBA BARDHAMAN |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Restructuring, redesigning, adaptation of new technologies with up-dation, modification & maintenance of different modules of Map Domain along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical presentations; upload & hosting of high quality Web GIS compatible based maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes which are to be used as a Decision Support System. (w.e.f. 03.06.2022 to 02.06.2023) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000025/2022-2023 | 865/B.Ar.D. | 11/05/2022 | 06/05/2023 | HORIZEN | 97.13 | 72.73 | 74.88 | 100
63 | PURBA MEDINIPUR |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Restructuring, redesigning, adaptation of new technologies with up-dation, modification & maintenance of different modules of Map Domain along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical presentations; upload & hosting of high quality Web GIS compatible based maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes which are to be used as a Decision Support System. (w.e.f. 03.06.2022 to 02.06.2023) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000025/2022-2023 | 865/B.Ar.D. | 11/05/2022 | 06/05/2023 | HORIZEN | 97.13 | 72.73 | 74.88 | 100
64 | PURULIA |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Restructuring, redesigning, adaptation of new technologies with up-dation, modification & maintenance of different modules of Map Domain along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical presentations; upload & hosting of high quality Web GIS compatible based maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes which are to be used as a Decision Support System. (w.e.f. 03.06.2022 to 02.06.2023) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000025/2022-2023 | 865/B.Ar.D. | 11/05/2022 | 06/05/2023 | HORIZEN | 97.13 | 72.73 | 74.88 | 100
65 | SOUTH 24 PARAGANAS |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Restructuring, redesigning, adaptation of new technologies with up-dation, modification & maintenance of different modules of Map Domain along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical presentations; upload & hosting of high quality Web GIS compatible based maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes which are to be used as a Decision Support System. (w.e.f. 03.06.2022 to 02.06.2023) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000025/2022-2023 | 865/B.Ar.D. | 11/05/2022 | 06/05/2023 | HORIZEN | 97.13 | 72.73 | 74.88 | 100
66 | UTTAR DINAJPUR |  | Barasat Arsenic Division | Restructuring, redesigning, adaptation of new technologies, with updation, modification & maintenance of different modules of Map Domain, along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical pr | SM/10736 | Support-MIS | Restructuring, redesigning, adaptation of new technologies with up-dation, modification & maintenance of different modules of Map Domain along with backup of data & codebase; solving critical issues along with preparation of data driven info-graphical presentations; upload & hosting of high quality Web GIS compatible based maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes which are to be used as a Decision Support System. (w.e.f. 03.06.2022 to 02.06.2023) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000025/2022-2023 | 865/B.Ar.D. | 11/05/2022 | 06/05/2023 | HORIZEN | 97.13 | 72.73 | 74.88 | 100
Total | [13 empty] | 2737.24 | 1714.43 | 62.63