## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | Procurement of Chemicals & Consumables, Glassware for Laboratories, Consumables for OMAS, OMAS Kit & Annual Maintenance contract of Computer, Printer, UPS & other peripherals for Laboratories. | SM/06623 | Support-WQMSP | Supply and delivery of portable multi-parameter water quality testing device including training on operation of the device of all Gram Panchayats of Alipuduar-I & kalchini Blocks of Alipurduar District : Alipurduar Division: P.H.E. Dte. | Alipurduar RWS |  | ORD/000017/2021-2022 | 432/ALD | 23/06/2021 | 08/07/2021 | SUNANDA ENVIRONMENTAL INTERNATIONAL PVT. LTD. | 2.29 | 2.16 | 94.24 | 0
2 | ALIPURDUAR |  | Alipurduar Division | Procurement of Chemicals & Consumables, Glassware for Laboratories, Consumables for OMAS, OMAS Kit & Annual Maintenance contract of Computer, Printer, UPS & other peripherals for Laboratories. | SM/06623 | Support-WQMSP | Supply and delivery of portable multi-parameter water quality testing device including training on operation of the device of all Gram Panchayats of Falakata & Madarihat- Birpara Blocks of Alipurduar District : Alipurduar Division: P.H.E. Dte | Birpara A.E |  | ORD/000018/2021-2022 | 433/ALD | 23/06/2021 | 08/07/2021 | SUNANDA ENVIRONMENTAL INTERNATIONAL PVT. LTD. | 2.28 | 2.2 | 96.55 | 0
3 | ALIPURDUAR |  | Alipurduar Division | Procurement of Chemicals & Consumables, Glassware for Laboratories, Consumables for OMAS, OMAS Kit & Annual Maintenance contract of Computer, Printer, UPS & other peripherals for Laboratories. | SM/06623 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Samuktala Sub-District Water Testing Laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000051/2021-2022 | 787/ALD | 18/08/2021 | 02/09/2021 | LAB SOLUTION | 4.83 | 4.81 | 99.62 | 0
4 | ALIPURDUAR |  | Alipurduar Division | Procurement of Chemicals & Consumables, Glassware for Laboratories, Consumables for OMAS, OMAS Kit & Annual Maintenance contract of Computer, Printer, UPS & other peripherals for Laboratories. | SM/06623 | Support-WQMSP | Procurement of Chemicals, Consumables & Glassware for all laboratories under Alipurduar Division , PHE Dte. | Alipurduar RWS |  | ORD/000290/2021-2022 | 1859/ALD | 13/12/2021 | 12/01/2022 | DULAL MAJUMDER | 4.76 | 4.76 | 100 | 0
5 | ALIPURDUAR |  | Alipurduar Division | Procurement of Chemicals & Consumables, Glassware for Laboratories, Consumables for OMAS, OMAS Kit & Annual Maintenance contract of Computer, Printer, UPS & other peripherals for Laboratories. | SM/06623 | Support-WQMSP | Supply and delivery of portable multi-parameter water quality testing device including training on operation of the device of all Gram Panchayats of Alipuduar-II & Kumargram Blocks of Alipurduar District : Alipurduar Division: P.H.E. Dte. | Alipurduar Sadar Sub Division |  | ORD/000016/2021-2022 | 431/ALD | 23/06/2021 | 08/07/2021 | SUNANDA ENVIRONMENTAL INTERNATIONAL PVT. LTD. | 2.28 | 2.28 | 100 | 0
6 | ALIPURDUAR |  | Alipurduar Division | Procurement of Chemicals & Consumables, Glassware for Laboratories, Consumables for OMAS, OMAS Kit & Annual Maintenance contract of Computer, Printer, UPS & other peripherals for Laboratories. | SM/06623 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Birpara Sub-District Water Testing Laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Madarihat - Birpara Block | ORD/000050/2021-2022 | 786/ALD | 18/08/2021 | 02/09/2021 | LAB SOLUTION | 4.83 | 4.81 | 99.62 | 0
Total | [13 empty] | 21.28 | 21.03 | 98.84