## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) | SM/07057 | Retrofitting | Fuel bill for the month of August 2021 |  |  | VCH/000568/2021-2022 | 118/21-22/PFMS | 08/09/2021 | 08/09/2021 | SHIVAM SERVICE STATION | 0.21 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) | SM/07057 | Retrofitting | Laying of UPVC/DI/MS Distribution pipe line and FHTC in connection with Jaldhara Jal Sapna and other misc. work for Jateswar WSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000239/2020-2021 | 1180/ALD | 15/12/2020 | 13/02/2021 | SANJIT SAHA | 41.94 | 61.91 | 147.61 | 96
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) | SM/07057 | Retrofitting | Laying of UPVC/DI/MS/CI distribution pipe line for gap filling and FHTC connection for Sahapara and adjoining area of Jateswar PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000539/2021-2022 | 3191/ALD | 28/03/2022 | 27/05/2022 | AASHIRBAD ENTERPRISE | 12.35 | 0 | 0 | 78
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) | SM/07057 | Retrofitting | Construction of 500cum OHR for Augmentation of Jateswar Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000409/2021-2022 | 2525/ALD | 11/02/2022 | 10/08/2022 | ASHIT KUMAR SINGHA | 91.76 | 0 | 0 | 80
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) | SM/07057 | Retrofitting | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 25/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 25 | 4.97 | 100
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) | SM/07057 | Retrofitting | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Alipurduar Sub Division,Birpara Sub Division,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000556/2021-2022 | 855/ALD | 31/08/2021 | 30/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 3.2 | 0.12 | 0
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) | SM/07057 | Retrofitting | Laying of UPVC/DI/MS/CI distribution pipe line for gap filling and FHTC connection for Beltali Road and adjoining area of Jateswar PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000026/2022-2023 | 24/ALD | 01/04/2022 | 31/05/2022 | AASHIRBAD ENTERPRISE | 12.35 | 0 | 0 | 80
8 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) | SM/07057 | Retrofitting | Construction of roof truss, field development and other allied works at Headwork site of Old Jaigaon WSS under Alipurduar Division, PHE Dte. | Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Kalchini Block | ORD/000393/2021-2022 | 2307/ALD | 25/01/2022 | 24/02/2022 | DILIP MAHATO | 4.17 | 0 | 0 | 75
9 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) | SM/07057 | Retrofitting | Extension of Distribution line with UPVC pipe line near Narendra Nath Sishu Siksha Kendra under Jateswar Water Supply Scheme under Alipurduar Division,PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000134/2020-2021 | 880/ALD | 14/10/2020 | 13/11/2020 | NARAYAN CHANDRA SAHA | 2.02 | 3.71 | 183.52 | 0
10 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) | SM/07057 | Retrofitting | Providing House connection for JATESWAR water supply scheme at FALAKATA Block under Alipuduar Division, P.H.E. Dte. PART-1 |  |  | ORD/000155/2020-2021 | 867/ALD | 14/10/2020 | 13/11/2020 | PARAMJYOTI ENTERPRISE | 4.93 | 9.87 | 200 | 0
11 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) | SM/07057 | Retrofitting | Providing House connection for JATESWAR water supply scheme at FALAKATA Block under Alipuduar Division, P.H.E. Dte. PART-2 |  |  | ORD/000156/2020-2021 | 868/ALD | 14/10/2020 | 13/11/2020 | NARAYAN CHANDRA SAHA & SONS | 4.93 | 9.87 | 200 | 0
12 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) | SM/07057 | Retrofitting | Laying of DI/MS/HDPE pipe line and providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-II) | Birpara A.E | Birpara Sub Division | ORD/000320/2020-2021 | 1453/ALD | 25/01/2021 | 11/03/2021 | PRAMESH LAMA | 33.97 | 5.88 | 17.3 | 100
13 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) | SM/07057 | Retrofitting | Laying of distribution of UPVC/DI/GI pipeline including FHTC for JATESWAR PWSS under Alipurduar Division, PHE DTE. PART-I | Birpara A.E | Alipurduar Sub Division | ORD/000467/2021-2022 | 2812/ALD | 28/02/2022 | 29/04/2022 | SOUVIK ROY PALADHI | 98.49 | 0.03 | 0.04 | 63
14 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) | SM/07057 | Retrofitting | Laying of distribution of UPVC/DI/GI pipeline including FHTC for JATESWAR PWSS under Alipurduar Division, PHE DTE. PART-II | Birpara A.E | Alipurduar Sub Division | ORD/000450/2021-2022 | 2747/ALD | 24/02/2022 | 25/04/2022 | TAPASH DAS | 49.62 | 8.38 | 16.88 | 59
Total | [13 empty] | 3449.99 | 127.84 | 3.71