## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-2) | SM/07058 | Retrofitting | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under BAKLA PWSS, Block- Alipurduar-II, Dist-Alipurduar. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000271/2020-2021 | 1283/ALD | 05/01/2021 | 06/03/2021 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 45.19 | 0 | 0 | 74
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-2) | SM/07058 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Bakla WSS under Alipurduar Division, PHE Dte. Part-6 | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000352/2021-2022 | 2151/ALD | 06/01/2022 | 05/02/2022 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 5 | 0 | 0 | 73
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-2) | SM/07058 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Bakla WSS under Alipurduar Division, PHE Dte. Part-5 | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000351/2021-2022 | 2150/ALD | 06/01/2022 | 05/02/2022 | SHIB RATAN BHOWMIK | 4.99 | 0 | 0 | 73
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-2) | SM/07058 | Retrofitting | Restoration of laying distribution system of Totpara PWSS by replacing of damaged AC pipeline with UPVC and DI pipeline including interconnection with Bakla Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,RWS Alipurduar - II Block | ORD/000227/2021-2022 | 1573/ALD | 22/11/2021 | 22/03/2022 | HARIDAS GHOSH | 55.38 | 0 | 0 | 100
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-2) | SM/07058 | Retrofitting | Hiring of Diesel vehicle maxi cab (at least 7 seater) for Executive Engineer, Alipurduar Division.(01.09.2020 to 31.03.2021) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000191/2020-2021 | 600/ALD | 31/08/2020 | 31/03/2021 | APSARI BHOWMICK | 1.25 | 0 | 0 | 0
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-2) | SM/07058 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Bakla PWSS Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000444/2021-2022 | 2753/ALD | 24/02/2022 | 08/06/2025 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 43.78 | 0 | 0 | 43
Total | [13 empty] | 155.59 | 0 | 0