## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) | SM/07062 | Retrofitting | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Kamakhyaguri PWSS, Kumargram Block under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000370/2021-2022 | 2289/ALD | 24/01/2022 | 25/03/2022 | GOUTAM KUMAR DAS | 27.39 | 0 | 0 | 93
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) | SM/07062 | Retrofitting | Providing House connection for KAMAKHYAGURI water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000149/2020-2021 | 861/ALD | 14/10/2020 | 13/11/2020 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 4.94 | 0 | 0 | 98
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) | SM/07062 | Retrofitting | Restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipeline of Uttar Kamakhyaguri WSS under Alipurduar Division, PHE Dte.(Part-A) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000167/2021-2022 | 1306/ALD | 05/10/2021 | 04/12/2021 | GOUTAM KUMAR DAS | 25.34 | 0 | 0 | 74
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) | SM/07062 | Retrofitting | Restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipeline and Providing House Connection of Uttar Kamakhyaguri Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000226/2021-2022 | 1574/ALD | 22/11/2021 | 21/01/2022 | M/S PALIT ENTERPRISE | 48.63 | 0 | 0 | 78
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) | SM/07062 | Retrofitting | Restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipeline of Uttar Kamakhyaguri WSS under Alipurduar Division, PHE Dte.(Part-A) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000180/2021-2022 | 1307/ALD | 05/10/2021 | 04/12/2021 | TAPASH DAS | 25.34 | 0 | 0 | 76
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) | SM/07062 | Retrofitting | Construction of Pump House ,Boundary Wall and laying distribution system for Uttar Kamkhyaguri Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000424/2021-2022 | 2608/ALD | 17/02/2022 | 18/05/2022 | GOUTAM KUMAR DAS | 90.8 | 0 | 0 | 74
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) | SM/07062 | Retrofitting | Providing House connection for KAMAKHYAGURI water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-III | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000209/2020-2021 | 1163/ALD | 15/12/2020 | 13/02/2021 | TAPASH DAS | 19.94 | 4.43 | 22.2 | 77
8 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) | SM/07062 | Retrofitting | Providing FHTC of Uttar Kamakhyaguri WSS under Alipurduar Division, PHE Dte. (Part-4) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000162/2021-2022 | 1304/ALD | 05/10/2021 | 04/12/2021 | DULAL MAJUMDER | 34.38 | 0 | 0 | 76
9 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) | SM/07062 | Retrofitting | Construction of 400cum OHR for Augmentation of Uttar Kamakhyaguri Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000412/2021-2022 | 2580/ALD | 17/02/2022 | 16/08/2022 | DILIP MAHATO | 77.31 | 0 | 0 | 74
10 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) | SM/07062 | Retrofitting | Preparation of Augmentation D.P.R after investigation For Bhatibari W/S scheme under Alipurduar Division. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000110/2021-2022 | 913/ALD | 06/09/2021 | 06/10/2021 | BHAGWATI BHUJEL | 2.62 | 2.62 | 100 | 0
Total | [13 empty] | 356.69 | 7.05 | 1.98