## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-2) | SM/07063 | Retrofitting | Providing House connection for FALAKATA AUG. piped water supply scheme (Subhaspally area, right side of NH) under Alipuduar Division, P.H.E. Dte. Part-5 | Alipurduar Sadar Sub Division,HQ-A.E | RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000248/2020-2021 | 1248/ALD | 28/12/2020 | 26/02/2021 | BILTU DAS | 29.59 | 0 | 0 | 82
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-2) | SM/07063 | Retrofitting | "Providing House Connection (FHTC) at Salsalabari WSS under Alipurduar Division, PHE Dte. Part-5" | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000339/2021-2022 | 2115/ALD | 05/01/2022 | 04/02/2022 | MATRI ENTERPRISE | 5.04 | 5.04 | 100 | 96.5
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-2) | SM/07063 | Retrofitting | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 25/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 0 | 0 | 100
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-2) | SM/07063 | Retrofitting | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Alipurduar Sub Division,Birpara Sub Division,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000556/2021-2022 | 855/ALD | 31/08/2021 | 30/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 0 | 0 | 0
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-2) | SM/07063 | Retrofitting | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under SALSALABARI PWSS, Block- Alipurduar-II, Dist-Alipurduar. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000267/2020-2021 | 1279/ALD | 05/01/2021 | 06/03/2021 | MATRI ENTERPRISE | 45.43 | 28.41 | 62.55 | 97
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-2) | SM/07063 | Retrofitting | Providing House connection for BAROBISHA ZONE- III water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division,HQ-A.E | Alipurduar Sub Division,RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000148/2020-2021 | 860/ALD | 14/10/2020 | 13/11/2020 | AKANSHA COMMERCIAL PRIVATE LTD. | 4.98 | 0 | 0 | 78.5
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-2) | SM/07063 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Salsalabari Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000469/2021-2022 | 2765/ALD | 25/02/2022 | 26/04/2022 | NARENDRA BHADANI. | 47.7 | 25.54 | 53.54 | 97
8 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-2) | SM/07063 | Retrofitting | Extension and replacement of damaged pipeline and providing house connection at Salsalabari area under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,RWS Alipurduar - II Block | ORD/000082/2021-2022 | 978/ALD | 13/09/2021 | 11/01/2022 | HARIDAS GHOSH | 17.44 | 4.48 | 25.67 | 100
Total | [13 empty] | 3243.42 | 63.47 | 1.96