## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Hantupara Tea Garden Piped Water Supply Scheme | SM/07064 | Retrofitting | Repair of Gate, Drainage System & Rest Shed infront of Office cum Godown building at H/W Site of Birpara WSS under Alipuduar Division, P.H.E. Dte. |  |  | ORD/000129/2020-2021 | 875/ALD | 14/10/2020 | 28/11/2020 | DILIP MAHATO | 4.97 | 9.61 | 193.14 | 0
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Hantupara Tea Garden Piped Water Supply Scheme | SM/07064 | Retrofitting | PROVIDING HOUSE CONNECTION FOR DIMDIMA Z-II PWSS AT MADARIHAT-BIRPARA BLOCK UNDER ALIPURDUAR DIVISION, PHE DTE. PART-2 | Birpara A.E | Alipurduar Sub Division | ORD/000195/2020-2021 | 1026/ALD | 18/11/2020 | 17/01/2021 | ASHIT KUMAR SINGHA | 19.61 | 30.28 | 154.44 | 0
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Hantupara Tea Garden Piped Water Supply Scheme | SM/07064 | Retrofitting | House connection Providing for MAKRAPARA TG PWSS at MADARIHAT-BIRPARA Block under Alipurduar Division PHED . | Birpara A.E | Birpara Sub Division | ORD/000091/2020-2021 | 697/ALD | 16/09/2020 | 14/01/2021 | DILIP MAHATO | 25.73 | 15.24 | 59.25 | 0
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Hantupara Tea Garden Piped Water Supply Scheme | SM/07064 | Retrofitting | Laying of DI/MS/HDPE pipeline for the Hantapara WSS (Jamtala Area) under Alipurduar Division, PHE Dte. | Alipurduar RWS,Birpara A.E | Birpara Sub Division,RWS Madarihat - Birpara Block | ORD/000323/2020-2021 | 1455/ALD | 25/01/2021 | 11/03/2021 | M/S SURAJIT DEY & CO | 8.92 | 7.79 | 87.3 | 98
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Hantupara Tea Garden Piped Water Supply Scheme | SM/07064 | Retrofitting | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under PURBA CHEPANI PWSS, Block- Alipurduar-II, Dist-Alipurduar. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000269/2020-2021 | 1281/ALD | 05/01/2021 | 06/03/2021 | MATRI ENTERPRISE | 37.84 | 26.98 | 71.28 | 94
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Hantupara Tea Garden Piped Water Supply Scheme | SM/07064 | Retrofitting | Laying of DI/MS/HDPE pipe line from Nepali School (H.S.) towards Birpara Boro Houda WSS providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-I) |  |  | VCH/000942/2020-2021 | 570/20-21 | 26/03/2021 | 26/03/2021 | GOUTAM KUMAR DAS | 15 | 0 | 0 | 0
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Hantupara Tea Garden Piped Water Supply Scheme | SM/07064 | Retrofitting | Laying of HDPE pipeline for Hantapara Topline under Hatapara WSS within Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000429/2021-2022 | 2627/ALD | 18/02/2022 | 19/04/2022 | DILIP MAHATO | 16.19 | 0 | 0 | 69
8 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Hantupara Tea Garden Piped Water Supply Scheme | SM/07064 | Retrofitting | Road crossing (by NP3 Hume pipe) at Dhupguri Road under under Zone-II of augmentation of Falakata WSS and infront of bhutnirghat WSS due to widening of PWD Road under Alipurduar Division, PHE Dte. (3 nos) | Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Kalchini Block | ORD/000394/2021-2022 | 2308/ALD | 25/01/2022 | 24/02/2022 | ASSOCIATE CONSTRUCTION COMPANY | 2.49 | 0 | 0 | 89
Total | [13 empty] | 130.74 | 89.89 | 68.76