## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-1) | SM/07068 | Retrofitting | Balance part of laying of HDPE/DI pipe line alongwith construction of RCC piller at different area of DIMDIMA TG under ALIPURDUAR Division, PHED. | Birpara A.E | Birpara Sub Division | ORD/000069/2020-2021 | 622/ALD | 03/09/2020 | 01/01/2021 | M/S SSB CONSTRUCTION | 34.11 | 0 | 0 | 88
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-1) | SM/07068 | Retrofitting | Laying of DI/MS/HDPE pipe line from Nepali School (H.S.) towards Birpara Boro Houda WSS providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-I) | Birpara A.E | Birpara Sub Division | ORD/000319/2020-2021 | 1452/ALD | 25/01/2021 | 11/03/2021 | GOUTAM KUMAR DAS | 43.73 | 0 | 0 | 87
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-1) | SM/07068 | Retrofitting | Laying of DI/MS/HDPE pipe line and providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-II) | Birpara A.E | Birpara Sub Division | ORD/000320/2020-2021 | 1453/ALD | 25/01/2021 | 11/03/2021 | PRAMESH LAMA | 33.97 | 0 | 0 | 100
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-1) | SM/07068 | Retrofitting | Extension of pipeline for implementation of FHTC at Bandapani TG Area attached with Nangdala TG (for Dimdima PWSS Zone-II) under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000523/2021-2022 | 2997/ALD | 15/03/2022 | 14/05/2022 | DILIP MAHATO | 15.04 | 0 | 0 | 87
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-1) | SM/07068 | Retrofitting | Laying of DI/MS/HDPE Pipe line for the Dimdima Zone-II and Nangdala Extension, Dimdima WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000357/2020-2021 | 1795/ALD | 22/02/2021 | 23/04/2021 | DILIP MAHATO | 31.27 | 0 | 0 | 87
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-1) | SM/07068 | Retrofitting | Quotation for New Connection for Dangapara, Sishujumra |  |  | BILL/00107/2022-2023 | 445/22-23/PFMS | 21/01/2023 | 21/01/2023 | WBSEDCL | 0.1 | 0 | 0 | 0
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-1) | SM/07068 | Retrofitting | Laying of UPVC pipeline and Tube well Boring by Reverse Rotary method of drilling for BHUTNIRGHAT Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Birpara A.E | Alipurduar Sub Division | ORD/000380/2021-2022 | 2380/ALD | 31/01/2022 | 01/04/2022 | DILIP MAHATO | 95.15 | 0 | 0 | 97
8 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-1) | SM/07068 | Retrofitting | Protective and Decorative Acrylic exterior paint on existing 350 cum OHR at Dimdima of Birpara Sub-Division under Alipurduar Division, P.H.E.Dte. (SM/07068) | Birpara A.E | RWS Falakata Block | ORD/000507/2023-2024 | 825/ALD | 14/03/2024 | 13/05/2024 | BHAGWATI BHUJEL | 1.96 | 0 | 0 | 10
Total | [13 empty] | 255.34 | 0 | 0