## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-2) | SM/07121 | Retrofitting | Laying of Distribution Line (HDPE and DI) for retrofitting of FHTC for BIRPARA WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000360/2020-2021 | 1754/ALD | 19/02/2021 | 05/04/2021 | BILTU DAS | 47.98 | 3.97 | 8.27 | 61
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-2) | SM/07121 | Retrofitting | Extension and replacement of damaged pipeline and providing FHTC at Alipurduar Birpara Bazar Chowpathi and surrounding area under Birpara PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000178/2021-2022 | 1308/ALD | 05/10/2021 | 04/12/2021 | DAS CONSTRUCTION | 43.41 | 23.31 | 53.71 | 99
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-2) | SM/07121 | Retrofitting | Repairing of office Quarter and construction of attached toilet for Assistant Engineer Chamber of Birpara Sub-Division Office under Alipurduar Division PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000284/2021-2022 | 1853/ALD | 13/12/2021 | 27/01/2022 | DAS ENTERPRISE | 4.91 | 0 | 0 | 97
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-2) | SM/07121 | Retrofitting | Providing House Connection (FHTC) at Birpara (APD) WSS under Alipurduar Division, PHE Dte. Part-7 | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000342/2021-2022 | 2118/ALD | 05/01/2022 | 04/02/2022 | DAS CONSTRUCTION | 5 | 0 | 0 | 96
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-2) | SM/07121 | Retrofitting | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Alipurduar ITI College area under Birpara PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000327/2021-2022 | 2200/ALD | 11/01/2022 | 12/03/2022 | DAS CONSTRUCTION | 42.69 | 30.1 | 70.52 | 98
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-2) | SM/07121 | Retrofitting | Dismantling Concrete road and re -casting the same for providing FHTC at different area of BIRPARA (APD) PWSS AND Alipurduar - I Block under Alipurduar Division , PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000078/2022-2023 | 441/ALD | 13/05/2022 | 12/06/2022 | R.K.CONSTRUCTION | 4.96 | 4.95 | 99.8 | 71
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-2) | SM/07121 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Birpara PWSS (APD) Under Alipurduar Division, PHE DTE. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000443/2021-2022 | 2751/ALD | 24/02/2022 | 25/04/2022 | R.K.CONSTRUCTION | 31.74 | 17.01 | 53.58 | 60
Total | [13 empty] | 180.68 | 79.34 | 43.91