## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) | SM/07123 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-II) Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000474/2021-2022 | 2764/ALD | 25/02/2022 | 26/04/2022 | TAPAN CHANDA | 50.32 | 4.02 | 7.98 | 60
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) | SM/07123 | Retrofitting | Restoration of laying distribution system by replacing of damaged AC pipeline with DI and UPVC pipe of Kumargram WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000084/2021-2022 | 980/ALD | 13/09/2021 | 12/11/2021 | DILIP MAHATO | 48.35 | 39.41 | 81.51 | 68
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) | SM/07123 | Retrofitting | Laying of UPVC & DI (with pillar) pipeline for Barobisha Zone-III Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000170/2021-2022 | 1320/ALD | 05/10/2021 | 04/12/2021 | AKANSHA COMMERCIAL PRIVATE LTD. | 79.02 | 6.06 | 7.67 | 66
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) | SM/07123 | Retrofitting | Laying of UPVC and DI (with pillar) pipeline Barobisa Zone-III Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000225/2021-2022 | 1575/ALD | 22/11/2021 | 20/02/2022 | TAPAN CHANDA | 75.74 | 30.67 | 40.49 | 69
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) | SM/07123 | Retrofitting | Providing House connection for BAROBISHA ZONE- III water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division,HQ-A.E | Alipurduar Sub Division,RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000148/2020-2021 | 860/ALD | 14/10/2020 | 13/11/2020 | AKANSHA COMMERCIAL PRIVATE LTD. | 4.98 | 2.5 | 50.08 | 79
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) | SM/07123 | Retrofitting | Distribution line for Barobisha (Zone-III) water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000109/2020-2021 | 730/ALD | 22/09/2020 | 06/11/2020 | TAPAN CHANDA | 5 | 0.74 | 14.7 | 0
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) | SM/07123 | Retrofitting | Distribution line for Barobisha (Zone-III) water Supply Scheme under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000108/2020-2021 | 729/ALD | 22/09/2020 | 06/11/2020 | TAPAN CHANDA | 4.97 | 9.27 | 186.57 | 0
8 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) | SM/07123 | Retrofitting | Providing House connection for BAROBISHA ZONE- I water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte.(PART-2) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000167/2020-2021 | 911/ALD | 16/10/2020 | 15/11/2020 | TAPAN CHANDA | 4.98 | 9.97 | 200 | 0
9 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) | SM/07123 | Retrofitting | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under PURBA CHEPANI PWSS, Block- Alipurduar-II, Dist-Alipurduar. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000269/2020-2021 | 1281/ALD | 05/01/2021 | 06/03/2021 | MATRI ENTERPRISE | 37.84 | 6.95 | 18.36 | 94
10 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) | SM/07123 | Retrofitting | Providing House connection for JAIGAON piped water supply scheme (Old scheme Area) under Alipuduar Division, P.H.E. Dte. Part-1 | HQ-A.E | RWS Kalchini Block | ORD/000317/2020-2021 | 1449/ALD | 25/01/2021 | 11/03/2021 | MAHENDRA CHHETRI | 43.86 | 2.86 | 6.51 | 67
Total | [13 empty] | 355.07 | 112.42 | 31.66