## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-2) | SM/07125 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-II) Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000474/2021-2022 | 2764/ALD | 25/02/2022 | 26/04/2022 | TAPAN CHANDA | 50.32 | 0 | 0 | 59.71
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-2) | SM/07125 | Retrofitting | Laying Distribution line of UPVC, DI Pipe (with pillar) and cons. Of new toilet, repairing of pump house (2nd site), Land Development at Barobisa Zone-I Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000169/2021-2022 | 1319/ALD | 05/10/2021 | 04/12/2021 | M/S SURAJIT DEY & CO | 81.49 | 0 | 0 | 69.5
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-2) | SM/07125 | Retrofitting | Extension of Distribution pipe line (Barman Para and Beltala) with UPVC Connection of BAROBISA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000555/2021-2022 | 3082/ALD | 22/03/2022 | 21/05/2022 | AASHIRBAD ENTERPRISE | 13.46 | 0 | 0 | 69.67
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-2) | SM/07125 | Retrofitting | Laying of UPVC and DI (with pillar) pipeline Barobisa Zone-III Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000225/2021-2022 | 1575/ALD | 22/11/2021 | 20/02/2022 | TAPAN CHANDA | 75.74 | 0 | 0 | 69
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-2) | SM/07125 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-I) Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000473/2021-2022 | 2763/ALD | 25/02/2022 | 26/04/2022 | TAPAN CHANDA | 50.32 | 0 | 0 | 69
Total | [13 empty] | 271.33 | 0 | 0