## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-2) | SM/07136 | Retrofitting | Extension/Merging of Distribution pipeline (UPVC/DI/MS/CI) from Paschim Khairbari WSS to Uttar Sishubari WSS and others misc. work under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000264/2020-2021 | 1255/ALD | 28/12/2020 | 26/02/2021 | MITHUN DAS | 45.83 | 0 | 0 | 80
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-2) | SM/07136 | Retrofitting | Providing House connection for PASCHIM KHAYERBARI water supply scheme at Madarihat-Birpara Block under Alipuduar Division, P.H.E. Dte. Part-II | Birpara A.E | Birpara Sub Division | ORD/000219/2020-2021 | 1170/ALD | 15/12/2020 | 13/02/2021 | MITHUN DAS | 29.88 | 0 | 0 | 91
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-2) | SM/07136 | Retrofitting | Withdrawing and relaying and laying of UPVC/DI/MS Distribution pipe line and other misc. work for retrofitting of Paschim Khayerbari WSS under Birpara Sub-Division, Alipurduar Division, PHE Dte.(Part-II) | Birpara A.E | Birpara Sub Division | ORD/000231/2020-2021 | 1177/ALD | 15/12/2020 | 13/02/2021 | MATARA CONSTRUCTION CO | 45.1 | 0 | 0 | 92
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-2) | SM/07136 | Retrofitting | Restotation of pipeline by providing steel piles for JJM at Paschim Khairbari WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000235/2022-2023 | 1227/ALD | 10/08/2022 | 09/09/2022 | MATARA CONSTRUCTION CO | 1.3 | 0 | 0 | 62
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-2) | SM/07136 | Retrofitting | Withdrawing and relaying and laying of UPVC/DI/MS/CI Distribution pipe line and other misc work for retrofitting of PASCHIM KHAYERBAR WSS under Birpara Sub-Division, Alipurduar Division,PHE Dte. Part-I | Birpara A.E | Alipurduar Sub Division,Birpara Sub Division | ORD/000236/2020-2021 | 1181/ALD | 15/12/2020 | 13/02/2021 | SANJIT SAHA | 43.88 | 0 | 0 | 100
Total | [13 empty] | 165.98 | 0 | 0