## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-1) | SM/07174 | Retrofitting | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under BAKLA PWSS, Block- Alipurduar-II, Dist-Alipurduar. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000271/2020-2021 | 1283/ALD | 05/01/2021 | 06/03/2021 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 45.19 | 56.51 | 125.04 | 74
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-1) | SM/07174 | Retrofitting | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Alipurduar Sub Division,Birpara Sub Division,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000556/2021-2022 | 855/ALD | 31/08/2021 | 30/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 5 | 0.19 | 0
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-1) | SM/07174 | Retrofitting | Providing House connection for Bakla Piped water supply scheme at Alipurduar-II Block under Alipuduar Division, P.H.E. Dte. |  |  | ORD/000107/2020-2021 | 728/ALD | 22/09/2020 | 22/10/2020 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 4.98 | 9.96 | 200 | 0
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-1) | SM/07174 | Retrofitting | "Providing House connection for Bakla water supply scheme at Alipurduar-II Block under Alipuduar Division, P.H.E. Dte. (Part-II)" | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000227/2020-2021 | 1137/ALD | 10/12/2020 | 09/01/2021 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 4.98 | 9.96 | 200 | 0
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-1) | SM/07174 | Retrofitting | Preparation of Augmentation D.P.R after investigation For SamuktalaW/S scheme under Alipurduar Division. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000112/2021-2022 | 915/ALD | 06/09/2021 | 06/10/2021 | BHAGWATI BHUJEL | 2.81 | 5.61 | 200 | 0
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-1) | SM/07174 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Bakla PWSS Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000444/2021-2022 | 2753/ALD | 24/02/2022 | 08/06/2025 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 43.78 | 0 | 0 | 43
Total | [13 empty] | 2692.4 | 87.05 | 3.23