## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) | SM/07176 | Retrofitting | Withdrawing and relaying and laying of UPVC/DI/MS/CI Distribution pipe line for retrofitting and providing functional household tap connection (FHTC) in connection with Jaldhara Jal Sapno of Chhoto Salkumar PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000298/2020-2021 | 1378/ALD | 19/01/2021 | 05/03/2021 | M/S PALIT ENTERPRISE | 43.75 | 0 | 0 | 68
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) | SM/07176 | Retrofitting | Laying Distribution line of UPVC & Di Pipe , with providing FHTC Connection for the Salkumar Water Supply Scheme Under Alipurduar Division PHE DTE (PART-A) | Birpara A.E | Birpara Sub Division | ORD/000133/2021-2022 | 1243/ALD | 27/09/2021 | 26/11/2021 | TAPASH DAS | 25.25 | 4.11 | 16.28 | 78
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) | SM/07176 | Retrofitting | Laying Distribution line of UPVC and DI with providing FHTC Connection for the Salkumar Water Supply Scheme Area under Alipurduar Division, PHE Dte. | Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Kalchini Block | ORD/000197/2021-2022 | 1318/ALD | 05/10/2021 | 04/12/2021 | TAPASH KUMAR BHOWMICK | 35.38 | 3.16 | 8.93 | 85
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) | SM/07176 | Retrofitting | Laying Distribution line of UPVC and DI with providing FHTC Connection for the Salkumar and Munshipara Water Supply Scheme Area under Alipurduar Division, PHE Dte. | Alipurduar RWS,Birpara A.E | Birpara Sub Division,RWS Alipurduar - I Block | ORD/000196/2021-2022 | 1317/ALD | 05/10/2021 | 04/12/2021 | DILIP MAHATO | 58.07 | 0 | 0 | 68
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) | SM/07176 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for AWC and school & others) at Chhoto Salkumar WSS under Alipurduar Division, PHE Dte.Part-5 | Birpara A.E | Birpara Sub Division | ORD/000389/2021-2022 | 2303/ALD | 25/01/2022 | 24/02/2022 | AASHIRBAD ENTERPRISE | 5.03 | 3.99 | 79.31 | 61.33
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) | SM/07176 | Retrofitting | Laying distribution line of UPVC and providing FHTC connection for Chhoto Salkumar Water Supply Scheme Area under Alipurduar Division, P.H.E. Dte. | Birpara A.E | Birpara Sub Division | ORD/000397/2021-2022 | 2311/ALD | 25/01/2022 | 11/03/2022 | AASHIRBAD ENTERPRISE | 5.01 | 0 | 0 | 61.67
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) | SM/07176 | Retrofitting | Construction of 300 m3 capacity RCC Over Head Reservoir For SALKUMARHAT PWSS under Alipurduar Division PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000080/2020-2021 | 632/ALD | 03/09/2020 | 02/12/2020 | HARIDAS GHOSH | 63.58 | 0 | 0 | 79.67
8 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) | SM/07176 | Retrofitting | Providing House connection for CHOTO SALKUMAR water supply scheme at Falakata Block under Alipuduar Division, P.H.E. Dte. Part-III | Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Kalchini Block | ORD/000218/2020-2021 | 1169/ALD | 15/12/2020 | 13/02/2021 | SASANKA ROY | 29.9 | 5.13 | 17.14 | 69.5
9 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) | SM/07176 | Retrofitting | Repairing & renovation of Pump House, Pathway, Boundary wall (2nd site) & laying DI Pipe line at Salkumarhat WSS under Alipurduar Division PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000099/2021-2022 | 898/ALD | 03/09/2021 | 18/10/2021 | TAPASH DAS | 4.82 | 0 | 0 | 62
10 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) | SM/07176 | Retrofitting | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of CHHOTO SALKUMAR Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Birpara A.E | Birpara Sub Division | ORD/000318/2021-2022 | 2194/ALD | 11/01/2022 | 11/04/2022 | KAJAL KUMAR DE | 21.92 | 5.05 | 23.04 | 46
11 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) | SM/07176 | Retrofitting | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 25/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 0 | 0 | 100
12 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) | SM/07176 | Retrofitting | Providing FHTC at surrounding area of Chhoto Salkumar Under Alipurduar Division, PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000445/2021-2022 | 2754/ALD | 24/02/2022 | 25/04/2022 | KAJAL KUMAR DE | 34.67 | 7.95 | 22.94 | 45
13 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) | SM/07176 | Retrofitting | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Alipurduar Sub Division,Birpara Sub Division,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000556/2021-2022 | 855/ALD | 31/08/2021 | 30/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 0 | 0 | 0
14 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) | SM/07176 | Retrofitting | Laying of UPVC/DI/MS/CI distribution pipeline for Gap filling of Chhoto Salkumar PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000577/2021-2022 | 3132/ALD | 25/03/2022 | 24/04/2022 | PRITAM DAS | 5.04 | 4.19 | 83.3 | 70.5
Total | [13 empty] | 3425.66 | 33.59 | 0.98