## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-1) | SM/07182 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Loknathpur WSS under Alipurduar Division, PHE Dte. Part-5 | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000282/2021-2022 | 1851/ALD | 13/12/2021 | 12/01/2022 | GOUTAM KUMAR DAS | 5.04 | 0 | 0 | 63
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-1) | SM/07182 | Retrofitting | Retrofitting of pipeline etc. for the 'Jal Sapna' programme (FHTC for every house hold) under Loknathpur PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000368/2021-2022 | 2296/ALD | 24/01/2022 | 25/03/2022 | GOUTAM KUMAR DAS | 45.8 | 0 | 0 | 94
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-1) | SM/07182 | Retrofitting | Laying of distribution pipeline with DI and UPVC pipes for interconnection of Dhaolajhora PWSS with Loknathpur PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000540/2021-2022 | 3192/ALD | 28/03/2022 | 27/05/2022 | GOUTAM KUMAR DAS | 49.89 | 0 | 0 | 81
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-1) | SM/07182 | Retrofitting | Construction of boundary wall at 2nd TW site at Loknathpur WSS under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000333/2021-2022 | 2109/ALD | 05/01/2022 | 19/02/2022 | GOUTAM KUMAR DAS | 4.67 | 0 | 0 | 62
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-1) | SM/07182 | Retrofitting | Providing House connection for LOKNATHPUR water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. |  |  | ORD/000152/2020-2021 | 864/ALD | 14/10/2020 | 13/11/2020 | MATARA CONSTRUCTION CO | 4.98 | 4.98 | 100 | 0
Total | [13 empty] | 110.39 | 4.98 | 4.51