## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) | SM/07185 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-II) Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000474/2021-2022 | 2764/ALD | 25/02/2022 | 26/04/2022 | TAPAN CHANDA | 50.32 | 0 | 0 | 59.71
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) | SM/07185 | Retrofitting | Restoration of laying distribution system by replacing of damaged AC pipeline with DI and UPVC pipe of Kumargram WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000084/2021-2022 | 980/ALD | 13/09/2021 | 12/11/2021 | DILIP MAHATO | 48.35 | 0 | 0 | 68.33
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) | SM/07185 | Retrofitting | Laying Distribution line of UPVC, DI Pipe (with pillar) and cons. Of new toilet, repairing of pump house (2nd site), Land Development at Barobisa Zone-I Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000169/2021-2022 | 1319/ALD | 05/10/2021 | 04/12/2021 | M/S SURAJIT DEY & CO | 81.49 | 0 | 0 | 69.5
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) | SM/07185 | Retrofitting | Extension of Distribution pipe line (Barman Para and Beltala) with UPVC Connection of BAROBISA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000555/2021-2022 | 3082/ALD | 22/03/2022 | 21/05/2022 | AASHIRBAD ENTERPRISE | 13.46 | 0.05 | 0.35 | 69.67
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) | SM/07185 | Retrofitting | Providing House connection for BAROBISHA Zone-I water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-III | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000206/2020-2021 | 1160/ALD | 15/12/2020 | 13/02/2021 | M/S SURAJIT DEY & CO | 29.98 | 28.7 | 95.73 | 69
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) | SM/07185 | Retrofitting | Providing House connection for BAROBISHA Zone-III water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-II | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000208/2020-2021 | 1162/ALD | 15/12/2020 | 13/02/2021 | AKANSHA COMMERCIAL PRIVATE LTD. | 19.93 | 0 | 0 | 76.5
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) | SM/07185 | Retrofitting | Laying of DI Pipeline and other misc works related to barobisha Water Supply Scheme (Zone-I) under Alipurduar Division PHE Dte. |  |  | ORD/000397/2018-2019 | 32/ALD | 15/01/2019 |  | M/S SURAJIT DEY & CO | 40.7 | 5.6 | 13.75 | 0
8 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) | SM/07185 | Retrofitting | Providing House connection for BAROBISHA ZONE- II water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. |  |  | ORD/000143/2020-2021 | 859/ALD | 14/10/2020 | 13/11/2020 | AKANSHA COMMERCIAL PRIVATE LTD. | 4.98 | 4.98 | 100 | 0
9 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) | SM/07185 | Retrofitting | Preparation of Agumentation D.P.R after investigation For Kumargram W/Sscheme under Alipurduar Division. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000109/2021-2022 | 912/ALD | 06/09/2021 | 06/10/2021 | BHAGWATI BHUJEL | 2.77 | 0 | 0 | 0
10 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) | SM/07185 | Retrofitting | Providing House connection for BAROBISHA ZONE- II water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte.(PART-2) |  |  | ORD/000168/2020-2021 | 912/ALD | 16/10/2020 | 15/11/2020 | AKANSHA COMMERCIAL PRIVATE LTD. | 4.98 | 4.98 | 100 | 0
11 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) | SM/07185 | Retrofitting | Laying of rising main and delivery line connection, horizontal boring by HDD method with HDPE pipe, distribution gap filling with UPVC pipe and others allied works at Barobisha Zone-I PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000388/2023-2024 | 199/ALD | 16/01/2024 | 14/07/2024 | SREE MAA CONSTRUCTION | 22.86 | 0 | 0 | 20
Total | [13 empty] | 319.83 | 44.31 | 13.85