## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paitkapara T.G Piped Water Supply Scheme | SM/07190 | Retrofitting | Laying of DI / UPVC Pipeline & other Misc. works for Bhutiya Basti area at PAITKAPARA PWSS under Alipurduar Division PHED. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000071/2020-2021 | 625/ALD | 03/09/2020 | 01/01/2021 | DAS CONSTRUCTION | 16.33 | 0 | 0 | 99
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paitkapara T.G Piped Water Supply Scheme | SM/07190 | Retrofitting | Retrofitting work of pipeline of Madarihat PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000199/2021-2022 | 972/ALD | 13/09/2021 | 13/10/2021 | MS DEYS CONSTRUCTION | 4.99 | 0 | 0 | 99
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paitkapara T.G Piped Water Supply Scheme | SM/07190 | Retrofitting | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 25/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 0 | 0 | 100
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paitkapara T.G Piped Water Supply Scheme | SM/07190 | Retrofitting | Providing House connection for DHEKLAPARA PWSS at MADARIHAT-BIRPARA Block under Alipurduar Division PHED PART 1 | Birpara A.E | Birpara Sub Division | ORD/000082/2020-2021 | 634/ALD | 03/09/2020 | 02/12/2020 | DILIP MAHATO | 21.8 | 9.37 | 43 | 0
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paitkapara T.G Piped Water Supply Scheme | SM/07190 | Retrofitting | Laying of DI/MS/HDPE Distribution pipe line for the LANKAPARA WSS (TULSHIPARA TG) under Alipurduar Division, PHE Dte. Dist-Alipurduar. | Birpara A.E | Birpara Sub Division | ORD/000268/2020-2021 | 1280/ALD | 05/01/2021 | 06/03/2021 | UMWELT ENGINEER PVT. LTD. | 30.9 | 14.31 | 46.32 | 98
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paitkapara T.G Piped Water Supply Scheme | SM/07190 | Retrofitting | Extension and Replacement of damaged pipeline under Patlakhawa PWSS under Alipurduar Division, P.H.E. Dte.(Part-C) | Alipurduar RWS | Birpara Sub Division | ORD/000183/2020-2021 | 1008/ALD | 12/11/2020 | 11/01/2021 | JAI BHARAT COMMERCIAL CORPORATION | 14.4 | 8.61 | 59.82 | 100
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paitkapara T.G Piped Water Supply Scheme | SM/07190 | Retrofitting | Providing House connection for PURBA KATHALBARI water supply scheme at Alipurduar -I Block under Alipuduar Division, P.H.E. Dte. Part-II | Alipurduar RWS | Birpara Sub Division | ORD/000222/2020-2021 | 1173/ALD | 15/12/2020 | 13/02/2021 | MADHAB SAHA | 19.93 | 13.95 | 70 | 0
8 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paitkapara T.G Piped Water Supply Scheme | SM/07190 | Retrofitting | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of PAITKAPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar RWS | RWS Alipurduar - I Block,RWS Madarihat - Birpara Block | ORD/000296/2021-2022 | 1994/ALD | 27/12/2021 | 27/03/2022 | ANUP GUPTA | 20.99 | 0 | 0 | 80
Total | [13 empty] | 631.91 | 46.25 | 7.32