## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme | SM/07192 | Retrofitting | Repairing of old UPVC Pipeline, FHTC and other misc. works related to Dima PWSS & Madhu PWSS under Kalchini Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000214/2022-2023 | 1103/ALD | 29/07/2022 | 28/08/2022 | MADHAB SAHA | 1.79 | 0 | 0 | 95
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme | SM/07192 | Retrofitting | Providing House connection for Munshipara piped water supply scheme at Alipurduar -I Block under Alipuduar Division, P.H.E. Dte. |  |  | ORD/000101/2020-2021 | 722/ALD | 22/09/2020 | 22/10/2020 | TAPASH DAS | 4.98 | 4.98 | 100 | 0
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme | SM/07192 | Retrofitting | Construction of Soak well, Fencing and other works at Madhu TG PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | Birpara Sub Division | ORD/000039/2020-2021 | 516/ALD | 20/08/2020 | 19/10/2020 | TAPASH KUMAR BHOWMICK | 3.91 | 3.91 | 100.03 | 0
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme | SM/07192 | Retrofitting | Construction of Fire hydrant, parking area for water collecting vehicles, surface drain and other miscellaneous works for Madhu T.G. P/W/S/S, Under Alipurduar Division P.H.E. Dte. | HQ-A.E | Birpara Sub Division | ORD/000051/2020-2021 | 530/ALD | 20/08/2020 | 19/10/2020 | TAPASH KUMAR BHOWMICK | 5 | 5 | 99.97 | 0
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme | SM/07192 | Retrofitting | Withdrawing and relaying and laying of UPVC/DI/MS/CI Distribution pipe line and other misc. work for retrofitting of Mujnai PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000144/2020-2021 | 943/ALD | 19/10/2020 | 18/12/2020 | VEDATRAYEE AND CO | 29.81 | 28.55 | 95.77 | 92
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme | SM/07192 | Retrofitting | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under PURBA CHEPANI PWSS, Block- Alipurduar-II, Dist-Alipurduar. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000269/2020-2021 | 1281/ALD | 05/01/2021 | 06/03/2021 | MATRI ENTERPRISE | 37.84 | 1.4 | 3.7 | 94
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme | SM/07192 | Retrofitting | Extension of pipeline to Bharnabari TG area under Hasimara PWSS for providing at Kalchini Block under Alipurduar Division, P.H.E. Dte.(Part-B) |  |  | ORD/000185/2020-2021 | 1010/ALD | 12/11/2020 | 11/01/2021 | ASHIT KUMAR SINGHA | 39.34 | 22.12 | 56.22 | 0
8 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme | SM/07192 | Retrofitting | Fuel bill for the month of August 2021 |  |  | VCH/000570/2021-2022 | 121/21-22/PFMS | 08/09/2021 |  | SHIVAM SERVICE STATION | 0.22 | 0 | 0 | 0
Total | [13 empty] | 122.9 | 65.96 | 53.67