## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dima T.G Piped Water Supply Scheme | SM/07194 | Retrofitting | Laying of DI/MS/HDPE pipe line from Nepali School (H.S.) towards Birpara Boro Houda WSS providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-I) |  |  | VCH/000942/2020-2021 | 570/20-21 | 26/03/2021 |  | GOUTAM KUMAR DAS | 15 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dima T.G Piped Water Supply Scheme | SM/07194 | Retrofitting | Extension pipeline (HDPE) for providing FHTC at 28th and 29th mile busty area under Jainti Water Supply Scheme, Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,HQ-A.E | Alipurduar Sub Division,RWS Kalchini Block | ORD/000224/2021-2022 | 1576/ALD | 22/11/2021 | 21/01/2022 | DEBAJYOTI SUTRADHAR | 25.75 | 0.49 | 1.91 | 69
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dima T.G Piped Water Supply Scheme | SM/07194 | Retrofitting | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of DIMA TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar RWS,HQ-A.E | RWS Alipurduar - I Block,RWS Kalchini Block | ORD/000293/2021-2022 | 1991/ALD | 27/12/2021 | 27/03/2022 | GOBINDA BAGCHI | 20.87 | 2.89 | 13.83 | 72.14
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dima T.G Piped Water Supply Scheme | SM/07194 | Retrofitting | Distribution line for Barobisha (Zone-III) water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000109/2020-2021 | 730/ALD | 22/09/2020 | 06/11/2020 | TAPAN CHANDA | 5 | 4.6 | 92.02 | 0
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dima T.G Piped Water Supply Scheme | SM/07194 | Retrofitting | Providing House connection for PURBA KATHALBARI water supply scheme at ALIPURDUAR-I Block under Alipuduar Division, P.H.E. Dte. |  |  | ORD/000164/2020-2021 | 908/ALD | 16/10/2020 | 15/11/2020 | SREE MAA CONSTRUCTION & CO. | 4.98 | 3.45 | 69.19 | 0
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dima T.G Piped Water Supply Scheme | SM/07194 | Retrofitting | Providing House connection for UTTAR LATABARI piped water supply scheme under Alipuduar Division, P.H.E. Dte. Part-1 | HQ-A.E | Birpara Sub Division | ORD/000242/2020-2021 | 1244/ALD | 28/12/2020 | 26/02/2021 | SHIB RATAN BHOWMIK | 9.97 | 4.98 | 50 | 0
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dima T.G Piped Water Supply Scheme | SM/07194 | Retrofitting | Retrofitting of pipeline for UTTAR LATABARAI PWSS (Rabindranagar & surroundings) area at Kalchini Block under Alipurduar Division, PHE Dte. Part-A | HQ-A.E | RWS Kalchini Block | ORD/000273/2020-2021 | 1285/ALD | 05/01/2021 | 06/03/2021 | ASHOK SAPKOTA | 22.45 | 19.12 | 85.15 | 46
Total | [13 empty] | 104.03 | 35.53 | 34.15