## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti T.G Piped Water Supply Scheme | SM/07195 | Retrofitting | Extension pipeline (HDPE) for providing FHTC at 28th and 29th mile busty area under Jainti Water Supply Scheme, Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,HQ-A.E | Alipurduar Sub Division,RWS Kalchini Block | ORD/000224/2021-2022 | 1576/ALD | 22/11/2021 | 21/01/2022 | DEBAJYOTI SUTRADHAR | 25.75 | 6.6 | 25.63 | 69
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti T.G Piped Water Supply Scheme | SM/07195 | Retrofitting | Extension of pipeline for Jainti TG including connection from Reservoir-2 under Jainti TG Water Supply Scheme (Part-A). | Alipurduar Sadar Sub Division,HQ-A.E | Alipurduar Sub Division,RWS Kalchini Block | ORD/000123/2020-2021 | 795/ALD | 01/10/2020 | 30/11/2020 | CALCON CONSTRUCTIONS | 40.62 | 64.59 | 159.01 | 90
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti T.G Piped Water Supply Scheme | SM/07195 | Retrofitting | Laying of HDPE pipeline & other misc work related to Jayanti WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,HQ-A.E | Alipurduar Sub Division,RWS Kalchini Block | ORD/000354/2021-2022 | 2119/ALD | 05/01/2022 | 04/02/2022 | TAPASH KUMAR BHOWMICK | 4.28 | 3.87 | 90.32 | 71
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti T.G Piped Water Supply Scheme | SM/07195 | Retrofitting | Balance work of Jainty Rest Shed along with laying of delivery line from CWR of Jainti WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,HQ-A.E | Alipurduar Sub Division,RWS Kalchini Block | ORD/000431/2021-2022 | 2629/ALD | 18/02/2022 | 19/04/2022 | GHOSH & SAHA CONSTRUCTION | 13.4 | 8.21 | 61.25 | 64
Total | [13 empty] | 84.05 | 83.27 | 99.07