## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Gargenda T.G Piped Water Supply Scheme | SM/07197 | Retrofitting | Withdrawing & relaying & laying of pipeline and other misc. works for retrofitting of GARGENDA PWSS under Alipurduar Division PHED. | Birpara A.E | Birpara Sub Division | ORD/000092/2020-2021 | 698/ALD | 16/09/2020 | 14/01/2021 | M/S SSB CONSTRUCTION | 30.51 | 5.88 | 19.28 | 60
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Gargenda T.G Piped Water Supply Scheme | SM/07197 | Retrofitting | Construction of 300cum OHR for Augmentation of Jagijhora Barabak Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000414/2021-2022 | 2582/ALD | 17/02/2022 | 16/08/2022 | ASHIM KUMAR GHOSH | 63.76 | 12.04 | 18.88 | 43
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Gargenda T.G Piped Water Supply Scheme | SM/07197 | Retrofitting | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Alipurduar Sub Division,Birpara Sub Division,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000556/2021-2022 | 855/ALD | 31/08/2021 | 30/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 7.5 | 0.29 | 0
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Gargenda T.G Piped Water Supply Scheme | SM/07197 | Retrofitting | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Birpara Sub-Division, P.H.E. Dte.(from 01.01.2023 to 31.12.2023) | Birpara A.E | RWS Falakata Block | ORD/000417/2022-2023 | 2732/ALD | 30/12/2022 | 30/12/2023 | PARITOSH SUTRADHAR | 4.8 | 2.27 | 47.39 | 90
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Gargenda T.G Piped Water Supply Scheme | SM/07197 | Retrofitting | Construction of Pump House, Boundary Wall, laying distribution system and providing FHTC for BHUTNIRGHAT Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Birpara A.E | Alipurduar Sub Division | ORD/000379/2021-2022 | 2379/ALD | 31/01/2022 | 01/05/2022 | DILIP MAHATO | 92.34 | 2.32 | 2.51 | 98
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Gargenda T.G Piped Water Supply Scheme | SM/07197 | Retrofitting | Construction of Pump House, Boundary Wall, and Tube well Boring by ODEX-195 method of drilling including Rising main for GARGENDA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Birpara A.E | Alipurduar Sub Division | ORD/000400/2021-2022 | 2391/ALD | 31/01/2022 | 01/05/2022 | MITHUN DAS | 27.16 | 25.52 | 93.96 | 100
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Gargenda T.G Piped Water Supply Scheme | SM/07197 | Retrofitting | Laying of UPVC/DI pipe line at flank of Asian Highway Road at Jateswar to towards Kazali Bazar under Jateswar PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000454/2022-2023 | 2944/ALD | 20/01/2023 | 21/03/2023 | TAPASH DAS | 16.1 | 4.72 | 29.33 | 95
Total | [13 empty] | 2825.35 | 60.25 | 2.13