## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Mujnai T.G Piped Water Supply Scheme | SM/07198 | Retrofitting | Withdrawing and relaying and laying of UPVC/DI/MS/CI Distribution pipe line and other misc. work for retrofitting of Mujnai PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000144/2020-2021 | 943/ALD | 19/10/2020 | 18/12/2020 | VEDATRAYEE AND CO | 29.81 | 1.8 | 6.02 | 92
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Mujnai T.G Piped Water Supply Scheme | SM/07198 | Retrofitting | Supplying & laying of UPVC/DI/GI Distribution pipeline for Mujnai PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000103/2021-2022 | 902/ALD | 03/09/2021 | 03/10/2021 | DILIP MAHATO | 4.99 | 3.81 | 76.28 | 91
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Mujnai T.G Piped Water Supply Scheme | SM/07198 | Retrofitting | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 25/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 10 | 1.99 | 100
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Mujnai T.G Piped Water Supply Scheme | SM/07198 | Retrofitting | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Alipurduar Sub Division,Birpara Sub Division,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000556/2021-2022 | 855/ALD | 31/08/2021 | 30/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 25 | 0.97 | 0
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Mujnai T.G Piped Water Supply Scheme | SM/07198 | Retrofitting | CONS. OF BOUNDARY WALL (80 m), PUMPHOUSE( 1.Nos) ,TUBEWELL (2 Nos.), RISING MAIN AND DISTRIBUTION LINE FOR MUJNAI T.G (All Other Division & Line 60 unit) CHA SUNDARI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION PHE DTE. | Birpara A.E | Alipurduar Sub Division | ORD/000387/2020-2021 | 1946/ALD | 25/02/2021 | 15/06/2023 | GHOSH & SAHA CONSTRUCTION | 36.68 | 6.84 | 18.66 | 100
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Mujnai T.G Piped Water Supply Scheme | SM/07198 | Retrofitting | Soil investigation work at 4 different places of Alipurduar District under Alipurduar Division PHE Dte. Part-5 Venue : 1)Madarihat (1 no.) 2)Mujnai (2 nos) 3)Sidhabari (1 no.) | Alipurduar RWS,Birpara A.E |  | ORD/000363/2021-2022 | 2125/ALD | 05/01/2022 | 04/02/2022 | G. MITRA & ASSOCIATES, | 4.9 | 4.9 | 100 | 50
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Mujnai T.G Piped Water Supply Scheme | SM/07198 | Retrofitting | Supply of fuel for Diesel Vehicle Maxi Cab(At least 7 seater) (Preferably Scorpio) for Executive Engineer, Alipurduar Division, P.H.E. Dte.(from 08.08.2022 to 31.12.2022) | HQ-A.E |  | ORD/000181/2022-2023 | 1187/ALD | 05/08/2022 | 05/01/2023 | MITHU DAS | 1.16 | 1.09 | 93.54 | 100
8 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Mujnai T.G Piped Water Supply Scheme | SM/07198 | Retrofitting | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Executive Engineer, Alipurduar Division, P.H.E. Dte.(from 01.08.2022 to 31.12.2022) | HQ-A.E |  | ORD/000200/2022-2023 | 1121/ALD | 29/07/2022 | 29/12/2022 | MITHU DAS | 0.84 | 0.84 | 99.9 | 100
Total | [13 empty] | 3171.63 | 54.27 | 1.71