## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR MADARIHAT Water Supply Scheme | SM/08880 | Retrofitting | Repair of Pump House with additional Toilet at 2nd Pump House site of Madarihat WSS under Alipuduar Division, P.H.E. | Birpara A.E | Alipurduar Sub Division | ORD/000131/2020-2021 | 877/ALD | 14/10/2020 | 28/11/2020 | DILIP MAHATO | 2.13 | 1.86 | 87.2 | 91
2 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR MADARIHAT Water Supply Scheme | SM/08880 | Retrofitting | Laying of HDPE pipeline and interconnection of other different dia pipe line with CIDF Specials & Providing house connection (FHTC) at Uttar Madarihat WSS under Alipurduar Division PHE Dte. | Alipurduar RWS,Birpara A.E | Alipurduar Sub Division,RWS Madarihat - Birpara Block | ORD/000127/2021-2022 | 1241/ALD | 27/09/2021 | 26/11/2021 | M/S SURAJIT DEY & CO | 47.32 | 22.91 | 48.41 | 96
3 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR MADARIHAT Water Supply Scheme | SM/08880 | Retrofitting | Construction of RCC boundary wall for Uttar Latabari WSS Pump House (rabindra nagar) at Uttar Latabari PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | Birpara Sub Division | ORD/000268/2021-2022 | 1834/ALD | 10/12/2021 | 24/01/2022 | SHIB RATAN BHOWMIK | 4.9 | 0 | 0 | 75
4 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR MADARIHAT Water Supply Scheme | SM/08880 | Retrofitting | Providing House connection for MADARIHAT PWSS under Alipuduar Division, P.H.E. Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000386/2020-2021 | 1806/ALD | 22/02/2021 | 23/04/2021 | DILIP MAHATO | 20.13 | 18.11 | 90 | 90
5 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR MADARIHAT Water Supply Scheme | SM/08880 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna for AWC and school under Madarihat WSS under Alipurduar Division, PHE Dte. | Birpara A.E |  | ORD/000266/2021-2022 | 1831/ALD | 10/12/2021 | 09/01/2022 | RATAN DUTTA | 5.04 | 4.07 | 80.75 | 59
6 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR MADARIHAT Water Supply Scheme | SM/08880 | Retrofitting | Retrofitting work of pipeline of Madarihat PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000199/2021-2022 | 972/ALD | 13/09/2021 | 13/10/2021 | MS DEYS CONSTRUCTION | 4.99 | 4.99 | 100 | 99
7 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR MADARIHAT Water Supply Scheme | SM/08880 | Retrofitting | Laying of HDPE pipe line for Madarihat Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000358/2021-2022 | 2284/ALD | 21/01/2022 | 22/03/2022 | DILIP MAHATO | 37.73 | 35.81 | 94.89 | 97
8 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR MADARIHAT Water Supply Scheme | SM/08880 | Retrofitting | Laying of HDPE pipe line for Madarihat Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000359/2021-2022 | 2285/ALD | 21/01/2022 | 22/03/2022 | MAHENDRA CHHETRI | 37.73 | 32.37 | 85.78 | 99
9 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR MADARIHAT Water Supply Scheme | SM/08880 | Retrofitting | Construction of 350cum OHR for Madarihat TG Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E |  | ORD/000417/2021-2022 | 2586/ALD | 17/02/2022 | 16/08/2022 | DILIP MAHATO | 71.4 | 20.13 | 28.2 | 90
Total | [13 empty] | 231.38 | 140.24 | 60.61