## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR SISHUBARI Water Supply Scheme | SM/08881 | Retrofitting | Replacement of old existing AC pipeline with UPVC pipe and providing FHTC in connection with Jaldhara/Jal Sapna for Uttar Sishubari WSS under Alipurduar Division, PHE Dte. (Opposite of Rail line area) | Birpara A.E | Alipurduar Sub Division,Birpara Sub Division | ORD/000236/2021-2022 | 1577/ALD | 22/11/2021 | 21/01/2022 | ASHOK SAPKOTA | 22.55 | 20.81 | 92.3 | 54
2 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR SISHUBARI Water Supply Scheme | SM/08881 | Retrofitting | Replacement of old existing AC pipeline with UPVC pipe and providing FHTC in connection with Jaldhara/Jal Sapna for Uttar Sishubari WSS under Alipurduar Division, PHE Dte. (Opposite of Rail line area) | Alipurduar Sadar Sub Division,Birpara A.E | Alipurduar Sub Division,Birpara Sub Division | ORD/000237/2021-2022 | 1578/ALD | 22/11/2021 | 21/01/2022 | KAMALESH ROY | 22.55 | 20.81 | 92.3 | 55
3 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR SISHUBARI Water Supply Scheme | SM/08881 | Retrofitting | Laying of UPVC/DI/MS/CI Distribution pipe line for Gap filling of Chapaguri area at Uttar Sishubari PWSS under Alipurduar Division PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000435/2021-2022 | 2652/ALD | 21/02/2022 | 07/04/2022 | KAMALESH ROY | 4.94 | 4.68 | 94.76 | 55
4 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR SISHUBARI Water Supply Scheme | SM/08881 | Retrofitting | Extension/Merging of Distribution pipeline (UPVC/DI/MS/CI) from Paschim Khairbari WSS to Uttar Sishubari WSS and others misc. work under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000264/2020-2021 | 1255/ALD | 28/12/2020 | 26/02/2021 | MITHUN DAS | 45.83 | 9 | 19.64 | 80
5 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR SISHUBARI Water Supply Scheme | SM/08881 | Retrofitting | Construction of boundary wall at 2nd PH Site of Uttar Sishubari WSS under Alipurduar Division. | Birpara A.E | Birpara Sub Division | ORD/000096/2021-2022 | 895/ALD | 03/09/2021 | 18/10/2021 | MITHUN DAS | 4.98 | 4.99 | 100.28 | 56
6 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR SISHUBARI Water Supply Scheme | SM/08881 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000013/2022-2023 | 718/ALD | 13/06/2022 | 13/06/2022 | Resource Division | 87.66 | 0 | 0 | 0
7 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR SISHUBARI Water Supply Scheme | SM/08881 | Retrofitting | Repairing of 2 nos. P/H with toilet block (PH-1 and 2) and Replacement of old existing AC p/l with UPVC pipe and providing FHTC in connection with Jaldhara/Jal Sapna for Uttar Sishubari WSS under Alipurduar Division, PHE Dte. (Sishubari High School and adjacent area) | Birpara A.E | Alipurduar Sub Division,Birpara Sub Division | ORD/000179/2021-2022 | 1309/ALD | 05/10/2021 | 04/12/2021 | MITHUN DAS | 45.4 | 35.57 | 78.33 | 100
Total | [13 empty] | 233.91 | 95.87 | 40.98