## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of CHANDIRJHAR Water Supply Scheme | SM/08882 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Chandirjhar PWSS under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000475/2021-2022 | 2761/ALD | 25/02/2022 | 26/04/2022 | MATRI ENTERPRISE | 58 | 25.43 | 43.85 | 49
2 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of CHANDIRJHAR Water Supply Scheme | SM/08882 | Retrofitting | Retrofitting of pipeline for the 'Jal Sapno' programme and providing FHTC Connection under Chandirjhar WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000164/2021-2022 | 1305/ALD | 05/10/2021 | 04/12/2021 | SASANKA ROY | 50.06 | 42.97 | 85.82 | 36
3 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of CHANDIRJHAR Water Supply Scheme | SM/08882 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Chandirjhar WSS under Alipurduar Division, PHE Dte. Part-4 | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000345/2021-2022 | 2138/ALD | 06/01/2022 | 05/02/2022 | SASANKA ROY | 5.04 | 5.04 | 100 | 49
4 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of CHANDIRJHAR Water Supply Scheme | SM/08882 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Chandirjhar WSS under Alipurduar Division, PHE Dte. Part-5 | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000346/2021-2022 | 2139/ALD | 06/01/2022 | 05/02/2022 | SASANKA ROY | 5.04 | 5.04 | 100 | 48.5
5 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of CHANDIRJHAR Water Supply Scheme | SM/08882 | Retrofitting | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Alipurduar Sub Division,Birpara Sub Division,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000556/2021-2022 | 855/ALD | 31/08/2021 | 30/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 0 | 0 | 0
6 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of CHANDIRJHAR Water Supply Scheme | SM/08882 | Retrofitting | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of CHANDIRJHAR Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000317/2021-2022 | 2193/ALD | 11/01/2022 | 11/04/2022 | DULAL DAS | 21.92 | 8.72 | 39.8 | 100
7 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of CHANDIRJHAR Water Supply Scheme | SM/08882 | Retrofitting | Providing House connection for CHANDIRJHAR water supply scheme at Alipurduar -II Block under Alipuduar Division, P.H.E. Dte. Part-II | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000223/2020-2021 | 1174/ALD | 15/12/2020 | 13/02/2021 | TAPASH KUMAR BHOWMICK | 19.93 | 19.93 | 100 | 0
Total | [13 empty] | 2750.65 | 107.13 | 3.89