## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of SALKUMARHAT Water Supply Scheme | SM/08883 | Retrofitting | Providing FHTC connection for AWC, School, Health Centre etc. of Salkumarhat WSS under Alipurduar Division, PHE Dte. Part-C | Alipurduar RWS | Birpara Sub Division | ORD/000263/2021-2022 | 1596/ALD | 22/11/2021 | 22/12/2021 | DEBABRATA DUTTA | 4.92 | 0 | 0 | 98
2 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of SALKUMARHAT Water Supply Scheme | SM/08883 | Retrofitting | Laying Distribution line of UPVC & Di Pipe , with providing FHTC Connection for the Salkumarhat Water Supply Scheme Under Alipurduar Division PHE DTE (PART-A) | Alipurduar RWS | Birpara Sub Division | ORD/000087/2021-2022 | 983/ALD | 13/09/2021 | 12/11/2021 | TAPASH DAS | 25.25 | 0 | 0 | 97
3 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of SALKUMARHAT Water Supply Scheme | SM/08883 | Retrofitting | Laying Distribution line of UPVC & Di Pipe , with providing FHTC Connection for the Salkumar Water Supply Scheme Under Alipurduar Division PHE DTE (PART-A) | Birpara A.E | Birpara Sub Division | ORD/000133/2021-2022 | 1243/ALD | 27/09/2021 | 26/11/2021 | TAPASH DAS | 25.25 | 0 | 0 | 78
4 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of SALKUMARHAT Water Supply Scheme | SM/08883 | Retrofitting | Laying Distribution line of UPVC and DI with providing FHTC Connection for the Salkumar Water Supply Scheme Area under Alipurduar Division, PHE Dte. | Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Kalchini Block | ORD/000197/2021-2022 | 1318/ALD | 05/10/2021 | 04/12/2021 | TAPASH KUMAR BHOWMICK | 35.38 | 0 | 0 | 85
5 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of SALKUMARHAT Water Supply Scheme | SM/08883 | Retrofitting | Construction of 300 m3 capacity RCC Over Head Reservoir For SALKUMARHAT PWSS under Alipurduar Division PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000080/2020-2021 | 632/ALD | 03/09/2020 | 02/12/2020 | HARIDAS GHOSH | 63.58 | 0 | 0 | 80
6 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of SALKUMARHAT Water Supply Scheme | SM/08883 | Retrofitting | Repairing & renovation of Pump House, Pathway, Boundary wall (2nd site) & laying DI Pipe line at Salkumarhat WSS under Alipurduar Division PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000099/2021-2022 | 898/ALD | 03/09/2021 | 18/10/2021 | TAPASH DAS | 4.82 | 0 | 0 | 62
7 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of SALKUMARHAT Water Supply Scheme | SM/08883 | Retrofitting | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Salkumarhat PWSS, Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division,RWS Madarihat - Birpara Block | ORD/000479/2021-2022 | 2898/ALD | 08/03/2022 | 18/12/2025 | DILIP MAHATO | 48.52 | 0 | 0 | 65
Total | [13 empty] | 207.72 | 0 | 0