## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Providing House Connection of Bholardabri WSS under Alipurduar Division, PHE Dte.Part-7 | Alipurduar RWS,Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000203/2021-2022 | 991/ALD | 13/09/2021 | 13/10/2021 | MANORAMA ENTERPRISE | 4.3 | 3 | 69.6 | 63
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Bholardabri WSS under Alipurduar Division, PHE Dte. Part-10 | Alipurduar RWS | Alipurduar Sub Division | ORD/000276/2021-2022 | 1842/ALD | 10/12/2021 | 09/01/2022 | HARIDAS GHOSH | 5.02 | 4.39 | 87.59 | 63
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Bholardabri WSS under Alipurduar Division, PHE Dte. Part-8 | Alipurduar RWS | Alipurduar Sub Division | ORD/000274/2021-2022 | 1840/ALD | 10/12/2021 | 09/01/2022 | HARI CONSTRUCTION | 5 | 4.72 | 94.48 | 66
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Bholardabri WSS under Alipurduar Division, PHE Dte. Part-9 | Alipurduar RWS | Alipurduar Sub Division | ORD/000275/2021-2022 | 1841/ALD | 10/12/2021 | 09/01/2022 | HARI CONSTRUCTION | 5.04 | 4.42 | 87.59 | 65
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Bholardabri WSS under Alipurduar Division, PHE Dte. Part-12 | Alipurduar RWS,Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000348/2021-2022 | 2141/ALD | 06/01/2022 | 07/03/2022 | HARIDAS GHOSH | 5.04 | 4.66 | 92.41 | 65
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Restoration of laying distribution system by replacing of Damaged AC pipeline with UPVC pipeline of Bholardabri WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division | ORD/000204/2021-2022 | 992/ALD | 13/09/2021 | 13/10/2021 | MANORAMA ENTERPRISE | 4.89 | 4.62 | 94.47 | 65
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Repairing and renovation of 2 nos. P/H, cons. Of 2 nos. Toilet (for 1st and 2nd site) and laying of UPVC pipe line with providing House connection at Bholardabri WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division | ORD/000184/2021-2022 | 1313/ALD | 05/10/2021 | 04/12/2021 | HARI CONSTRUCTION | 33.81 | 33.47 | 98.97 | 64
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Bholardabri WSS under Alipurduar Division, PHE Dte. Part-11 | Alipurduar RWS | Alipurduar Sub Division | ORD/000347/2021-2022 | 2140/ALD | 06/01/2022 | 05/02/2022 | HARIDAS GHOSH | 5.04 | 5.04 | 100 | 64
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Bholardabri Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar RWS | Alipurduar Sub Division | ORD/000105/2022-2023 | 697/ALD | 08/06/2022 | 08/07/2022 | KAMALESH ROY | 4.84 | 4.84 | 100 | 63
10 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Quotation for new service connection at Bholardabri, P/H no.III, Application no.4003012374 |  |  | VCH/001473/2022-2023 | bp-87/22-23 | 11/11/2022 | 11/11/2022 | WBSEDCL | 1.23 | 0 | 0 | 0
11 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Quotation for new service connection for Bholardabri, near Modakpara t/W no. III, Application no. 4003012374 |  |  | VCH/001451/2022-2023 |  | 07/11/2022 | 07/11/2022 | WBSEDCL | 1.23 | 0 | 0 | 0
12 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) (Preferably TUV) for Assistant Engineer, Alipurduar RWS Sub-Division, P.H.E. Dte.(from 01.01.2022 to 31.12.2022) | Alipurduar RWS |  | ORD/000307/2021-2022 | 2014/ALD | 29/12/2021 | 29/12/2022 | KAMALESH ROY | 1.76 | 1.49 | 84.24 | 61
13 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Construction of 450cum OHR for Bholardabri water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division | ORD/000311/2021-2022 | 2187/ALD | 11/01/2022 | 10/07/2022 | HARIDAS GHOSH | 87.58 | 86.43 | 98.68 | 63
14 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | soil investigation work at 4 different places of Alipurduar District under Alipurduar Division PHE Dte. Part-1 Places : 1)Uttar Kamakhyaguri 2)Uttar Majherdabri. 3)Bholardabri. 4) Narathali. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000356/2021-2022 | 2121/ALD | 05/01/2022 | 04/02/2022 | MOYTEC | 4.9 | 4.9 | 100 | 69
15 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Alipurduar Sub Division,Birpara Sub Division,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000556/2021-2022 | 855/ALD | 31/08/2021 | 30/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 10 | 0.39 | 0
16 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Restoration of laying distribution system by replacing of damaged AC Pipeline with UPVC pipeline of Bholardabri Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000533/2021-2022 | 3107/ALD | 24/03/2022 | 23/05/2022 | HARI CONSTRUCTION | 56.51 | 51.82 | 91.69 | 100
17 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Bholardabri Water Supply Scheme TW No.- III (Aug) under NMD-II,PHE. Dte Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000709/2022-2023 | 2061/NMD-II | 20/12/2022 | 19/01/2023 | SUMON ELECTRICAL | 10.5 | 10.38 | 98.82 | 100
18 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Construction of Rig Machine Approach Road of Bholardabri 3rd TW Site under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division | ORD/000407/2022-2023 | 2792/ALD | 10/01/2023 | 09/02/2023 | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 0.33 | 0.32 | 98.34 | 64
19 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Providing FHTC in school in Bholardabri PWSS under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,RWS Madarihat - Birpara Block | ORD/000495/2022-2023 | 3359/ALD | 14/03/2023 | 13/04/2023 | HARIDAS GHOSH | 0.25 | 0.25 | 100 | 100
20 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Construction of Pump House ,Boundary Wall and Providing FHTC including Laying of UPVC pipeline and Tube well Boring by ODEX-165 Method of drilling for Bholardabri PWSS under Alipurduar Division PHE DTE. | Alipurduar RWS,Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000382/2021-2022 | 2382/ALD | 31/01/2022 | 15/01/2025 | HARIDAS GHOSH | 82.3 | 46.48 | 56.48 | 80
21 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Laying of new UPVC/DI pipeline for filling of Gap in the distribution system and laying of delivery line connection, supply of CIDF specials, land development works, construction of surface drain, pathway at 3rd TW site and other allied works in connection with the Augmentation of Bholardabri PWSS under Alipurduarn Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,RWS Madarihat - Birpara Block | ORD/000318/2023-2024 | 2410/ALD | 09/11/2023 | 01/02/2025 | HARI CONSTRUCTION | 30.3 | 16.52 | 54.51 | 100
22 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Construction of Pump House ,Boundary Wall and Providing FHTC including Laying of UPVC pipeline and Tube well Boring by ODEX-165 Method of drilling for Bholardabri PWSS under Alipurduar Division PHE DTE.(2382/ALD DT:31/01/2022) Construction of 450cum OHR for Bholardabri water Supply Scheme under Alipurduar Division, PHE Dte. (2187/ALD DT:29/02/2022) |  |  | BILL/00750/2023-2024 | 449/23-24/PFMS | 30/03/2024 | 30/03/2024 | HARIDAS GHOSH | 1.19 | 0 | 0 | 0
23 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Construction of Pump House ,Boundary Wall and Providing FHTC including Laying of UPVC pipeline and Tube well Boring by ODEX-165 Method of drilling for Bholardabri PWSS under Alipurduar Division PHE DTE.(2382/ALD DT:31/01/2022) Construction of 450cum OHR for Bholardabri water Supply Scheme under Alipurduar Division, PHE Dte. (2187/ALD DT:29/02/2022) |  |  | BILL/00601/2023-2024 |  | 29/02/2024 | 29/02/2024 | HARIDAS GHOSH | 2.68 | 0 | 0 | 0
24 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 14/11/2024 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
25 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Construction of Pump House ,Boundary Wall and Providing FHTC including Laying of UPVC pipeline and Tube well Boring by ODEX-165 Method of drilling for Bholardabri PWSS under Alipurduar Division PHE DTE.(2382/ALD DT:31/01/2022) Construction of 450cum OHR for Bholardabri water Supply Scheme under Alipurduar Division, PHE Dte. (2187/ALD DT:29/02/2022) |  |  | BILL/00749/2023-2024 | 448/23-24/PFMS | 30/03/2024 | 30/03/2024 | HARIDAS GHOSH | 1.49 | 0 | 0 | 0
26 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Drilling Rigbore tube well (ODEX-115 method) at Modakpara, Paschim Bholardabri under Alipurduar Division, PHE Dte. |  |  | ORD/000305/2022-2023 | 1943/ALD | 17/10/2022 | 16/11/2022 | HARIDAS GHOSH | 2.77 | 0 | 0 | 0
27 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Laying of new UPVC/DI pipeline for interconnection in the distribution system and other allied works under Bholardabri PWSS, Alipurduar Division, PHE Dte. (SM/09883) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000353/2024-2025 | 3423/ALD | 26/09/2024 | 25/03/2025 | TAPASH DAS | 20.57 | 0 | 0 | 70
28 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Repairing of pump house at 2nd TW site of Bholardabri PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000164/2025-2026 | 1772/ALD | 18/08/2025 | 17/09/2025 | TAPASH DAS | 1.01 | 0 | 0 | 0
29 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | SM/09883 | Augmentation | Laying rising main line from 2nd side to HW Site of Bholardabri WSS and construction of different dia valve chamber and restoration of damaged FHTC connection and other allied work at Bholardabri PWSS under JJM Programme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000170/2025-2026 | 1778/ALD | 18/08/2025 | 17/10/2025 | TAPASH DAS | 2.88 | 0 | 0 | 0
Total | [13 empty] | 3037.17 | 297.73 | 9.8