## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME | SM/09885 | Augmentation | Laying of CIDF, Rising Main, Delivery line, Hydraulic Testing, disinfection of UPVC pipeline and other allied works at Bhutnirghat WSS under Alipurduar Division, PHE Dte. |  |  | ORD/000297/2022-2023 | 1688/ALD | 20/09/2022 | 19/11/2022 | DILIP MAHATO | 5.82 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME | SM/09885 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/Jal Swapna for Bhutnirghat PWSS under Birpara Sub-Division under Alipurduar Division, PHE Dte. Part-5 | Birpara A.E | Alipurduar Sub Division | ORD/000259/2021-2022 | 1606/ALD | 22/11/2021 | 22/12/2021 | GOUTAM KUMAR DAS | 5.04 | 0 | 0 | 97
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME | SM/09885 | Augmentation | Providing FHTC including Rising main and laying of distribution pipeline for BHUTNIRGHAT Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Birpara A.E | Alipurduar Sub Division | ORD/000381/2021-2022 | 2381/ALD | 31/01/2022 | 01/04/2022 | DILIP MAHATO | 89.08 | 64.5 | 72.41 | 94
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME | SM/09885 | Augmentation | Extension of pipeline and connection with main line by UPVC, GI, DI pipe and construction of valve chamberand others at Bhutnirghat WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000065/2022-2023 | 342/ALD | 02/05/2022 | 16/06/2022 | DILIP MAHATO | 25.7 | 0 | 0 | 92
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME | SM/09885 | Augmentation | Sinking of Big Dia T/Well P/House B/Wall & Rising Main of 3rd T/Well Site at FALAKATA Aug. PWSS under Alipurduar Division PHED. | HQ-A.E | RWS Kalchini Block | ORD/000083/2020-2021 | 655/ALD | 08/09/2020 | 06/01/2021 | BILTU DAS | 22.65 | 16.12 | 71.16 | 81.5
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME | SM/09885 | Augmentation | Loop Connention between West Falakata & Barodoba area via Mujnai River Bridge incl interconnection with the existing BHUTNIRGHAT PWSS under FALAKATA Aug. PWSS under Alipurduar Division PHED. | HQ-A.E | RWS Kalchini Block | ORD/000072/2020-2021 | 626/ALD | 03/09/2020 | 01/01/2021 | GOUTAM KUMAR DAS | 26.08 | 1.53 | 5.88 | 82.5
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME | SM/09885 | Augmentation | Shifting and Laying distribution of P/line due to Widening of Falkata to Dhupguri rd. & other allied works to Bhutnirghat PWSS under Alipurduar Division PHED. part (II). |  |  | ORD/000438/2020-2021 | 08/ALD | 02/04/2020 | 01/04/2025 | SHIB RATAN BHOWMIK | 17.51 | 6.68 | 38.15 | 0
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME | SM/09885 | Augmentation | Gap filling by UPVC/DI pipe for Bhutnirghat WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000253/2021-2022 | 1600/ALD | 22/11/2021 | 22/12/2021 | GOUTAM KUMAR DAS | 4.99 | 4.99 | 100 | 98
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME | SM/09885 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/Jal Swapna (Schools, AWC and others) for Bhutnirghat PWSS under Birpara Sub-Division under Alipurduar Division, PHE Dte. Part-4 | Birpara A.E | Alipurduar Sub Division | ORD/000258/2021-2022 | 1605/ALD | 22/11/2021 | 22/12/2021 | GOUTAM KUMAR DAS | 5.04 | 5.04 | 100 | 95
10 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME | SM/09885 | Augmentation | Construction of Pump House, Boundary Wall, laying distribution system and providing FHTC for BHUTNIRGHAT Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Birpara A.E | Alipurduar Sub Division | ORD/000379/2021-2022 | 2379/ALD | 31/01/2022 | 01/05/2022 | DILIP MAHATO | 92.34 | 80.52 | 87.2 | 98
11 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME | SM/09885 | Augmentation | Laying of UPVC pipeline and Tube well Boring by Reverse Rotary method of drilling for BHUTNIRGHAT Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Birpara A.E | Alipurduar Sub Division | ORD/000380/2021-2022 | 2380/ALD | 31/01/2022 | 01/04/2022 | DILIP MAHATO | 95.15 | 81.04 | 85.17 | 97
12 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME | SM/09885 | Augmentation | Road crossing (by NP3 Hume pipe) at Dhupguri Road under under Zone-II of augmentation of Falakata WSS and infront of bhutnirghat WSS due to widening of PWD Road under Alipurduar Division, PHE Dte. (3 nos) | Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Kalchini Block | ORD/000394/2021-2022 | 2308/ALD | 25/01/2022 | 24/02/2022 | ASSOCIATE CONSTRUCTION COMPANY | 2.49 | 2.45 | 98.62 | 89.25
13 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME | SM/09885 | Augmentation | Construction of 450cum OHR for Bhutnirghat Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000310/2021-2022 | 2186/ALD | 11/01/2022 | 10/07/2022 | DILIP MAHATO | 87.59 | 74.96 | 85.58 | 79.5
14 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME | SM/09885 | Augmentation | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 25/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 0 | 0 | 100
15 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME | SM/09885 | Augmentation | Supply of 250 mm dia CI Sluice Valve for Augmentation of Bhutnirghat Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000117/2022-2023 | 709/ALD | 08/06/2022 | 08/07/2022 | DILIP MAHATO | 4.93 | 4.93 | 100 | 98
16 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME | SM/09885 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Bhutnirghat water supply scheme, TW no. III under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000060/2023-2024 | 1194/NMD-II | 23/06/2023 | 23/07/2023 | ANUP BASU | 10.59 | 10.48 | 98.91 | 100
17 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME | SM/09885 | Augmentation | Soil investigation work at 4 different places of Alipurduar District under Alipurduar Division PHE Dte. Part-3 VENUE : 1)Chuniajhora TG 2) Dakshin Paitkapara 3)Jay Birpara 4) Bhutnirghat | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000361/2021-2022 | 2123/ALD | 05/01/2022 | 04/02/2022 | R B TESTING | 4.86 | 4.86 | 100 | 66.75
18 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME | SM/09885 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT BHUTNIRGHAT TW NO-III |  |  | BILL/00057/2023-2024 | BP-2023-24-69 | 13/05/2023 |  | WBSEDCL | 1.43 | 0 | 0 | 0
Total | [13 empty] | 1003.87 | 358.11 | 35.67