## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF MADHYA PAROKATA PIPED WATER SUPPLY SCHEME | SM/09886 | Augmentation | Construction of 350cum OHR for Madhya Parokata Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000313/2021-2022 | 2189/ALD | 11/01/2022 | 10/07/2022 | SOUVIK ROY PALADHI | 71.4 | 8.57 | 12 | 96
2 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF MADHYA PAROKATA PIPED WATER SUPPLY SCHEME | SM/09886 | Augmentation | Providing FHTC including Rising main for Madhya Parokata Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000385/2021-2022 | 2385/ALD | 31/01/2022 | 01/04/2022 | SOUVIK ROY PALADHI | 74.19 | 64.79 | 87.34 | 94
3 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF MADHYA PAROKATA PIPED WATER SUPPLY SCHEME | SM/09886 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Madhya Parokata Water Supply Scheme TW No.-III under NMD-II,PHE.Dte, Alipurduar. |  |  | ORD/000911/2021-2022 | 402/NMD-II | 22/03/2022 | 21/04/2022 | TALUKDAR ENTERPRISE | 2.38 | 2.36 | 99.04 | 0
4 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF MADHYA PAROKATA PIPED WATER SUPPLY SCHEME | SM/09886 | Augmentation | Providing House Connection (FHTC) at Parokata WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000340/2021-2022 | 2116/ALD | 05/01/2022 | 04/02/2022 | SREE MAA CONSTRUCTION | 5.02 | 5.02 | 100 | 95
5 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF MADHYA PAROKATA PIPED WATER SUPPLY SCHEME | SM/09886 | Augmentation | Laying of UPVC pipeline and Tube well Boring by ODEX-165 Method of drilling for Madhya Parokata Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000384/2021-2022 | 2384/ALD | 31/01/2022 | 01/04/2022 | SOUVIK ROY PALADHI | 96.14 | 101.62 | 105.69 | 95
6 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF MADHYA PAROKATA PIPED WATER SUPPLY SCHEME | SM/09886 | Augmentation | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 25/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 0 | 0 | 100
7 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF MADHYA PAROKATA PIPED WATER SUPPLY SCHEME | SM/09886 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Madhya Parokata water supply scheme TW No. III under NMD-II, PHE Dte. Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000007/2022-2023 | 555/NMD-II | 26/04/2022 | 26/05/2022 | M/S UTPAL CHAKRABORTY & CO. | 7.85 | 7.73 | 98.48 | 100
8 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF MADHYA PAROKATA PIPED WATER SUPPLY SCHEME | SM/09886 | Augmentation | MADHYA PAROKATA T/W no. III, Application no. 4002930511, Ref no. 402824640, SM/09886/160 |  |  | VCH/000698/2022-2023 | BP-26/22-23 | 15/07/2022 |  | WBSEDCL | 0.87 | 0 | 0 | 0
Total | [13 empty] | 760.43 | 190.08 | 25