## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | REJUVINATION OF 'DHAOLAJHORA .T.G WATER SUPPLY SCHEME' | SM/09888 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of DHAOLAJHORA TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000325/2021-2022 | 2226/ALD | 14/01/2022 | 14/04/2022 | MADHAB SAHA | 20.99 | 17.04 | 81.17 | 100
2 | ALIPURDUAR |  | Alipurduar Division | REJUVINATION OF 'DHAOLAJHORA .T.G WATER SUPPLY SCHEME' | SM/09888 | Augmentation | Repairing of old UPVC pipe line , FHTC and other misc. work related to DHAOLAJHORA PWSS Alipurduar - II Block under Alipurduar Division , PHE Dte | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000071/2022-2023 | 436/ALD | 13/05/2022 | 12/06/2022 | MATARA CONSTRUCTION CO | 3.3 | 0 | 0 | 27
3 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVINATION OF 'DHAOLAJHORA .T.G WATER SUPPLY SCHEME' | SM/09888 | Augmentation | Quotation for NSC at P/H No.III under Dhaoljhora TG W/S/S |  |  | BILL/00604/2023-2024 | BP-2023-24-169 | 15/06/2023 | 15/06/2023 | WBSEDCL | 1.31 | 0 | 0 | 0
4 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVINATION OF 'DHAOLAJHORA .T.G WATER SUPPLY SCHEME' | SM/09888 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Rejuvination of Dhaolajhora TG Water Supply Scheme TW No.-I under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000036/2023-2024 | 986/NMD-II | 15/05/2023 | 14/06/2023 | MASSK ENGINEERING WORKS | 10.82 | 10.73 | 99.2 | 100
Total | [13 empty] | 36.41 | 27.77 | 76.26