## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF 'BAKLA WATER SUPPLY SCHEME' | SM/09890 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVINATION OF BAKLA water supply scheme, TW no III under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000822/2022-2023 | 478/NMD-II | 02/03/2023 | 01/04/2023 | M/S A.D. ENTERPRISE | 10.86 | 10.19 | 93.79 | 80
2 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF 'BAKLA WATER SUPPLY SCHEME' | SM/09890 | Augmentation | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Bakla PWSS Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000444/2021-2022 | 2753/ALD | 24/02/2022 | 08/06/2025 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 43.78 | 0 | 0 | 43
3 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF 'BAKLA WATER SUPPLY SCHEME' | SM/09890 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method)and Rising Main for Additional T/W of BAKLA Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000314/2021-2022 | 2190/ALD | 11/01/2022 | 27/12/2024 | SHYAMAL ROY | 21.81 | 10.18 | 46.68 | 100
Total | [13 empty] | 76.46 | 20.37 | 26.65