## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVINATION OF CHANDIRJHAR WATER SUPPLY SCHEME | SM/09892 | Augmentation | Quotation for new service connection at Loknathpur W/SS Application No-4002943882 |  |  | VCH/000644/2022-2023 |  | 14/07/2022 | 14/07/2022 | WBSEDCL | 0.95 | 0 | 0 | 0
2 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVINATION OF CHANDIRJHAR WATER SUPPLY SCHEME | SM/09892 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT CHANDIJHAR W/SS TW NO-III |  |  | VCH/000642/2022-2023 |  | 14/07/2022 | 14/07/2022 | WBSEDCL | 0.95 | 0 | 0 | 0
3 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVINATION OF CHANDIRJHAR WATER SUPPLY SCHEME | SM/09892 | Augmentation | New Connection Chandirjhar P/H no. III, Appplication no. 402943882,Ref no. 402837622 (SM/09892) |  |  | VCH/001067/2022-2023 | BP-38/22-23 | 08/08/2022 | 08/08/2022 | WBSEDCL | 0.95 | 0 | 0 | 0
4 | ALIPURDUAR |  | Alipurduar Division | REJUVINATION OF CHANDIRJHAR WATER SUPPLY SCHEME | SM/09892 | Augmentation | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Chandirjhar PWSS under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000475/2021-2022 | 2761/ALD | 25/02/2022 | 26/04/2022 | MATRI ENTERPRISE | 58 | 0 | 0 | 49
5 | ALIPURDUAR |  | Alipurduar Division | REJUVINATION OF CHANDIRJHAR WATER SUPPLY SCHEME | SM/09892 | Augmentation | Retrofitting of pipeline for the 'Jal Sapno' programme and providing FHTC Connection under Chandirjhar WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000164/2021-2022 | 1305/ALD | 05/10/2021 | 04/12/2021 | SASANKA ROY | 50.06 | 0 | 0 | 36
6 | ALIPURDUAR |  | Alipurduar Division | REJUVINATION OF CHANDIRJHAR WATER SUPPLY SCHEME | SM/09892 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of CHANDIRJHAR Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000317/2021-2022 | 2193/ALD | 11/01/2022 | 11/04/2022 | DULAL DAS | 21.92 | 0 | 0 | 100
7 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVINATION OF CHANDIRJHAR WATER SUPPLY SCHEME | SM/09892 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Chandijhar Water Supply Scheme TW No.- III under NMD-II, PHE. Dte, Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000926/2021-2022 | 409/NMD-II | 22/03/2022 | 21/04/2022 | M/S J.K ENGINEERING CO. | 2.39 | 0 | 0 | 0
8 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVINATION OF CHANDIRJHAR WATER SUPPLY SCHEME | SM/09892 | Augmentation | supply, delivery,of standby Automatically controlled diaphragm type chlorinator for accurate dosing of chlorine solution at Chandijhar Water Supply Scheme ,in the dist. of Alipurduar under NMD-II ,PHE Dte. Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000714/2022-2023 | 2100/NMD-II | 29/12/2022 | 13/01/2023 | M/S ANJALI ENTERPRISE | 1.8 | 0 | 0 | 0
9 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVINATION OF CHANDIRJHAR WATER SUPPLY SCHEME | SM/09892 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Chandijhar Water Supply Scheme TW No.-III under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000900/2021-2022 | 427/NMD-II | 25/03/2022 | 24/04/2022 | KASHI NATH DEY | 7.85 | 0 | 0 | 100
Total | [13 empty] | 144.86 | 0 | 0