## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF MUNSHIPARA WATER SUPPLY SCHEME | SM/09894 | Augmentation | Additional quotation for Munshipara p/h-III |  |  | BILL/02150/2023-2024 | BP-2023-24-479 | 12/12/2023 | 12/12/2023 | WBSEDCL | 3.86 | 0 | 0 | 0
2 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF MUNSHIPARA WATER SUPPLY SCHEME | SM/09894 | Augmentation | QUOTATION FOR NSC AT MUNSHIPARA PH NO-III |  |  | BILL/01750/2023-2024 | BP-2023-24-359 | 27/09/2023 | 27/09/2023 | WBSEDCL | 1 | 0 | 0 | 0
3 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF MUNSHIPARA WATER SUPPLY SCHEME | SM/09894 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of MUNSHIPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000326/2021-2022 | 2227/ALD | 14/01/2022 | 14/04/2022 | TAPASH DAS | 21.92 | 0 | 0 | 25
4 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF MUNSHIPARA WATER SUPPLY SCHEME | SM/09894 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation of Munshipara water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte.Alipurduar | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000687/2023-2024 | 2173/NMD-II | 27/07/2023 | 02/09/2024 | M/S KUNDU CONSTRUCTION | 10.81 | 0 | 0 | 100
5 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF MUNSHIPARA WATER SUPPLY SCHEME | SM/09894 | Augmentation | ADDITIONAL QUOTATION CHARGES FOR MUNSHIPARA PWSS . |  |  | BILL/00209/2024-2025 | BP-42/24-25 | 29/04/2024 | 29/04/2024 | WBSEDCL | 0.36 | 0 | 0 | 0
Total | [13 empty] | 37.95 | 0 | 0