## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF DHUMCHIPARA. T.G. WATER SUPPLY SCHEME | SM/09896 | Augmentation | Quotation for new service connection at Dhumchipara TW No- IV |  |  | BILL/00039/2022-2023 | BP-140/22-23 | 23/02/2023 |  | WBSEDCL | 1.99 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF DHUMCHIPARA. T.G. WATER SUPPLY SCHEME | SM/09896 | Augmentation | Construction of Pump House, Boundary Wall, and Tube well Boring by ODEX-195 method of drilling including Rising main for DHUMCHIPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000399/2021-2022 | 2390/ALD | 31/01/2022 | 01/05/2022 | DILIP MAHATO | 27.18 | 0 | 0 | 18
3 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF DHUMCHIPARA. T.G. WATER SUPPLY SCHEME | SM/09896 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for DHUMCHIPARA TG Water Supply Scheme TW No.-IV under NMD-II,PHE Dte. Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000783/2022-2023 | 247/NMD-II | 13/02/2023 | 15/03/2023 | ALPHA ENTERPRISE | 13.78 | 13.78 | 100 | 100
4 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF DHUMCHIPARA. T.G. WATER SUPPLY SCHEME | SM/09896 | Augmentation | Quotation for Meter Burn at DUMCHIPARA TG PH NO-2 |  |  | BILL/00173/2024-2025 | null | 23/04/2024 |  | WBSEDCL | 0.1 | 0 | 0 | null
5 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF DHUMCHIPARA. T.G. WATER SUPPLY SCHEME | SM/09896 | Augmentation | QUOTATION CHARGES FOR METER BURN AT DHUMCHIPARA TG PH NO-I |  |  | BILL/00175/2024-2025 | null | 23/04/2024 |  | WBSEDCL | 0.1 | 0 | 0 | null
6 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF DHUMCHIPARA. T.G. WATER SUPPLY SCHEME | SM/09896 | Augmentation | Sinking of Big dia. Tubewell (200 x 150 mm dia.)By modified DTH -ODEX method of drilling at Dhumchipara-2nos. site (SM/09896 & SM/07130) of Birpara Sub-Division under Alipurduar Division, PHE Dte. | Alipurduar RWS,Birpara A.E | JUNIOR ENGINEER | ORD/000533/2023-2024 | 891/ALD | 15/03/2024 | 11/09/2024 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 34.47 | 0 | 0 | 10
Total | [13 empty] | 77.63 | 13.78 | 17.75