## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF BIRPARA(APD) WATER SUPPLY SCHEME | SM/09897 | Augmentation | Laying of Distribution Line (HDPE and DI) for retrofitting of FHTC for BIRPARA WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000360/2020-2021 | 1754/ALD | 19/02/2021 | 05/04/2021 | BILTU DAS | 47.98 | 15 | 31.26 | 61
2 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF BIRPARA(APD) WATER SUPPLY SCHEME | SM/09897 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of BIRPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000316/2021-2022 | 2192/ALD | 11/01/2022 | 11/04/2022 | DAS CONSTRUCTION | 22.03 | 7.86 | 35.67 | 65
3 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF BIRPARA(APD) WATER SUPPLY SCHEME | SM/09897 | Augmentation | Extension and replacement of damaged pipeline under Birpara APD PWSS at Alipurduar-I under Alipurduar Division, P.H.E. Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000077/2021-2022 | 883/ALD | 03/09/2021 | 18/10/2021 | KAMALESH ROY | 15.92 | 3.32 | 20.88 | 0
4 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF BIRPARA(APD) WATER SUPPLY SCHEME | SM/09897 | Augmentation | Quotation for new service connection at Birpara (apd) TG P/H No-III. Application No- 4003027982 |  |  | BILL/00017/2022-2023 | BP-110/22-23 | 19/12/2022 | 19/12/2022 | WBSEDCL | 1.34 | 0 | 0 | 0
5 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF BIRPARA(APD) WATER SUPPLY SCHEME | SM/09897 | Augmentation | Extension work order for Hiring of Diesel vehicle Maxi Cab(At least 7 seater) for Executive Engineer, Alipurduar Division under Alipurduar Division, PHE Dte.( 01.04.2021 to 30.06.2021) | Alipurduar Sadar Sub Division,HQ-A.E | Birpara Sub Division | ORD/000609/2020-2021 | 3051/ALD | 31/03/2021 | 30/06/2021 | APSARI BHOWMICK | 0.54 | 0 | 0 | 100
6 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF BIRPARA(APD) WATER SUPPLY SCHEME | SM/09897 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Rejuvenation of Birpara (APD) water supply scheme, TW no III under JJM under NMD-II, PHE Dte. APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000038/2023-2024 | 991/NMD-II | 15/05/2023 | 14/06/2023 | P K ENGINEERING | 10.95 | 10.3 | 93.99 | 80
Total | [13 empty] | 98.76 | 36.48 | 36.93