## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | Rejuvenation Of Dima T.G. W.S.S | SM/09904 | Augmentation | Laying of DI / UPVC Pipeline & other Misc. works related to DIMA PWSS under Alipurduar Division PHED. | HQ-A.E | RWS Kalchini Block | ORD/000068/2020-2021 | 623/ALD | 03/09/2020 | 01/01/2021 | TILAK SHARMA | 29.43 | 0 | 0 | 30
2 | ALIPURDUAR |  | Alipurduar Division | Rejuvenation Of Dima T.G. W.S.S | SM/09904 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of DIMA TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar RWS,HQ-A.E | RWS Alipurduar - I Block,RWS Kalchini Block | ORD/000293/2021-2022 | 1991/ALD | 27/12/2021 | 27/03/2022 | GOBINDA BAGCHI | 20.87 | 0 | 0 | 72
3 | ALIPURDUAR |  | Northern Mechanical Division II | Rejuvenation Of Dima T.G. W.S.S | SM/09904 | Augmentation | Supply, delivery of Electro mechanical components at Dima T.G Water Supply Scheme, in the dist. of ALIPURDUAR under NMD-II, PHE. Dte, Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000865/2021-2022 | 307/NMD-II | 10/03/2022 | 09/04/2022 | DIAMOND ELECTRICAL WORKS | 8.32 | 0 | 0 | 30
4 | ALIPURDUAR |  | Northern Mechanical Division II | Rejuvenation Of Dima T.G. W.S.S | SM/09904 | Augmentation | Quotation for new service connection at Dima TG TW No III |  |  | BILL/00034/2022-2023 | BP-120/22-23 | 09/01/2023 | 09/01/2023 | WBSEDCL | 1.34 | 0 | 0 | 0
5 | ALIPURDUAR |  | Northern Mechanical Division II | Rejuvenation Of Dima T.G. W.S.S | SM/09904 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Rejuvenation of DIMA T.G water supply scheme, TW no III under NMD-II, PHE Dte 106. APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/001076/2023-2024 | 2766/NMD-II | 04/10/2023 | 02/08/2025 | ASHWIRBAD WOOD CRAFT | 10.68 | 0 | 0 | 90
6 | ALIPURDUAR |  | Alipurduar Division | Rejuvenation Of Dima T.G. W.S.S | SM/09904 | Augmentation | Reparing of Pump House at Headwork site of Dima TG PWSS Under Alipurduar Division PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000142/2025-2026 | 1579/ALD | 31/07/2025 | 29/09/2025 | TAPASH DAS | 0.79 | 0 | 0 | 0
7 | ALIPURDUAR |  | Alipurduar Division | Rejuvenation Of Dima T.G. W.S.S | SM/09904 | Augmentation | Reparing of Pump House at 2nd site of Dima TG PWSS Under Alipurduar Division PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000141/2025-2026 | 1578/ALD | 31/07/2025 | 29/09/2025 | TAPASH DAS | 0.99 | 0 | 0 | 0
Total | [13 empty] | 72.43 | 0 | 0