## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF MADHU TG WATER SUPPLY SCHEME | SM/09909 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of DIMA TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar RWS,HQ-A.E | RWS Alipurduar - I Block,RWS Kalchini Block | ORD/000293/2021-2022 | 1991/ALD | 27/12/2021 | 27/03/2022 | GOBINDA BAGCHI | 20.87 | 0 | 0 | 72.14
2 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF MADHU TG WATER SUPPLY SCHEME | SM/09909 | Augmentation | Hiring of Motor cab for site of the Executive Engineer, Northern Mechanical Division-II, PHE Dte. |  |  | ORD/000693/2023-2024 | 201/AMSD | 28/07/2023 | 22/07/2024 | DILIP MAHATO | 4.16 | 0 | 0 | 0
3 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF MADHU TG WATER SUPPLY SCHEME | SM/09909 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of MADHU TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE | HQ-A.E | RWS Kalchini Block | ORD/000320/2021-2022 | 2196/ALD | 11/01/2022 | 11/04/2022 | NARENDRA BHADANI. | 20.88 | 21.06 | 100.88 | 50
4 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF MADHU TG WATER SUPPLY SCHEME | SM/09909 | Augmentation | Supply and Delivery of Al. armoured cable for Breakdown purpose at REJUVENATION OF MADHU TG WATER SUPPLY SCHEME in the dist. Alipurduar under,AMSD,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000337/2022-2023 | 226/AMSD | 21/07/2022 | 05/08/2022 | MUSTAFI CONCERN | 2.39 | 2.39 | 100 | 52
5 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF MADHU TG WATER SUPPLY SCHEME | SM/09909 | Augmentation | upply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION of MADHU TG PWSS, TW no .III in the district of ALIPURDUAR under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000804/2022-2023 | 388/NMD-II | 23/02/2023 | 25/03/2023 | HARAGOURI ENTERPRISE | 11.59 | 11.19 | 96.58 | 100
6 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF MADHU TG WATER SUPPLY SCHEME | SM/09909 | Augmentation | Quotation for new service connection at Madhu T.G, P/H no. III, Application no. 4003018858 |  |  | VCH/001471/2022-2023 | BP-94/22-23 | 25/11/2022 |  | WBSEDCL | 0.98 | 0 | 0 | 0
Total | [13 empty] | 60.88 | 34.65 | 56.91